DAILY FIELD REPORT - 03-03-2026

Project: Morena Conveyance North
Resident Engineer: 
Weather: High: 75°F, Low: 42°F, Sunny
Hours: 07:00 - 15:30

## Activities Detail

Marian Bear Park Curb Ramps - AR Concrete - Broke out and Fomred Curb Ramps

• Established traffic control, closing the #2 northbound lane and the entrance to Marian Bear Park, shifting traffic into the #1 northbound lane.
• Demolished the existing concrete curb ramps at locations CR-232 and CR-233 using skid steers equipped with hydraulic breakers.
• Loaded and hauled demolition debris off-site for disposal using a super 10 dump truck.
• Placed and compacted aggregate base in the prepared curb ramp areas.
• Set forms for the new concrete curb ramps at locations CR-232 and CR-233.
• Removed all traffic control devices and reopened the lane and park entrance to traffic at the end of the shift.

Hours: 7:00 AM - 3:30 PM

Manpower:

LL-03- Laborers - QTY 3 - 8 HRS EA - AR Concrete

LL-01- Superintendent - QTY 1 - 8 HRS EA - AR Concrete

LL-15- Cement Mason - QTY 2 - 8 HRS EA - AR Concrete

LL-02- Foreman - QTY 1 - 8 HRS EA - AR Concrete

Equipment:

LE-23- Super 10 End Dump Truck - QTY 1 - 8 HRS EA - AR Concrete

LE-01- Crew Truck - QTY 1 - 8 HRS EA - AR Concrete

LE-51- Pickup Truck - QTY 1 - 8 HRS EA - AR Concrete

LE-83- Equipment-Hauling Trailer - QTY 1 - 8 HRS EA - AR Concrete

LE-42- Utility Truck - QTY 1 - 8 HRS EA - AR Concrete

LE-125- Skid Steer - QTY 2 - 8 HRS EA - AR Concrete

Morena CN - OHLA - Sewer Repair

• Setup Traffic control in the southbound lanes of Town Centre South of Golden Haven. In the #1 lane shifting traffic into the #2 lane. 
• Set the blower up on executive in the median with the hose running over to the edge of the road where the manway is.
• Entered the 30" pipe through the manway on town centre at  1191+33 
• The crew started repair work, grinding and patching traveling south down the pipeline towards Nobel. 
• Made it to BO # 7 before turning back 
• picked up traffic control at 3:30 PM and ended the day.

Hours: 7:00 AM - 4:00 PM

Manpower:

LL-05- Journeyman - QTY 1 - 8.5 HRS EA - OHLA

LL-05- Journeyman - QTY 1 - 8.5 HRS EA - OHLA

LL-05- Journeyman - QTY 1 - 8.5 HRS EA - OHLA

LL-02- Foreman - QTY 1 - 9.5 HRS EA - OHLA

Equipment:

LE-111- Trailer Mounted Blower - QTY 1 - 8 HRS EA - United Rental - RENTAL

LE-01- Crew Truck - QTY 1 - 9.5 HRS EA - OHLA

## Consolidated Resources

| Resource | Pay Type | Class | Qty | Company | Total Hours |
| --- | --- | --- | --- | --- | --- |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 3 | AR Concrete | 24 |
| LL-01- Superintendent | CS - Cost | LR - Labor Regular Time | 1 | AR Concrete | 8 |
| LL-15- Cement Mason | CS - Cost | LR - Labor Regular Time | 2 | AR Concrete | 16 |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 1 | AR Concrete | 8 |
| LE-23- Super 10 End Dump Truck | CS - Cost | LR - Labor Regular Time | 1 | AR Concrete | 8 |
| LE-01- Crew Truck | CS - Cost | LR - Labor Regular Time | 1 | AR Concrete | 8 |
| LE-51- Pickup Truck | CS - Cost | LR - Labor Regular Time | 1 | AR Concrete | 8 |
| LE-83- Equipment-Hauling Trailer | CS - Cost | LR - Labor Regular Time | 1 | AR Concrete | 8 |
| LE-42- Utility Truck | CS - Cost | LR - Labor Regular Time | 1 | AR Concrete | 8 |
| LE-125- Skid Steer | CS - Cost | LR - Labor Regular Time | 2 | AR Concrete | 16 |
| LL-05- Journeyman | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-05- Journeyman | CS - Cost | LO - Labor Overtime | 1 | OHL NA | 0.5 |
| LL-05- Journeyman | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-05- Journeyman | CS - Cost | LO - Labor Overtime | 1 | OHL NA | 0.5 |
| LL-05- Journeyman | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-05- Journeyman | CS - Cost | LO - Labor Overtime | 1 | OHL NA | 0.5 |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-02- Foreman | CS - Cost | LO - Labor Overtime | 1 | OHL NA | 1.5 |
| LE-111- Trailer Mounted Blower | CS - Cost | LR - Labor Regular Time | 1 | United Rental | 8 |
| LE-01- Crew Truck | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LE-01- Crew Truck | CS - Cost | LO - Labor Overtime | 1 | OHL NA | 1.5 |