DAILY FIELD REPORT - 06-18-2026

Project: Morena Conveyance Northern
Location: Northbound Genesee Avenue
Resident Engineer: Terry West
Weather: High: 73°F, Low: 60°F, Wind: 4 mph NNW, Clear
Hours: 19:30 - 03:30

General Notes:

OHL performed a night closure on Genesee Avenue to excavate for and relocate cathodic protection test station wires. RJ Noble was on site to pave dig outs at la jolla village dr.

## Activities Detail

Northbound Genesee Avenue - OHL - Cathodic Protection Test Station Work

• OHL established a traffic control closure on northbound Genesee Avenue, just north of the SR-52 westbound off-ramp.

• The closure included the westbound off-ramp as well as the number one and number two lanes of northbound Genesee.

• Traffic was shifted into the westbound on-ramp turn lane to facilitate the work.

• The crew excavated to locate the cathodic protection (CP) test station wires at approximately Sta 406+16.

• The wires for Cathodic Test Station (CTS) 37A and CTS 36B were successfully located.

• A mini excavator was used to excavate a trench across both lanes to the sidewalk on the east side of Genesee Avenue.

• Conduit and wire were installed in the new trench from the mainline to the new test station location at the sidewalk, where a test station box is to be installed.

• Cathodic warning tape was placed in the trench.

• The trench was then backfilled and compacted.

• Both sets of wires were tested with a multimeter for millivolts and continuity, and both tested good.

• RJ Noble arrived on-site and paved the excavated trench area with hot mix asphalt.

• All work was completed by 2:00 AM; the crew began removing traffic control and cleared the site by 2:30 AM.

Manpower:

LL-03- Laborers - QTY 5 - 8 HRS EA - OHL

LL-04- Operator - QTY 2 - 8 HRS EA - OHL

Equipment:

Light Plant - QTY 1 - 8 HRS EA - OHL

LE-04- Mini Excavator - QTY 1 - 8 HRS EA - OHL

LE-23- Super 10 End Dump Truck - QTY 2 - 8 HRS EA - OHL

LE-01- Crew Truck - QTY 1 - 8 HRS EA - OHL

LE-41- Saw Cutter - QTY 1 - 8 HRS EA - OHL

SD MORENA CONVEYANCE - SOUTH PAVE CREW / SD MORENA CONVEYANCE - SOUTH GRIND CREW — GENESSEE AVE / NOBEL DR - UTC

• Digout Schedule — 6/18/2026:

Setup traffic control closing the North and Southbound lanes of traffic on Town Centre Dr at la jolla villiage and closed the # 2 lanes East and Westbound on La Jolla Village drive at Town Centre.

RJ noble completed the digouts shown below. Started at 7:30 PM and wrapped up paving at 2:45 AM.

Ran the street sweeper througout the work area

picked up traffic control at 3:15 AM

everybody off the jobsite at 3:30 AM

- DO #La Jolla Inside Lanes — 0.5' depth × 0W × 0L = 4,617 SF (173.1 tons)

Total: 4,617 SF / 173.1 Tons

• Material: 177.84 Tons 3/4" HM

Hours: 7:00 PM - 3:30 AM

Manpower:

LL-02- Foreman - QTY 1 - 8 HRS EA - RJ NOBLE

LL-04- Operator - QTY 9 - 8 HRS EA - RJ NOBLE

LL-03- Laborers - QTY 6 - 8 HRS EA - RJ NOBLE

LL-11- Teamster - QTY 1 - 7 HRS EA - DIII

LL-03- Laborers - QTY 2 - 8.5 HRS EA - RJ NOBLE

LL-11- Teamster - QTY 4 - 7.5 HRS EA - DIII

LL-04- Operator - QTY 1 - 7.5 HRS EA - PRSI

LL-03- Laborers - QTY 1 - 8 HRS EA - HUDSON

Equipment:

LE-13- Roller H222 - QTY 4 - 8 HRS EA - RJ NOBLE

LE-09- Skip Loader - QTY 1 - 8 HRS EA - RJ NOBLE

LE-125- Skid Steer - QTY 1 - 8 HRS EA - RJ NOBLE

LE-63- Asphalt Paver - QTY 2 - 8 HRS EA - RJ NOBLE

LE-51- Pickup Truck - QTY 5 - 8 HRS EA - RJ NOBLE

LE-01- Crew Truck - QTY 1 - 8 HRS EA - RJ NOBLE

LE-23- Super 10 End Dump Truck - QTY 1 - 7 HRS EA - DIII

LL-03- Laborers - QTY 3 - 8 HRS EA - RJ NOBLE - RENTAL

LE-157- Tack Truck - QTY 1 - 8 HRS EA - RJ NOBLE

LE-42- Utility Truck - QTY 2 - 8 HRS EA - RJ NOBLE

LE-19- Street sweeper - QTY 2 - 8 HRS EA - RJ NOBLE

LE-23- Super 10 End Dump Truck - QTY 4 - 7.5 HRS EA - DIII

LE-71- Pavement Grinder - QTY 1 - 7.5 HRS EA - PRSI

LE-19- Street sweeper - QTY 1 - 8 HRS EA - CTI

## Consolidated Resources

| Resource | Pay Type | Class | Qty | Company | Total Hours |
| --- | --- | --- | --- | --- | --- |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 5 | OHL | 40 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 2 | OHL | 16 |
| Light Plant | CS - Cost | LR - Labor Regular Time | 1 | OHL | 8 |
| LE-04- Mini Excavator | CS - Cost | LR - Labor Regular Time | 1 | OHL | 8 |
| LE-23- Super 10 End Dump Truck | CS - Cost | LR - Labor Regular Time | 2 | OHL | 16 |
| LE-01- Crew Truck | CS - Cost | LR - Labor Regular Time | 1 | OHL | 8 |
| LE-41- Saw Cutter | CS - Cost | LR - Labor Regular Time | 1 | OHL | 8 |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE | 8 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 9 | RJ NOBLE | 72 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 11 | RJ NOBLE | 88 |
| LL-11- Teamster | CS - Cost | LR - Labor Regular Time | 1 | DIII | 7 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 2 | RJ NOBLE | 1 |
| LL-11- Teamster | CS - Cost | LR - Labor Regular Time | 4 | DIII | 30 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | PRSI | 7.5 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | HUDSON | 8 |
| LE-13- Roller H222 | CS - Cost | LR - Labor Regular Time | 4 | RJ NOBLE | 32 |
| LE-09- Skip Loader | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE | 8 |
| LE-125- Skid Steer | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE | 8 |
| LE-63- Asphalt Paver | CS - Cost | LR - Labor Regular Time | 2 | RJ NOBLE | 16 |
| LE-51- Pickup Truck | CS - Cost | LR - Labor Regular Time | 5 | RJ NOBLE | 40 |
| LE-01- Crew Truck | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE | 8 |
| LE-23- Super 10 End Dump Truck | CS - Cost | LR - Labor Regular Time | 1 | DIII | 7 |
| LE-157- Tack Truck | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE | 8 |
| LE-42- Utility Truck | CS - Cost | LR - Labor Regular Time | 2 | RJ NOBLE | 16 |
| LE-19- Street sweeper | CS - Cost | LR - Labor Regular Time | 2 | RJ NOBLE | 16 |
| LE-23- Super 10 End Dump Truck | CS - Cost | LR - Labor Regular Time | 4 | DIII | 30 |
| LE-71- Pavement Grinder | CS - Cost | LR - Labor Regular Time | 1 | PRSI | 7.5 |
| LE-19- Street sweeper | CS - Cost | LR - Labor Regular Time | 1 | CTI | 8 |