DAILY FIELD REPORT - 12-29-2025

## Project: Morena Conveyance North

Location: Genesee, Town Centre, Noble, Executive Resident Engineer: Terry West

Weather: High: 73.3°F, Low: 46°F, Cloudy, Overcast, Windy Hours: 07:00 - 17:30

# Activities Detail

## Town Centre Dr to Executive — 501+73 to 548+03

- SRK Engineering blew water from the 4-inch fiber optic conduit and pull box between Sta 501+73 and Sta 507+62.

- A mouse was blown through the conduit, followed by a mandrel pull through the same segment.

- The mandrel pulling sequence was repeated for the conduit segment between Sta 517+67 and Sta 507+62.

- An attempt to pull the mandrel between Sta 537+33 and Sta 517+67 was not completed.

- Water could not be removed from the conduit on this segment; the obstruction was noted as potentially caused by installed sweeps.

- Water was blown out of the conduit between Sta 548+03 and Sta 537+33.

- The mandrel pull for the segment from Sta 548+03 to Sta 537+33 was scheduled for the following day.

Hours: 7:00 AM - 3:30 PM

Manpower:

LL-02- Foreman - QTY 1 - 8 HRS EA - SRK Engineering LL-03- Laborers - QTY 1 - 8 HRS EA - SRK Engineering

Equipment:

LE-42- Utility Truck - QTY 1 - 8 HRS EA - SRK Engineering LE-110- Compressor - QTY 1 - 8 HRS EA - SRK Engineering LE-01- Crew Truck - QTY 1 - 8 HRS EA - SRK Engineering

## Marian Bear Park — 395+87 to 396+52

- Backfilling was performed around the vault for Blowoff #5, bringing the northeast side to approximately 80% completion.

- Fiber optic conduit was extended and connected into the pull box from Sta. 395+87 to Sta. 396+52.

- 28 LF of 8-inch C900 pipe was installed for the blowoff drain line.

- Cathodic protection wires were raised to finished grade elevation.

- Base material was placed and compacted within the excavation.

Hours: 7:00 AM - 3:30 PM

Manpower:

LL-03- Laborers - QTY 5 - 8 HRS EA - OHL NA LL-04- Operator - QTY 1 - 8 HRS EA - OHL NA

LL-01- Superintendent - QTY 1 - 8 HRS EA - OHL NA

Equipment:

LE-51- Pickup Truck - QTY 1 - 8 HRS EA - OHL NA LE-109- Excavator - QTY 1 - 8 HRS EA - OHL NA

LE-14- Water Truck F750 - QTY 1 - 8 HRS EA - OHL NA

## Blow Off #7

- Backfill was placed at Blow Off #7 to an elevation 2 feet below finished grade.

- A 4-inch camlock pipe was installed.

- The backfill material was placed with an excavator and compacted with a wacker.

- Work at Blow Off #7 was completed at 13:00.

- The crew relocated to air vac vault #11.

Hours: 7:00 AM - 3:30 PM

Manpower:

LL-02- Foreman - QTY 1 - 8 HRS EA - OHL NA

LL-03- Laborers - QTY 2 - 8 HRS EA - OHL NA LL-04- Operator - QTY 1 - 8 HRS EA - OHL NA

Equipment:

LE-109- Excavator - QTY 1 - 8 HRS EA - OHL NA

LE-81- Mechanical Wacker - QTY 1 - 8 HRS EA - OHL NA

## Genesee - OHLA - Pipe Joint Grout Repair — 471+25 to 495+87

- OHL's crew performed joint grout repair inside the 48-inch pipeline from Genesee Station 471+25 to Station 495+87.

- Grout at each joint was inspected for cracks and chips and repaired.

- Work was performed from the manhole at Lombard and Nobel to Station 488+66, which was the limit of previously completed repairs.

- A CCTV inspection of the pipeline by NorCal Pipeline was scheduled for the following day.

Hours: 7:00 AM - 2:30 PM

Manpower:

LL-02- Foreman - QTY 1 - 7 HRS EA - OHL

LL-15- Cement Mason - QTY 2 - 7 HRS EA - OHL

Equipment:

LE-51- Pickup Truck - QTY 1 - 7 HRS EA - OHL

LE-111- Trailer Mounted Blower - QTY 1 - 7 HRS EA - OHL

## Governor and Genesee — Curb Ramps 247 and 248

- AR Concrete removed protective plastic covering from curb ramp locations.

- Saturated soil was removed from curb ramp locations and replaced with base material.

- The replacement base material was compacted.

- Formwork for the curb ramps was reinstalled.

- Concrete placement was scheduled for the following morning.

- The Contractor stated the work to remove and replace saturated soil would be documented as Time and Materials (T&M) work attributed to a prior rain event.

Hours: 7:00 AM - 3:30 PM

Manpower:

LL-02- Foreman - QTY 1 - 8 HRS EA - AR Concrete / HMS LL-03- Laborers - QTY 3 - 8 HRS EA - AR Concrete / HMS

LL-15- Cement Mason - QTY 4 - 8 HRS EA - AR Concrete / HMS LL-11- Teamster - QTY 1 - 5 HRS EA - AR Concrete / HMS

Equipment:

LE-51- Pickup Truck - QTY 1 - 8 HRS EA - AR CONCRETE LE-42- Utility Truck - QTY 1 - 8 HRS EA - AR CONCRETE Vibratory Plate - QTY 1 - 8 HRS EA - AR CONCRETE

LE-81- Mechanical Wacker - QTY 1 - 8 HRS EA - AR CONCRETE LE-01- Crew Truck - QTY 1 - 8 HRS EA - AR CONCRETE

LE-125- Skid Steer - QTY 1 - 8 HRS EA - AR CONCRETE

# Consolidated Resources

| Resource | Pay Type | Class | Qty | Company | Total Hours |
| --- | --- | --- | --- | --- | --- |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 1 | SRK Engineering | 8 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | SRK Engineering | 8 |
| LE-42- Utility Truck | CS - Cost | LR - Labor Regular Time | 1 | SRK Engineering | 8 |
| LE-110- Compressor | CS - Cost | LR - Labor Regular Time | 1 | SRK Engineering | 8 |
| LE-01- Crew Truck | CS - Cost | LR - Labor Regular Time | 1 | SRK Engineering | 8 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 5 | OHL NA | 40 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LE-51- Pickup Truck | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LE-109- Excavator | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LE-14- Water Truck F750 | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-01- Superintendent | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 2 | OHL NA | 16 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LE-109- Excavator | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LE-81- Mechanical Wacker | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 1 | OHL | 7 |
| LL-15- Cement Mason | CS - Cost | LR - Labor Regular Time | 2 | OHL | 14 |
| LE-51- Pickup Truck | CS - Cost | LR - Labor Regular Time | 1 | OHL | 7 |
| LE-111- Trailer Mounted Blower | CS - Cost | LR - Labor Regular Time | 1 | OHL | 7 |
| LL-02- Foreman | EW - Extra Work | LR - Labor Regular Time | 1 | AR CONCRETE | 8 |
| LL-03- Laborers | EW - Extra Work | LR - Labor Regular Time | 3 | AR CONCRETE | 24 |
| LL-15- Cement Mason | EW - Extra Work | LR - Labor Regular Time | 4 | AR CONCRETE | 32 |
| LL-11- Teamster | EW - Extra Work | LR - Labor Regular Time | 1 | AR CONCRETE | 5 |
| LE-51- Pickup Truck | EW - Extra Work | LR - Labor Regular Time | 1 | AR CONCRETE | 8 |
| LE-42- Utility Truck | EW - Extra Work | LR - Labor Regular Time | 1 | AR CONCRETE | 8 |
| Vibratory Plate | EW - Extra Work | LR - Labor Regular Time | 1 | AR CONCRETE | 8 |
| LE-81- Mechanical Wacker | EW - Extra Work | LR - Labor Regular Time | 1 | AR CONCRETE | 8 |
| LE-01- Crew Truck | EW - Extra Work | LR - Labor Regular Time | 1 | AR CONCRETE | 8 |

| LE-125- Skid Steer | EW - Extra Work | LR - Labor Regular Time | 1 | AR CONCRETE | 8 |
| --- | --- | --- | --- | --- | --- |