DAILY FIELD REPORT - 03-25-2026

Project: Morena Conveyance North
Location: Both pipelines on town centre to executive are buttoned up, the 30" is full and the 48" is being filled. Paving is taking place on genesee at the crossings under the SR-52.
Resident Engineer: Terry West
Weather: High: 74°F, Low: 56°F, Wind: WNW 6 mph, Sunny
Hours: 07:00 - 15:30

## Activities Detail

Nobel and Towne Centre + Genesee @ SR52 - OHLA - Hydrotest Prep, & Paving

• Set up traffic control at Nobel and Towne Centre.
• Drained lines from rose canyon to town centre into the lines from town centre to executive in both 48 and 30" lines
• The crew went to the SR-52 on genesee to assist with grading and paving.
• at 2:30 the foreman and a laborer left the paving operation to pick up the traffic control and closed the manhole at town centre and noble

Hours: 6:30 AM - 3:30 PM

Manpower:

LL-03- Laborers - QTY 1 - 8.5 HRS EA - OHL NA

LL-02- Foreman - QTY 1 - 9.5 HRS EA - OHL NA

Equipment:

LE-72- Arrow Board - QTY 1 - 8 HRS EA - OHL NA

LE-01- Crew Truck - QTY 1 - 8 HRS EA - OHL NA

LE-32- Skytrak Forklift - QTY 1 - 8 HRS EA - OHL NA

Genesse, Rose Canyon, Sunview Yard - OHLA - Paving & Site Maintenance

• Established traffic control in the northbound #2 lane on Genesse for trench paving operations.
• Prepared trenches for paving and placed and compacted 17 tons of 3/4-inch asphalt concrete for trench restoration.
• Base paved the #2 lane at crossings
• Monitored the dewatering system at the Rose Canyon location and refueled the generator.
• Installed silt fence along the perimeter of the Sunview Yard.
• Performed Best Management Practice (BMP) maintenance throughout the project site.

Hours: 6:30 AM - 4:30 PM

Manpower:

LL-03- Laborers - QTY 1 - 9 HRS EA - OHLA

LL-12- Carpenter - QTY 1 - 8.5 HRS EA - OHLA

LL-03- Laborers - QTY 1 - 9.5 HRS EA - OHLA

LL-02- Foreman - QTY 1 - 9.5 HRS EA - OHLA

LL-03- Laborers - QTY 1 - 8.5 HRS EA - OHLA

LL-03- Laborers - QTY 1 - 8 HRS EA - OHLA

LL-12- Carpenter - QTY 1 - 9 HRS EA - OHLA

Equipment:

LE-23- Super 10 End Dump Truck - QTY 1 - 8 HRS EA - OHL NA - RENTAL

LE-51- Pickup Truck - QTY 1 - 8 HRS EA - OHL NA

LE-159- Roller - QTY 1 - 8 HRS EA - Herc - RENTAL

LE-42- Utility Truck - QTY 1 - 8 HRS EA - OHL NA

LE-126- Baker Tank - QTY 1 - 8 HRS EA - Prime - RENTAL

LE-70- Generator - QTY 1 - 8 HRS EA - United Rentals - RENTAL

LE-04- Mini Excavator - QTY 1 - 8 HRS EA - Herc - RENTAL