DAILY FIELD REPORT - 03-26-2026

Project: Morena Conveyance North
Resident Engineer: Terry West
Weather: 
Hours: 07:00 - 15:30

## Activities Detail

Genesee, Yard, Rose Canyon - OHLA - Trench Prep, Paving & Site Maintenance

• Setup TrAffic control in the Southbound #1 lane of Genesee at marian bear park  
• Prepped trenches along Genesee for base and asphalt.
• Subcontractor A7 Trucking paved with 17 tons of 3/4 inch asphalt.
• Performed BMP maintenance throughout the job site.
• Monitored the dewatering system at Rose Canyon.
• Fueled up the generator.
•  picked up traffic control at 4:15

Hours: 6:30 AM - 3:00 PM

Manpower:

LL-03- Laborers - QTY 1 - 9.5 HRS EA - OHL NA

LL-03- Laborers - QTY 1 - 8 HRS EA - OHL NA

LE-01- Crew Truck - QTY 1 - 8 HRS EA - Prime

LL-02- Foreman - QTY 1 - 8.5 HRS EA - OHL NA

LL-12- Carpenter - QTY 1 - 9.5 HRS EA - OHL NA

LL-04- Operator - QTY 1 - 8 HRS EA - OHL NA

LL-03- Laborers - QTY 1 - 9 HRS EA - OHL NA

Equipment:

LE-51- Pickup Truck - QTY 1 - 8 HRS EA - OHL NA

LE-159- Roller - QTY 1 - 4 HRS EA - Herc - RENTAL

LE-126- Baker Tank - QTY 1 - 8 HRS EA - Prime - RENTAL

LE-09- Skip Loader - QTY 1 - 8 HRS EA - Herc - RENTAL

LE-01- Crew Truck - QTY 1 - 8 HRS EA - OHL NA

LE-04- Mini Excavator - QTY 1 - 8 HRS EA - Herc - RENTAL

LE-70- Generator - QTY 1 - 8 HRS EA - United Rentals - RENTAL

LE-23- Super 10 End Dump Truck - QTY 1 - 8 HRS EA - Prime - RENTAL

Towne Centre & Genesee - OHLA - Traffic Control & Paving

• Set up traffic control on Towne Centre from Renaissance to Nobel.
Connected phase 3 to phase 4 to contitnue dewatering phase 3 as well as filling phase 4
• Performed removal of cold patch and dirt on Genesee helping brandons crew
• Made grade, applied asphalt tack coat to the sides, and paved four areas in the # 1 Northbound lane of genesee near the south end of cal trans ROW
• Picked up traffic control at Nobel.

Hours: 6:30 AM - 3:00 PM

Manpower:

LL-03- Laborers - QTY 1 - 8 HRS EA - OHL NA

LL-02- Foreman - QTY 1 - 9 HRS EA - OHL NA

Equipment:

LE-04- Mini Excavator - QTY 1 - 8 HRS EA - Here - RENTAL

LE-72- Arrow Board - QTY 1 - 8 HRS EA - OHL NA

LE-01- Crew Truck - QTY 1 - 8 HRS EA - OHL NA

LE-28- Water Truck - QTY 1 - 8 HRS EA - Here - RENTAL

LE-125- Skid Steer - QTY 1 - 8 HRS EA - Here - RENTAL

## Consolidated Resources

| Resource | Pay Type | Class | Qty | Company | Total Hours |
| --- | --- | --- | --- | --- | --- |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 1 | OHL NA | 1.5 |
| LE-01- Crew Truck | CS - Cost | LR - Labor Regular Time | 1 |  | 8 |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-02- Foreman | CS - Cost | LO - Labor Overtime | 1 | OHL NA | 0.5 |
| LL-12- Carpenter | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-12- Carpenter | CS - Cost | LO - Labor Overtime | 1 | OHL NA | 1.5 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LE-51- Pickup Truck | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LE-159- Roller | CS - Cost | LR - Labor Regular Time | 1 | Herc | 4 |
| LE-126- Baker Tank | CS - Cost | LR - Labor Regular Time | 1 |  | 8 |
| LE-09- Skip Loader | CS - Cost | LR - Labor Regular Time | 1 | Herc | 8 |
| LE-01- Crew Truck | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LE-04- Mini Excavator | CS - Cost | LR - Labor Regular Time | 1 | Herc | 8 |
| LE-70- Generator | CS - Cost | LR - Labor Regular Time | 1 | United Rentals | 8 |
| LE-23- Super 10 End Dump Truck | CS - Cost | LR - Labor Regular Time | 1 |  | 8 |
| LE-04- Mini Excavator | CS - Cost | LR - Labor Regular Time | 1 | Here | 8 |
| LE-72- Arrow Board | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LE-28- Water Truck | CS - Cost | LR - Labor Regular Time | 1 | Here | 8 |
| LE-125- Skid Steer | CS - Cost | LR - Labor Regular Time | 1 | Here | 8 |