DAILY FIELD REPORT - 03-05-2026

Project: Morena Conveyance North
Resident Engineer: 
Weather: High: 71°F, Low: 50°F, Sunny
Hours: 07:00 - 15:30

## Activities Detail

Town Centre Dr. - OHLA - Prepping BO # 7 to Pump Water Through

• Established a traffic control closure on Town Centre Dr., closing the #2 lane beginning north of Blow-off (BO) #7 and extending 40 feet past the structure.
• Opened BO #7 and prepared for vault entry by setting up a blower, ladder, and air monitoring equipment.
• Unbolted and removed the 30-inch and 48-inch blind flanges from the piping within the vault. A forklift was utilized to handle the flanges.
• Work was performed to prepare for the dewatering of the final 50 feet of the 30-inch and 48-inch pipelines.
• Removed the traffic control setup at the end of the shift.

Hours: 7:00 AM - 3:30 PM

Manpower:

LL-02- Foreman - QTY 1 - 8 HRS EA - OHL NA

LL-03- Laborers - QTY 3 - 8 HRS EA - OHL NA

Equipment:

LE-01- Crew Truck - QTY 1 - 8 HRS EA - OHL NA

LE-32- Skytrak Forklift - QTY 1 - 8 HRS EA - OHL NA

Genesee - OHLA - Cold Patch settlements and potholes

• Attended required railway training at the Jutland office.
• Mobilized to the Marian Bear Park work area.
• Completed final cleanup and removal of tree branches.
• Inspected the trench alignment and applied cold patch material to repair observed settlements and potholes at various locations.

Hours: 7:00 AM - 3:30 PM

Manpower:

LL-03- Laborers - QTY 3 - 8 HRS EA - OHL NA

LL-04- Operator - QTY 1 - 8 HRS EA - OHL NA

LL-02- Foreman - QTY 1 - 8 HRS EA - OHL NA

Equipment:

LE-51- Pickup Truck - QTY 1 - 8 HRS EA - OHL NA

LE-23- Super 10 End Dump Truck - QTY 1 - 8 HRS EA - OHL NA

LE-72- Arrow Board - QTY 1 - 8 HRS EA - OHL NA

## Consolidated Resources

| Resource | Pay Type | Class | Qty | Company | Total Hours |
| --- | --- | --- | --- | --- | --- |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 3 | OHL NA | 24 |
| LE-01- Crew Truck | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LE-32- Skytrak Forklift | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 3 | OHL NA | 24 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LE-51- Pickup Truck | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LE-23- Super 10 End Dump Truck | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LE-72- Arrow Board | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |