DAILY FIELD REPORT - 04-01-2026

Project: Morena Conveyance North
Resident Engineer: Terry West
Weather: 
Hours: 07:00 - 15:30

## Activities Detail

Marian Bear Park - GC fence - Caltrans Fence Installation

• GC fence poured concrete for the last five posts at the north end of the Caltrans fence.
• Crew began installing chain link on posts that were poured the previous day.
• By end of day, chain link was hung on 50% of the posts but was not pulled tight.
• The crew finished work at 3:30 PM, with the chain link fence approximately 60% complete.

Hours: 7:00 AM - 3:30 PM

Manpower:

LL-03- Laborers - QTY 2 - 8 HRS EA - GC Fence

Equipment:

LE-125- Skid Steer - QTY 1 - 8 HRS EA - E-fence

LE-51- Pickup Truck - QTY 1 - 8 HRS EA - E-fence

Bear Park & Towne Centre - OHLA - Vault Work & Pipe Draining

• GF not on site today
• The crew went to the Towne Centre and Nobel, setup traffic control in the southbound # 2 lane to continue draining the both pipelines into the phase 4 pipe.
• a crew worked in BO # 5 bolting up blind  a blind flange but could not finish the 2nd blind due to lack of bolts
• Dewatering at rose canyon continued, a laborer went there to check on the generator and add gas. 
• The dry sump drain line inside the vault was not seen from inside the vault, after chipping out some concrete and base they were able to locate it and began planning the connection from the drain tap. 
•Pulled the traffic control from nobel and town centre

Hours: 6:30 AM - 3:00 PM

Manpower:

LL-03- Laborers - QTY 1 - 8 HRS EA - OHLA

LL-04- Operator - QTY 1 - 8 HRS EA - OHLA

LL-02- Foreman - QTY 1 - 9 HRS EA - OHLA

LL-03- Laborers - QTY 1 - 6 HRS EA - OHLA

Equipment:

LE-125- Skid Steer - QTY 1 - 8 HRS EA - Herc - RENTAL

LE-01- Crew Truck - QTY 1 - 8 HRS EA - OHLA

LE-72- Arrow Board - QTY 1 - 8 HRS EA - OHLA

LE-23- Super 10 End Dump Truck - QTY 1 - 8 HRS EA - Herc - RENTAL

LE-28- Water Truck - QTY 1 - 8 HRS EA - Herc - RENTAL

## Consolidated Resources

| Resource | Pay Type | Class | Qty | Company | Total Hours |
| --- | --- | --- | --- | --- | --- |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 2 | GC Fence | 16 |
| LE-125- Skid Steer | CS - Cost | LR - Labor Regular Time | 1 | E-fence | 8 |
| LE-51- Pickup Truck | CS - Cost | LR - Labor Regular Time | 1 | E-fence | 8 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-02- Foreman | CS - Cost | LO - Labor Overtime | 1 | OHL NA | 1 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 6 |
| LE-125- Skid Steer | CS - Cost | LR - Labor Regular Time | 1 | Herc | 8 |
| LE-01- Crew Truck | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LE-72- Arrow Board | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LE-23- Super 10 End Dump Truck | CS - Cost | LR - Labor Regular Time | 1 | Herc | 8 |
| LE-28- Water Truck | CS - Cost | LR - Labor Regular Time | 1 | Herc | 8 |