DAILY FIELD REPORT - 04-13-2026

Project: Morena Conveyance North
Location: Executive, Decoro/Genesee, Water Reclamation Plant, Appleton St.
Resident Engineer: Terry West
Weather: High: 66°F, Low: 53°F, Wind: W 8 mph, Sunny
Hours: 07:00 - 15:30

General Notes:

Picket Fences continues working at Executive in the median, OHLA is working at the water reclamation plant, and AR Concrete had a cancellation and called to come do the curb ramp and part of the cross gutter at Decoro and Genesee. During the night shift OHLA worked at Appleton to remove the highline. no work at Marion Bear Park today no work on the hydro test for phase 4 today

## Activities Detail

Decoro and Genesee - OHLA - Curb Ramp & Cross Gutter Demolition and Forming

• OHLA mobilized to the southwest corner of Decoro and Genesee at 10:00 AM following a cancellation on another project.
• A lane closure was set up, closing the eastbound right-hand turn lane and the southbound #2 lane shoulder.
• Crews demolished the existing curb ramp and a section of the cross gutter equal to one lane width.
• Set forms for the new curb ramp and cross gutter.
• AR concrete left for the day at 5:30
• The OHLA traffic control crew returned to set 3 missing signs;   but they need to bring a few more signs required tomorrow morning.
• OHLA traffic control crew left the site at 6:00 p.m.

Hours: 10:00 AM - 5:30 PM

Manpower:

LL-02- Foreman - QTY 1 - 8 HRS EA - AR Concrete

LL-01- Superintendent - QTY 1 - 8 HRS EA - AR Concrete

LL-15- Cement Mason - QTY 2 - 8 HRS EA - AR Concrete

LL-03- Laborers - QTY 3 - 8 HRS EA - AR Concrete

Equipment:

LE-23- Super 10 End Dump Truck - QTY 1 - 8 HRS EA - AR Concrete

LE-125- Skid Steer - QTY 2 - 8 HRS EA - AR Concrete

LE-51- Pickup Truck - QTY 1 - 8 HRS EA - AR Concrete

LE-01- Crew Truck - QTY 1 - 8 HRS EA - AR Concrete

LE-83- Equipment-Hauling Trailer - QTY 1 - 8 HRS EA - AR Concrete

LE-42- Utility Truck - QTY 1 - 8 HRS EA - AR Concrete

Executive - OHLA & Picket Fences - Irrigation & Utility Investigation

• OHLA set up a traffic control closure in the #1 lane for both eastbound and westbound traffic, shifting vehicles to the #2 lane.
• From 7:00 AM to 10:30 AM, an OHLA crew excavated at the west end of the median, along the south edge, to locate a water main connection.
• The crew dug 3.5 feet deep for a length of 6 feet east of two existing casings but did not locate the main.
• Picket Fences' crew arrived at 10:30 AM and worked until 3:00 PM installing the irrigation system.
• The crew performed hand excavation for lateral lines and a valve box.
• Crew installed irrigation valves, placed the valve box, and backfilled the main irrigation line and two lateral lines along the north edge of the median.
• Reclaimed Water warning tape was placed above the pipe before backfilling to grade and compacting.
• Picket Fences wrapped up for the day and was gone at 3:00 p.m.
• OHLA removed the traffic control at 3:30 PM.
• At 4:30 PM, an OHLA crew performed 15 minutes of BMP maintenance.

Hours: 6:00 AM (OHLA only) 7:00 AM - 4:45 PM

Manpower:

LL-03- Laborers - QTY 2 - 4.5 HRS EA - Pickette Fences

LL-03- Laborers - QTY 1 – 3.5 HRS EA - OHL NA

LL-05- Operator - QTY 1 – 3.5 HRS EA - OHL NA

Equipment:

LE-70- Generator - QTY 1 - 8 HRS EA - Prime

LE-51- Pickup Truck - QTY 2 - 8 HRS EA - Prime

Appleton Street - OHL LA - High Line Removal & Cleanup

• Crew set up traffic control in the northbound number two lane on genesee at appleton.
• The high line at the fire hydrant was disassembled.
• Crew removed the temporary piping from the gutter.
• A skid steer with a sweeper attachment was used to clean the street.
• All traffic control was removed at the end of the day.

Hours: 6:00 PM - 2:30 AM

Manpower:

LL-02- Foreman - QTY 1 - 9 HRS EA - OHL

LL-05- Journeyman - QTY 1 - 8 HRS EA - OHL

Equipment:

LE-32- Skytrak Forklift - QTY 1 - 8 HRS EA - Herc - RENTAL

LE-01- Crew Truck - QTY 1 - 8 HRS EA - OHL

LE-72- Arrow Board - QTY 1 - 8 HRS EA - OHL

LE-125- Skid Steer - QTY 1 - 8 HRS EA - OHL LA

Blow-off #9 & Sunrunner Yard - OHLA - Pipe Work & Site Support

• Set up traffic control for the picket fence
• Backfilled 30-inch pipe at Blow-off #9 (dished head).
• Accepted trench shields for the winch and blow-off.
• Excavated down to the knockouts at Blow-off #9.
• Loaded out trucks and accepted materials at the Sunrunner yard.
• Completed BMP maintenance across the site.
• Removed traffic control for the picket fence at the end of the day.

Hours: 6:30 AM - 5:30 PM

Manpower:

LL-04- Operator - QTY 1 - 8 HRS EA - OHLA

LL-03- Laborers - QTY 1 - 11.5 HRS EA - OHLA

LL-02- Foreman - QTY 1 - 11.5 HRS EA - OHLA

LL-03- Laborers - QTY 1 - 9 HRS EA - OHLA

LL-11- Teamster - QTY 1 - 9 HRS EA - OHLA

LL-03- Laborers - QTY 1 - 11 HRS EA - OHLA

Equipment:

LE-51- Pickup Truck - QTY 1 - 8 HRS EA - OHL NA

LE-109- Excavator - QTY 1 - 8 HRS EA - Herc - RENTAL

## Consolidated Resources

| Resource | Pay Type | Class | Qty | Company | Total Hours |
| --- | --- | --- | --- | --- | --- |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 1 | AR Concrete | 8 |
| LL-01- Superintendent | CS - Cost | LR - Labor Regular Time | 1 | AR Concrete | 8 |
| LL-15- Cement Mason | CS - Cost | LR - Labor Regular Time | 2 | AR Concrete | 16 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 3 | AR Concrete | 24 |
| LE-23- Super 10 End Dump Truck | CS - Cost | LR - Labor Regular Time | 1 | AR Concrete | 8 |
| LE-125- Skid Steer | CS - Cost | LR - Labor Regular Time | 2 | AR Concrete | 16 |
| LE-51- Pickup Truck | CS - Cost | LR - Labor Regular Time | 1 | AR Concrete | 8 |
| LE-01- Crew Truck | CS - Cost | LR - Labor Regular Time | 1 | AR Concrete | 8 |
| LE-83- Equipment-Hauling Trailer | CS - Cost | LR - Labor Regular Time | 1 | AR Concrete | 8 |
| LE-42- Utility Truck | CS - Cost | LR - Labor Regular Time | 1 | AR Concrete | 8 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 2 | Pickette Fences | 9 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 2 | OHL NA | 0.5 |
| LE-70- Generator | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LE-51- Pickup Truck | CS - Cost | LR - Labor Regular Time | 2 | OHL NA | 16 |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 1 | OHL | 8 |
| LL-02- Foreman | CS - Cost | LO - Labor Overtime | 1 | OHL | 1 |
| LL-05- Journeyman | CS - Cost | LR - Labor Regular Time | 1 | OHL | 8 |
| LL-05- Journeyman | CS - Cost | LR - Labor Regular Time | 1 | OHL | 8 |
| LL-05- Journeyman | CS - Cost | LR - Labor Regular Time | 1 | OHL | 8 |
| LL-05- Journeyman | CS - Cost | LR - Labor Regular Time | 1 | OHL | 8 |
| LE-32- Skytrak Forklift | CS - Cost | LR - Labor Regular Time | 1 | Herc | 8 |
| LE-01- Crew Truck | CS - Cost | LR - Labor Regular Time | 1 | OHL | 8 |
| LE-72- Arrow Board | CS - Cost | LR - Labor Regular Time | 1 | OHL | 8 |
| LE-125- Skid Steer | CS - Cost | LR - Labor Regular Time | 1 | OHL LA | 8 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 1 | OHL NA | 3.5 |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-02- Foreman | CS - Cost | LO - Labor Overtime | 1 | OHL NA | 3.5 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 1 | OHL NA | 1 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 1 | OHL NA | 3.5 |
| LL-11- Teamster | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-11- Teamster | CS - Cost | LO - Labor Overtime | 1 | OHL NA | 1 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 1 | OHL NA | 3 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 1 | OHL NA | 1 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 1 | OHL NA | 3 |
| LE-51- Pickup Truck | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LE-109- Excavator | CS - Cost | LR - Labor Regular Time | 1 | Herc | 8 |
| LE-51- Pickup Truck | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |