DAILY FIELD REPORT - 04-20-2026

Project: Morena Conveyance North
Resident Engineer: Terry West
Weather: High: 68°F, Low: 52°F, Wind: W 10 mph, Cloudy
Hours: 07:00 - 15:30

## Activities Detail

Rose Canyon - OHL - Pipe Coating & Wrapping

• Crew wrapped pipe and welds on connection pieces for the tie-in between Phase 2 and Phase 3.
• Crew stripped existing coating back from the weld areas to remove burnt or cut sections.
• The pipe surface was cleaned to SSPC-SP 2 or SP 3 standards prior to wrapping.
• A 50% or 2-inch overlap was used for the wrap application.
• The crew spent most of the day cleaning the pipe after it was moved out of the way for a crane that was relocated to the area around 9:00 AM.

Hours: 7:00 AM - 3:30 PM

Manpower:

LL-03- Laborers - QTY 3 - 8 HRS EA - OHL

Equipment:

LE-51- Pickup Truck - QTY 1 - 8 HRS EA - OHL

LE-27- JLG Lift - QTY 1 - 8 HRS EA - OHL

Town Center & AV 13 - OHL - Sidewalk Demolition & Forming

• Set up traffic control in the #2 northbound lane.
• Crew removed cold mix that was in place as the sidewalk and curb and gutter for replacement with concrete.
• Additional chipped and cracked concrete panels were identified for removal and replacement.
• Crew pulled string lines and set forms for curb and gutter.
• The curb and gutter pour is scheduled for tomorrow, and the sidewalk pour will follow the day after.
• The crew wrapped up at the work site at 2:30 PM, returned to the yard, and were gone for the day.

Hours: 6:00 AM - 3:00 PM

Manpower:

LL-02- Foreman - QTY 1 - 8 HRS EA - OHL NA

LL-03- Laborers - QTY 3 - 8 HRS EA - OHL NA

Equipment:

LE-51- Pickup Truck - QTY 1 - 8 HRS EA - Prime

LE-04- Mini Excavator - QTY 0 - 0 HRS EA - Prime

LE-70- Generator - QTY 0 - 0 HRS EA - Prime

LE-23- Super 10 End Dump Truck - QTY 1 - 8 HRS EA - Prime

Genesee & Executive - Picket Fences - Trenching & Pipeline Investigation

• At Genesee between Centurion and Decoro, the crew finished digging trenches along the east and west sides of the median.
• Crew began digging sections for valve box installations.
• The foreman went to a supply store and picked up backflow preventers and meters.
• At Executive, the crew met with a rooter company to attempt to clear existing pipeline sleeves. The attempt was unsuccessful, and the street will need to be excavated.
• An incorrect USA ticket was called in because OHL called it in for Picket Fences' work area, I explained to them that each contractor needs to call on their own USA but they did not do so. SDG&E arrived but would not perform the remark because the excavating contractor must call in their own ticket. This will delay the start of the 48-hour clock.
• The crew finished for the day at 3:30 PM.

Hours: 7:00 AM - 3:30 PM

Manpower:

LL-03- Laborers - QTY 1 - 8 HRS EA - Picket Fences

LL-04- Operator - QTY 1 - 8 HRS EA - Picket Fences

LL-03- Laborers - QTY 2 - 8 HRS EA - Picket Fences

Office Manager - QTY 1 - 8 HRS EA - Picket Fences

LL-02- Foreman - QTY 1 - 8 HRS EA - Picket Fences

## Consolidated Resources

| Resource | Pay Type | Class | Qty | Company | Total Hours |
| --- | --- | --- | --- | --- | --- |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 3 | OHL | 24 |
| LE-51- Pickup Truck | CS - Cost | LR - Labor Regular Time | 1 | OHL | 8 |
| LE-27- JLG Lift | CS - Cost | LR - Labor Regular Time | 1 | OHL | 8 |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 3 | OHL NA | 24 |
| LE-51- Pickup Truck | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LE-23- Super 10 End Dump Truck | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | Picket Fences | 8 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | Picket Fences | 8 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 2 | Picket Fences | 16 |
| Office Manager | CS - Cost | LR - Labor Regular Time | 1 | Picket Fences | 8 |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 1 | Picket Fences | 8 |