DAILY FIELD REPORT - 04-21-2026

Project: Morena Conveyance North
Resident Engineer: Terry West
Weather: High: 70°F, Low: 53°F, Wind: W 10 mph, Sunny
Hours: 07:00 - 15:30

## Activities Detail

Towne Center in front of UTC Mall - Traffic Control & Formwork

•   Set up traffic control in the number 2 northbound lane on Towne Center in front of the UTC Mall.
Shifted traffic into the number 1 lane.
•   Set forms for the curb and gutter before the concrete pour.
*   Placed and finished new concrete curb and gutter for the full length of the replacement area.
*   Demolished one remaining cracked concrete sidewalk panel adjacent to the new curb and gutter.
*   Implemented traffic control for the work area.
*   Identified aged and previously damaged sidewalk panels for demolition and replacement under the additional sidewalk bid item 
*   Directed the contractor to use cold mix for the slot trench backfill instead of the proposed base material. 
*   Directed the contractor to defer the concrete placement for the newly demolished panel area to consolidate it with upcoming pours.
*   Confirmed with the contractor that all subgrade must be compacted prior to concrete placement. Contractor acknowledged the requirement and stated a plate compactor would be brought to the site.
Hours: 6:00 AM - 3:00 PM

Manpower:

LL-03- Laborers - QTY 3 - 8 HRS EA - OHL NA

LL-02- Foreman - QTY 2 - 8 HRS EA - OHL NA

LL-04- Operator - QTY 1 - 8 HRS EA - OHL NA

Equipment:

LE-42- Utility Truck - QTY 1 - 8 HRS EA - OHL NA

LE-04- Mini Excavator - QTY 1 - 8 HRS EA - OHL NA

LE-23- Super 10 End Dump Truck - QTY 1 - 8 HRS EA - OHL NA

LE-70- Generator - QTY 1 - 8 HRS EA - OHL NA

Marian Bear Park - OHLA - Blow Off # 5

- Crew is working on vault lids, installing steps, and grouting inside the vault manways

- Steps are being installed at 14-inch spacing; One step had to be retieved from the yard and will be installed tomorrow
- Valve boxes for the valve handle extensions on the top of the vault lid were said to be on site and correct now. 
- Sewer lids on valve boxes are temporary and will be replaced once final materials arrive.
- OHLA said they expect most of the material to be delivered tomorrow.
- Completed grouting inside the vault to cover the work done to raise the lids.

Hours: 6:00 AM - 4:00 PM

Manpower:

LL-03- Laborers - QTY 0 - 9.5 HRS EA - OHL NA

LL-03- Laborers - QTY 1 - 9.5 HRS EA - OHL NA

Equipment:

LE-70- Generator - QTY 1 - 9.5 HRS EA - OHL NA

LE-51- Pickup Truck - QTY 1 - 9.5 HRS EA - OHL NA

Genesee

OHLA setup traffic control for picket fences at the median between decoro and Centurion, closing the # 1 lane in both directions and shifting traffic into the #2 lane for the duration of the day. 
Picket Fences is working on median landscaping on genesee; specifically, irrigation installation 
Trenches have been dug along both the east and west edges of the median 
They have pipe laid from the water service down to the first manifold location, and have the first manifold 80% built. 
The operator for OHLA ran the skid steer with a breaker for picket fences, breaking out the concrete on the north end of the work area where ohla poured the concrete to far to the south. 

They have the backflow preventers ordertd and are expecting them next monday. 

They informed me that the ball valves for the irrigation system were not available at there normal supply stores and shops. I will be sending them serveral other suppliers to work with and get the material asap.

Hours: 6:00 AM - 5:30 PM

Manpower:

LL-02- Foreman - QTY 1 - 8 HRS EA - Pickette Fences

LL-03- Laborers - QTY 2 - 2 HRS EA - OHL NA

LL-03- Laborers - QTY 2 - 8 HRS EA - Pickette Fences

LL-04- Operator - QTY 1 - 11 HRS EA - OHL NA

Equipment:

LE-51- Pickup Truck - QTY 1 - 8 HRS EA - Pickette Fences

LE-23- Super 10 End Dump Truck - QTY 1 - 8 HRS EA - Herc

LE-125- Skid Steer - QTY 1 - 8 HRS EA - Herc - RENTAL

Rose Canyon - OHLA - Phase 2 to Phase 3 Preparation

• An OHLA welder, working inside the shaft at Rose Canyon, cut off the 30-inch and 42-inch dish heads from the pipe coming from the south side.
• The welder also cut off the 42-inch pipe that extends to the north side of Rose Canyon using an oxy-acetylene torch.
• A hole watch was stationed on top while the welder was in the shaft.
• One laborer operated a water hose from the water truck to keep the work area wet.
• Two laborers spent the day stripping residual adhesive from the connection pieces where they welded on manways.
• Crews performed SSPC-SP 2 surface preparation on the connection pieces before installing new wrap.
• The crew plans to start wrapping the 30-inch pipe and finish cleaning the 42-inch pipe tomorrow morning.
• Finished the day at 5:00 PM

Hours: 6:00 AM - 5:00 PM

Manpower:

LL-02- Foreman - QTY 1 - 11 HRS EA - OHL NA

LL-03- Laborers - QTY 4 - 11 HRS EA - OHL NA

LL-19- Welder - QTY 1 - 11 HRS EA - Deans Weldng

Equipment:

LE-58- Welding Truck - QTY 1 - 10.5 HRS EA - Deans Weldng

LE-51- Pickup Truck - QTY 1 - 10.5 HRS EA - OHL NA

LE-28- Water Truck - QTY 1 - 10.5 HRS EA - OHL NA

## Consolidated Resources

| Resource | Pay Type | Class | Qty | Company | Total Hours |
| --- | --- | --- | --- | --- | --- |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 3 | OHL NA | 24 |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 2 | OHL NA | 16 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LE-42- Utility Truck | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LE-04- Mini Excavator | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LE-23- Super 10 End Dump Truck | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LE-70- Generator | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 1 | OHL NA | 1.5 |
| LE-70- Generator | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 9.5 |
| LE-51- Pickup Truck | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 9.5 |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 1 | Pickette Fences | 8 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 2 | OHL NA | 4 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 2 | Pickette Fences | 16 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 1 | OHL NA | 3 |
| LE-51- Pickup Truck | CS - Cost | LR - Labor Regular Time | 1 | Pickette Fences | 8 |
| LE-23- Super 10 End Dump Truck | CS - Cost | LR - Labor Regular Time | 1 | Herc | 8 |
| LE-125- Skid Steer | CS - Cost | LR - Labor Regular Time | 1 | Herc | 8 |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-02- Foreman | CS - Cost | LO - Labor Overtime | 1 | OHL NA | 3 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 4 | OHL NA | 32 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 4 | OHL NA | 12 |
| LL-19- Welder | CS - Cost | LR - Labor Regular Time | 1 | Deans Weldng | 8 |
| LL-19- Welder | CS - Cost | LO - Labor Overtime | 1 | Deans Weldng | 3 |
| LE-58- Welding Truck | CS - Cost | LR - Labor Regular Time | 1 | Deans Weldng | 10.5 |
| LE-51- Pickup Truck | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 10.5 |
| LE-28- Water Truck | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 10.5 |