DAILY FIELD REPORT - 04-22-2026

Project: Morena Conveyance North
Resident Engineer: Terry West
Weather: High: 67°F, Low: 54°F, Wind: NW 13 mph, Sunny
Hours: 07:00 - 15:30

## Activities Detail

Rose Canyon Shaft - OHLA - Pipe Tie-in phase 2 to 3

• Crews cleaned residual adhesive from the 30-inch pipe and re-wrapped it in preparation for installation.
• OHLA attempted to install 30-inch and 42-inch connection pieces to tie-in Phase 2 to Phase 3 in the Rose Canyon shaft.
• During a trial fit, the 30-inch connection piece was found to be 2 feet too long on the horizontal section.
• The 42-inch connection piece was also fabricated incorrectly; it was 30 inches too long on the horizontal leg and 24 inches too short on the vertical leg.
• No pipe was installed due to the fabrication errors.
 broke out concrete inside the pipe where they would be cutting the connection spools 
• The 42-in pipe is still being surface prepped to be rewrapped from welding on the manway.

Hours: 5:30 AM - 5:30 PM

Manpower:

Flagger - QTY 1 - 11.2 HRS EA - OHLA

LL-03- Laborers - QTY 6 - 11.5 HRS EA - OHLA

LL-19- Welder - QTY 2 - 10.5 HRS EA - OHLA

LL-04- Operator - QTY 1 - 11.2 HRS EA - OHLA

Equipment:

LE-114- Crane - QTY 1 - 11.2 HRS EA - OHLA

Town Center - OHL - Concrete Sidewalk Replacement

• Crew set up traffic control in the #2 northbound lane of Town Centre.
• The new sidewalk panels were formed in the morning and a compaction test was completed at 9:00 AM, passing at 96%.
• Concrete was poured for sidewalk panels that were previously removed for the tie-in to the sewer line for the AV-13 drain.
• As extra work, the crew demolished three additional adjacent panels to the south that were broken and damaged from age.
• The concrete truck was scheduled for 11:00 AM but arrived at 11:30 PM.
• The concrete pour was completed by 12:50 PM and all finishing work was done by 1:30 PM.
• Crew replaced sod behind the new concrete after the pour.
• The site was cleaned up and traffic control was removed at 1:35 PM.

Hours: 7:00 AM - 3:30 PM

Manpower:

LL-02- Foreman - QTY 1 - 8 HRS EA - OHL

LL-03- Laborers - QTY 5 - 8 HRS EA - OHL

Equipment:

LE-01- Crew Truck - QTY 1 - 8 HRS EA - OHL

LE-51- Pickup Truck - QTY 1 - 8 HRS EA - OHL

LE-04- Mini Excavator - QTY 1 - 8 HRS EA - OHL

Governor and Genesee - SRK - Conduit Damage Investigation

• SRK set up traffic control in the #1 southbound lane on Genesee Ave, north of Governor Dr.
• Crew investigated a damaged 4-inch fiber optic conduit and a cathodic protection wire conduit that was previously hit by another contractor.
• All four cathodic protection wires were broken in one location and damaged in another, requiring multiple splices.
• Jim Silverstein and Chris from Corpro arrived on-site to inspect the damage and test the wires.
• The wires were confirmed to lead to the rectifier and were tested to confirm they were intact except for the damaged section.
• A repair plan was established allowing for two splices. The repair requires testing of each wire to ensure the correct wires are connected together.
• Repair work is scheduled for Thursday, the 30th, at 9:00 AM.
• After the investigation, SRK removed traffic control and demobilized to go to the work site at Appleton and Genesee.

Hours: 7:00 AM - 1:15 PM

Manpower:

Consultant - QTY 1 - 3 HRS EA - Cor-Pro

Consultant - QTY 1 - 3 HRS EA - City of San Diego

LL-03- Laborers - QTY 2 - 5.8 HRS EA - SRK Eng

LL-02- Foreman - QTY 1 - 5.8 HRS EA - SRK Eng

LL-04- Operator - QTY 1 - 5.8 HRS EA - SRK Eng

Equipment:

LE-23- Super 10 End Dump Truck - QTY 1 - 5.8 HRS EA - SRK Eng

LE-01- Crew Truck - QTY 1 - 5.8 HRS EA - SRK Eng

LE-04- Mini Excavator - QTY 1 - 5.8 HRS EA - SRK Eng

LE-72- Arrow Board - QTY 1 - 5.8 HRS EA - SRK Eng

Median on Genesee between Decoro and Centurion - Picket Fences - Pipe Installation

• OHLA Traffic Control set up a lane closure in the #1 lanes, both northbound and southbound, at 7:00 AM.
• Workers finished the mainline trench excavation and installed the pipe down the length of the east side of the median.
• Backfilled the mainline trench along the east side of the median.
• Crew installed continued excavation for lateral lines, valve boxes, and installed quick disconnects.
• The crew is approximately 80% complete with the lateral piping installation.
• The manifold for the system is scheduled for delivery on Monday.
• Crew re-installed BMPs at the end of the shift.
• OHLA Traffic Control removed the lane closure at the end of the day.

Hours: 7:00 AM - 3:30 PM

Manpower:

LL-03- Laborers - QTY 4 - 8 HRS EA - Pickette Fences

LL-02- Foreman - QTY 1 - 8 HRS EA - Pickette Fences

LL-04- Operator - QTY 1 - 8 HRS EA - OHL NA

Equipment:

LE-125- Skid Steer - QTY 1 - 8 HRS EA - Herc - RENTAL

LE-04- Mini Excavator - QTY 1 - 4 HRS EA - Herc - RENTAL

Sta 368+00, Genesee - SRK Engineering - Fiber Optic  Conduit Installation

• SRK Engineering set up traffic control at Sta 368+00 on Genesee.
• The crew arrived on-site at approximately 1:15 PM after spending the morning at govenor and genesee.
• Crew saw cut the trench for a new fiber optic line.
• Crew removed traffic control and demobilized from the site for the day.

Hours: 1:15 PM - 3:30 PM

Manpower:

LL-03- Laborers - QTY 3 - 8 HRS EA - SRK Eng

LL-04- Operator - QTY 1 - 8 HRS EA - SRK Eng

LL-02- Foreman - QTY 1 - 8 HRS EA - SRK Eng

Equipment:

LE-42- Utility Truck - QTY 1 - 2.2 HRS EA - SRK Eng

LE-23- Super 10 End Dump Truck - QTY 2 - 8 HRS EA - SRK Eng

LE-72- Arrow Board - QTY 1 - 2.2 HRS EA - SRK Eng

LE-04- Mini Excavator - QTY 1 - 2.2 HRS EA - SRK Eng

## Consolidated Resources

| Resource | Pay Type | Class | Qty | Company | Total Hours |
| --- | --- | --- | --- | --- | --- |
| Flagger | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| Flagger | CS - Cost | LO - Labor Overtime | 1 | OHL NA | 3.25 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 6 | OHL NA | 48 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 6 | OHL NA | 21 |
| LL-19- Welder | CS - Cost | LR - Labor Regular Time | 2 | OHL NA | 16 |
| LL-19- Welder | CS - Cost | LO - Labor Overtime | 2 | OHL NA | 5 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 1 | OHL NA | 3.25 |
| LE-114- Crane | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 11.25 |
| LL-02- Foreman | EW - Extra Work | LR - Labor Regular Time | 1 | OHL | 8 |
| LL-03- Laborers | EW - Extra Work | LR - Labor Regular Time | 5 | OHL | 40 |
| LE-01- Crew Truck | EW - Extra Work | LR - Labor Regular Time | 1 | OHL | 8 |
| LE-51- Pickup Truck | EW - Extra Work | LR - Labor Regular Time | 1 | OHL | 8 |
| LE-04- Mini Excavator | EW - Extra Work | LR - Labor Regular Time | 1 | OHL | 8 |
| Consultant | CS - Cost | LR - Labor Regular Time | 1 | Cor-Pro | 3 |
| Consultant | CS - Cost | LR - Labor Regular Time | 1 | City of San Diego | 3 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 2 | SRK Eng | 11.5 |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 1 | SRK Eng | 5.75 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | SRK Eng | 5.75 |
| LE-23- Super 10 End Dump Truck | CS - Cost | LR - Labor Regular Time | 1 | SRK Eng | 5.75 |
| LE-01- Crew Truck | CS - Cost | LR - Labor Regular Time | 1 | SRK Eng | 5.75 |
| LE-04- Mini Excavator | CS - Cost | LR - Labor Regular Time | 1 | SRK Eng | 5.75 |
| LE-72- Arrow Board | CS - Cost | LR - Labor Regular Time | 1 | SRK Eng | 5.75 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 4 | Pickette Fences | 32 |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 1 | Pickette Fences | 8 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LE-125- Skid Steer | CS - Cost | LR - Labor Regular Time | 1 | Herc | 8 |
| LE-04- Mini Excavator | CS - Cost | LR - Labor Regular Time | 1 | Herc | 4 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 3 | SRK Eng | 24 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | SRK Eng | 8 |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 1 | SRK Eng | 8 |
| LE-42- Utility Truck | CS - Cost | LR - Labor Regular Time | 1 | SRK Eng | 2.25 |
| LE-23- Super 10 End Dump Truck | CS - Cost | LR - Labor Regular Time | 2 | SRK Eng | 16 |
| LE-72- Arrow Board | CS - Cost | LR - Labor Regular Time | 1 | SRK Eng | 2.25 |
| LE-04- Mini Excavator | CS - Cost | LR - Labor Regular Time | 1 | SRK Eng | 2.25 |