DAILY FIELD REPORT - 04-23-2026

Project: Morena Conveyance North
Location: Executive, Town Centre, Nobel, Genesee, Rose Canyon, Marian Bear Park
Resident Engineer: Terry West
Weather: High: 68°F, Low: 51°F, Wind: WNW 10 mph, Sunny
Hours: 07:00 - 15:30

General Notes:

Pressuring the 48" pipe from executive to Town Centre and Nobel, Demo sidewalk and curb and gutter at 512+39, 497+95, and 495+95, Landscaping in median on genesee from 469+00 to 476+00, connecting phase 2 and 3 in rose canyon, and planting plants and working in BO #5 at marian bear park.

## Activities Detail

Genesee Avenue Median - Pickett Fences - Site Work

•OHLA setup traffic control in the # 1 for northbound and southbound traffic lanes
• A Pickett Fences crew was working in the median on Genesee Avenue.
• Installed the remaining valve boxes 
• installed two more quick connect couplings
• started installing the forms for concrete. 
• Picked up traffic control at the end of the day, 3:15 PM

Hours: 7:00 AM - 3:30 PM

Manpower:

LL-03- Laborers - QTY 4 - 8 HRS EA - OHL NA

LL-02- Foreman - QTY 1 - 8 HRS EA - OHL NA

Equipment:

LE-125- Skid Steer - QTY 0 - 8 HRS EA - Pickette Fences

LE-51- Pickup Truck - QTY 0 - 8 HRS EA - Pickette Fences

Town Center & Nobel - OHL - Concrete Demolition & Forming

• Crew broke out concrete curb, gutter, and sidewalk at Town Center and Nobel near Bloff number 7 and Airvac number 12.
• Crew also broke out concrete sidewalk panels next to a curb ramp previously installed by AR Concrete that required repair.
• After demolition, the crew formed and poured new curb and gutter at Town Center and Nobel.
• Crew cleaned the site, removed traffic control, and demobilized for the day.
• Sidewalks are scheduled to be poured tomorrow.

Manpower:

LL-03- Laborers - QTY 1 - 8 HRS EA - OHL

Executive to Town Center - OHLA - Pressure Testing

• Laborers started the pump at Executive Dr to  push pressure while they checked on the system
• A crew inspected all vaults for air leaks and all manways to confirm flanges were tight between Nobel Dr and Executive Dr.
• Traffic control with a rolling stop was set up at Nobel Dr and Town Center Dr to access a manway.
• Specific locations checked include each manway at Nobel Dr & Town Center Dr, Blowoff #7 vault, Airvac #13 vault, and Airvac #14 vault
• All checked flanges were found to be tight with no audible air leaks detected.
• The source of the pressure loss was not found.

Hours: 7:00 AM - 4:30 PM

Manpower:

LL-03- Laborers - QTY 1 - 4 HRS EA - OHL NA

LL-03- Laborers - QTY 2 - 8 HRS EA - Rose Canyon Crew

LL-03- Laborers - QTY 2 - 8 HRS EA - Prime

Equipment:

LE-42- Utility Truck - QTY 0 - 4 HRS EA - OHL NA

LE-51- Pickup Truck - QTY 0 - 4 HRS EA - OHL NA

Rose Canyon - OHLA - Pipe Installation & Welding

• laborers prepped the 42-inch pipe for re-wrapping.
• Welders prepped the pipe inside the shaft for welding.
• Crew performed a test fit of the 30-inch to determine the needed cuts.
• Crew performed a test fit of the 42-inch determine the needed cuts.
• The 42-inch pipe required the vertical section to be extended and the horizontal section to be shortened.
• The 30-inch pipe required the horizontal section to be shortened.
• The 30-inch spool was shortend along with phase 3 coming from the north, then the spool was flown in and the pipe was tacked into place.
• Crew finished prepping the surface of the 42-inch pipe and wrapped it using a 50% overlap for each pass.
• The 42-inch pipe was modified and a 9" section of pipe tacked to the verical section 
• the welders began welding out the 30-inch pipe.
• At the end of the day, the 30-inch pipe was partially welded. and the 42" was still not in place.

Hours: 5:30 AM - 6:00 PM

Manpower:

LL-09- PE - QTY 1 - 12.5 HRS EA - CWI

LL-04- Operator - QTY 1 - 12.5 HRS EA - OHL

LL-19- Welder - QTY 2 - 12.5 HRS EA - OHL

Flagger - QTY 1 - 12.5 HRS EA - MTS

LL-03- Laborers - QTY 5 - 12.5 HRS EA - OHL

Flagger - QTY 1 - 12 HRS EA - North County Transit District

LL-19- Welder - QTY 2 - 12 HRS EA - OHLA

LL-03- Laborers - QTY 5 - 12 HRS EA - OHLA

LL-20- Certified Welding Inspector (CWI) - QTY 1 - 12 HRS EA - OHLA

Equipment:

LE-28- Water Truck - QTY 1 - 12.5 HRS EA - OHL

Dry Sump & Blowoff Number 5 Vault - OHLA - Grouting & Pipe Support Installation

•Western Gardens has one guy on site hand excavating and planting vegetation. 
• planting plants in specific location to see how they grow. 


• Installed the top step of the ladder system in BO vault # 5
• OHLA crew grouted the interior of the dry sump.
• Inside the Blowoff Number 5 Vault, the crew installed Red Head anchors for flange supports underneath the drain line system.
• Walked with the forman and identified locations prviously grouted that needed to be fixed along the perimeter of the vault. at  the joint mid way between the top and bottom of the vault.

Hours: 6:00 AM - 6:30 PM

Manpower:

LL-03- Laborers - QTY 1 - 6.5 HRS EA - Western Gardens Landscape Inc.

LL-03- Laborers - QTY 1 - 11 HRS EA - OHLA

LL-02- Foreman - QTY 1 - 11 HRS EA - OHLA

Equipment:

LE-01- Crew Truck - QTY 1 - 11 HRS EA - OHLA

## Consolidated Resources

| Resource | Pay Type | Class | Qty | Company | Total Hours |
| --- | --- | --- | --- | --- | --- |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 4 | OHL NA | 32 |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | OHL | 8 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 4 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 2 | Rose Canyon Crew | 16 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 2 | OHL NA | 16 |
| LL-09- PE | CS - Cost | LR - Labor Regular Time | 1 | CWI | 8 |
| LL-09- PE | CS - Cost | LO - Labor Overtime | 1 | CWI | 4.5 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | OHL | 8 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 1 | OHL | 4.5 |
| LL-19- Welder | CS - Cost | LR - Labor Regular Time | 2 | OHL | 16 |
| LL-19- Welder | CS - Cost | LO - Labor Overtime | 2 | OHL | 9 |
| Flagger | CS - Cost | LR - Labor Regular Time | 1 | MTS | 8 |
| Flagger | CS - Cost | LO - Labor Overtime | 1 | MTS | 4.5 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 5 | OHL | 40 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 5 | OHL | 22.5 |
| Flagger | CS - Cost | LR - Labor Regular Time | 1 | North County Transit District | 8 |
| Flagger | CS - Cost | LO - Labor Overtime | 1 | North County Transit District | 4 |
| LL-19- Welder | CS - Cost | LR - Labor Regular Time | 2 | OHL NA | 16 |
| LL-19- Welder | CS - Cost | LO - Labor Overtime | 2 | OHL NA | 8 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 5 | OHL NA | 40 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 5 | OHL NA | 20 |
| LL-20- Certified Welding Inspector (CWI) | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-20- Certified Welding Inspector (CWI) | CS - Cost | LO - Labor Overtime | 1 | OHL NA | 4 |
| LE-28- Water Truck | CS - Cost | LR - Labor Regular Time | 1 | OHL | 12.5 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | Western Gardens Landscape Inc. | 6.5 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 1 | OHL NA | 3 |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-02- Foreman | CS - Cost | LO - Labor Overtime | 1 | OHL NA | 3 |
| LE-01- Crew Truck | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 11 |