DAILY FIELD REPORT - 04-27-2026

Project: Morena Conveyance North
Location: Town Center, Nobel Drive, Lombard, Genesee Avenue, Centurion, Decoro, Executive Drive, Rose Canyon, Marian Bear Park, SR-52
Resident Engineer: Terry West
Weather: High: 66°F, Low: 48°F, Wind: SSW 4 mph, Sunny
Hours: 07:00 - 15:30

General Notes:

Crews performed a variety of tasks across multiple locations. OHLA stripped concrete forms and later performed concrete curb and sidewalk repairs at four different sites. SRK Engineering paved trenches on Nobel Drive. Picket Fences continued median work on Genesee and prepared for a USA ticket on Executive Drive. At Rose Canyon, Jacobs' crew performed welding, cleanup, and pipe wrapping. The welder then moved to Executive Drive to repair a leak on the 48-inch pipe for a hydrotest. Finally, landscaping and hydroseeding activities took place at Marian Bear Park.

## Activities Detail

Town Center & Nobel Drive - OHLA - Form Stripping & Cleanup

*   Established traffic control in the No. 2 southbound lane on Town Center Drive.
*   Stripped concrete forms from the structure at Blow-off No. 7.
*   Relocated to Nobel Drive and stripped concrete forms at Airvac No. 12 and the CT test station adjacent to Lombard Street. This work was performed within an existing traffic control setup.
*   Inspected a section of sidewalk requiring repair, located on the south side of the eastbound SR-52 on-ramp at Genesee Avenue.
*   Performed a concrete patch repair on a cracked curb in Marian Bear Park.
*   Performed a second concrete patch repair on a curb in the median on Genesee Avenue near the SR-52 interchange.
*   Established and removed temporary traffic control at each repair location.

Hours: 6:00 AM - 2:30 PM

Manpower:

LL-03- Laborers - QTY 1 - 8 HRS EA - OHL NA

LL-02- Foreman - QTY 1 - 8 HRS EA - OHL NA

LL-02- Foreman - QTY 1 - 7.5 HRS EA - OHLA

LL-03- Laborers - QTY 1 - 7.5 HRS EA - OHLA

Equipment:

LE-01- Crew Truck - QTY 1 - 7.5 HRS EA - OHLA

LE-01- Crew Truck - QTY 1 - 8 HRS EA - OHL NA

Nobel Drive - SRK Engineering - Paving

• Implemented traffic control, closing the No. 2 westbound lane on Nobel Drive to facilitate the work.
• Placed asphalt concrete pavement over trenches at Air Vacuum No. 12 and the Corrosion Test Station. 
• Picked up traffic control after completing the paving operations.

Hours: 7:00 AM - 3:30 PM

Manpower:

LL-03- Laborers - QTY 3 - 8 HRS EA - SRK Eng

LL-04- Operator - QTY 1 - 8 HRS EA - SRK Eng

LL-02- Foreman - QTY 1 - 8 HRS EA - SRK Eng

LL-03- Laborers - QTY 3 - 8 HRS EA - SRK Engineering

LL-02- Foreman - QTY 1 - 8 HRS EA - SRK Engineering

LL-04- Operator - QTY 1 - 8 HRS EA - SRK Engineering

Equipment:

LE-04- Mini Excavator - QTY 1 - 8 HRS EA - SRK Engineering

LE-01- Crew Truck - QTY 1 - 8 HRS EA - SRK Engineering

LE-23- Super 10 End Dump Truck - QTY 1 - 8 HRS EA - SRK Engineering

Genesee Ave & Executive Dr - Picket Fences - Median Work & USA Markout

• Implemented traffic control on Genesee Avenue, closing the #1 lane in both the northbound and southbound directions between Centurion Street and Decoro Street.
• Continued setting concrete formwork in the median on Genesee Avenue, progressing from north to south.
• Received a delivery of PVC fence material to the site.
• Met with a representative from Picket Fences on Executive Drive, I marked out for USA ticket submission and provided description of location so Picket Fences could call in a ticket.

Hours: 7:00 AM - 3:30 PM

Manpower:

LL-03- Laborers - QTY 4 - 8 HRS EA - Pickette Fences

LL-02- Foreman - QTY 1 - 8 HRS EA - Pickette Fences

LL-01- Superintendent - QTY 1 - 8 HRS EA - Prime

Equipment:

LE-51- Pickup Truck - QTY 0 - 8 HRS EA - Pickette Fences

Equipment - QTY 0 - 0 HRS EA - Prime

Rose Canyon - Jacobs - Pipe Welding & Cleanup

• Started the day welding hand holes for the connection piece from Saturday's work.
• Cut off the lifting eyes from the connection spools.
• After welding was complete, the welder left the site.
• Laborers wrapped both pipe lines.
• Crew cleaned up trash from within the excavation shaft.
Left for the day at 4:45

Hours: 6:00 AM - 4:45 PM

Manpower:

LL-19- Welder - QTY 1 - 9.2 HRS EA - OHL NA

LL-04- Operator - QTY 1 - 9.2 HRS EA - OHL NA

LL-03- Laborers - QTY 4 - 8 HRS EA - Jacobs

Flagman - QTY 1 - 9.2 HRS EA - Jacobs

LL-04- Operator - QTY 1 - 8 HRS EA - Jacobs

LL-03- Laborers - QTY 4 - 9.2 HRS EA - OHL NA

Flagman - QTY 1 - 8 HRS EA - Jacobs

LL-19- Welder - QTY 1 - 8 HRS EA - Jacobs

Equipment:

LE-32- Skytrak Forklift - QTY 1 - 9.2 HRS EA - OHL NA

LE-114- Crane - QTY 1 - 9.2 HRS EA - OHL NA

LE-51- Pickup Truck - QTY 1 - 8 HRS EA - Jacobs

LE-23- Super 10 End Dump Truck - QTY 1 - 9.2 HRS EA - OHL NA

LE-32- Skytrak Forklift - QTY 1 - 8 HRS EA - Jacobs

LE-51- Pickup Truck - QTY 1 - 9.2 HRS EA - OHL NA

LE-114- Crane - QTY 1 - 8 HRS EA - Jacobs

LE-23- Super 10 End Dump Truck - QTY 1 - 8 HRS EA - Jacobs

Executive Drive - Jacobs - Weld Repair & Hydrotest

• A welder mobilized to the Executive Drive location to perform a weld repair.
• Added weld metal to a leaking weld on the 48-inch pipe dish head, which was previously identified during hydrostatic testing.
• The pipeline was pressurized for a preliminary hydrostatic test.
• Witnessed the 4-hour pre-test, which resulted in an approximate pressure drop of 1 PSI.
• The pipeline was subsequently pressurized to 225 PSI and left under pressure for an overnight test.

Hours: 7:00 AM - 11:30 PM

Manpower:

LL-03- Laborers - QTY 1 - 0.8 HRS EA - OHL NA

LL-19- Welder - QTY 1 - 8 HRS EA - Jacobs

LL-19- Welder - QTY 1 - 1.5 HRS EA - Deans Weldng

LL-09- PE - QTY 1 - 4 HRS EA - Prime

Equipment:

LE-58- Welding Truck - QTY 1 - 1.5 HRS EA - Prime

LE-51- Pickup Truck - QTY 1 - 0.8 HRS EA - OHL NA

Marian Bear Park - Western Gardens & Hydroseed Co. - Landscaping

• Western Gardens was on site to check on the plants they installed last week.
• The hydroseed company was on site and sprayed hydroseed in two designated areas.
• Hydroseed was applied at the north end of the park and just south of the gate entryway.

Hours: 7:00 AM - 11:00 PM

Manpower:

LL-03- Laborers - QTY 4 - 4 HRS EA – Hydro Seed Company

LL-01- Superintendent - QTY 1 - 4 HRS EA – Western Gardens

LL-07- Engineer - QTY 1 - 2 HRS EA – City of San diego

## Consolidated Resources

| Resource | Pay Type | Class | Qty | Company | Total Hours |
| --- | --- | --- | --- | --- | --- |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 7.5 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 7.5 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 7.5 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 7.5 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LE-01- Crew Truck | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 7.5 |
| LE-01- Crew Truck | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LE-01- Crew Truck | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LE-01- Crew Truck | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LE-01- Crew Truck | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 7.5 |
| LE-01- Crew Truck | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LE-01- Crew Truck | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LE-01- Crew Truck | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LE-01- Crew Truck | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LE-01- Crew Truck | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 3 | SRK Eng | 24 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | SRK Eng | 8 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | SRK Eng | 8 |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 1 | SRK Eng | 8 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 3 | SRK Eng | 24 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 3 | SRK Engineering | 24 |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 1 | SRK Engineering | 8 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | SRK Engineering | 8 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 3 | SRK Eng | 24 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 3 | SRK Engineering | 24 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | SRK Eng | 8 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 3 | SRK Eng | 24 |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 1 | SRK Eng | 8 |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 1 | SRK Engineering | 8 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | SRK Eng | 8 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 3 | SRK Eng | 24 |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 1 | SRK Eng | 8 |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 1 | SRK Eng | 8 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | SRK Eng | 8 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 3 | SRK Eng | 24 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | SRK Engineering | 8 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | SRK Eng | 8 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 3 | SRK Eng | 24 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 3 | SRK Eng | 24 |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 1 | SRK Eng | 8 |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 1 | SRK Eng | 8 |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 1 | SRK Eng | 8 |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 1 | SRK Eng | 8 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | SRK Eng | 8 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | SRK Eng | 8 |
| LE-04- Mini Excavator | CS - Cost | LR - Labor Regular Time | 1 | SRK Engineering | 8 |
| LE-04- Mini Excavator | CS - Cost | LR - Labor Regular Time | 1 | SRK Engineering | 8 |
| LE-01- Crew Truck | CS - Cost | LR - Labor Regular Time | 1 | SRK Engineering | 8 |
| LE-23- Super 10 End Dump Truck | CS - Cost | LR - Labor Regular Time | 1 | SRK Engineering | 8 |
| LE-04- Mini Excavator | CS - Cost | LR - Labor Regular Time | 1 | SRK Engineering | 8 |
| LE-01- Crew Truck | CS - Cost | LR - Labor Regular Time | 1 | SRK Engineering | 8 |
| LE-23- Super 10 End Dump Truck | CS - Cost | LR - Labor Regular Time | 1 | SRK Engineering | 8 |
| LE-04- Mini Excavator | CS - Cost | LR - Labor Regular Time | 1 | SRK Engineering | 8 |
| LE-01- Crew Truck | CS - Cost | LR - Labor Regular Time | 1 | SRK Engineering | 8 |
| LE-23- Super 10 End Dump Truck | CS - Cost | LR - Labor Regular Time | 1 | SRK Engineering | 8 |
| LE-23- Super 10 End Dump Truck | CS - Cost | LR - Labor Regular Time | 1 | SRK Engineering | 8 |
| LE-01- Crew Truck | CS - Cost | LR - Labor Regular Time | 1 | SRK Engineering | 8 |
| LE-04- Mini Excavator | CS - Cost | LR - Labor Regular Time | 1 | SRK Engineering | 8 |
| LE-23- Super 10 End Dump Truck | CS - Cost | LR - Labor Regular Time | 1 | SRK Engineering | 8 |
| LE-23- Super 10 End Dump Truck | CS - Cost | LR - Labor Regular Time | 1 | SRK Engineering | 8 |
| LE-01- Crew Truck | CS - Cost | LR - Labor Regular Time | 1 | SRK Engineering | 8 |
| LE-01- Crew Truck | CS - Cost | LR - Labor Regular Time | 1 | SRK Engineering | 8 |
| LE-04- Mini Excavator | CS - Cost | LR - Labor Regular Time | 1 | SRK Engineering | 8 |
| LE-01- Crew Truck | CS - Cost | LR - Labor Regular Time | 1 | SRK Engineering | 8 |
| LE-23- Super 10 End Dump Truck | CS - Cost | LR - Labor Regular Time | 1 | SRK Engineering | 8 |
| LE-23- Super 10 End Dump Truck | CS - Cost | LR - Labor Regular Time | 1 | SRK Engineering | 8 |
| LE-04- Mini Excavator | CS - Cost | LR - Labor Regular Time | 1 | SRK Engineering | 8 |
| LE-23- Super 10 End Dump Truck | CS - Cost | LR - Labor Regular Time | 1 | SRK Engineering | 8 |
| LE-04- Mini Excavator | CS - Cost | LR - Labor Regular Time | 1 | SRK Engineering | 8 |
| LE-04- Mini Excavator | CS - Cost | LR - Labor Regular Time | 1 | SRK Engineering | 8 |
| LE-01- Crew Truck | CS - Cost | LR - Labor Regular Time | 1 | SRK Engineering | 8 |
| LE-01- Crew Truck | CS - Cost | LR - Labor Regular Time | 1 | SRK Engineering | 8 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 4 | Pickette Fences | 32 |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 1 | Pickette Fences | 8 |
| LL-01- Superintendent | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-19- Welder | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-19- Welder | CS - Cost | LO - Labor Overtime | 1 | OHL NA | 1.25 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 1 | OHL NA | 1.25 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 4 | Jacobs | 32 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 1 | OHL NA | 1.25 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 4 | Jacobs | 32 |
| LL-19- Welder | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-19- Welder | CS - Cost | LO - Labor Overtime | 1 | OHL NA | 1.25 |
| Flagman | CS - Cost | LR - Labor Regular Time | 1 | Jacobs | 8 |
| Flagman | CS - Cost | LO - Labor Overtime | 1 | Jacobs | 1.25 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | Jacobs | 8 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 4 | OHL NA | 32 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 4 | OHL NA | 5 |
| Flagman | CS - Cost | LR - Labor Regular Time | 1 | Jacobs | 8 |
| LL-19- Welder | CS - Cost | LR - Labor Regular Time | 1 | Jacobs | 8 |
| Flagman | CS - Cost | LR - Labor Regular Time | 1 | Jacobs | 8 |
| Flagman | CS - Cost | LO - Labor Overtime | 1 | Jacobs | 1.25 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 4 | OHL NA | 32 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 4 | OHL NA | 5 |
| Flagman | CS - Cost | LR - Labor Regular Time | 1 | Jacobs | 8 |
| Flagman | CS - Cost | LO - Labor Overtime | 1 | Jacobs | 1.25 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 4 | OHL NA | 32 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 4 | OHL NA | 5 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 4 | OHL NA | 32 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 4 | OHL NA | 5 |
| LL-19- Welder | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-19- Welder | CS - Cost | LO - Labor Overtime | 1 | OHL NA | 1.25 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 1 | OHL NA | 1.25 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 1 | OHL NA | 1.25 |
| Flagman | CS - Cost | LR - Labor Regular Time | 1 | Jacobs | 8 |
| Flagman | CS - Cost | LO - Labor Overtime | 1 | Jacobs | 1.25 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 1 | OHL NA | 1.25 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 4 | OHL NA | 32 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 4 | OHL NA | 5 |
| Flagman | CS - Cost | LR - Labor Regular Time | 1 | Jacobs | 8 |
| Flagman | CS - Cost | LO - Labor Overtime | 1 | Jacobs | 1.25 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 4 | OHL NA | 32 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 4 | OHL NA | 5 |
| LL-19- Welder | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-19- Welder | CS - Cost | LO - Labor Overtime | 1 | OHL NA | 1.25 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 4 | OHL NA | 32 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 4 | OHL NA | 5 |
| LL-19- Welder | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-19- Welder | CS - Cost | LO - Labor Overtime | 1 | OHL NA | 1.25 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | Jacobs | 8 |
| Flagman | CS - Cost | LR - Labor Regular Time | 1 | Jacobs | 8 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 1 | OHL NA | 1.25 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 1 | OHL NA | 1.25 |
| LL-19- Welder | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-19- Welder | CS - Cost | LO - Labor Overtime | 1 | OHL NA | 1.25 |
| Flagman | CS - Cost | LR - Labor Regular Time | 1 | Jacobs | 8 |
| Flagman | CS - Cost | LO - Labor Overtime | 1 | Jacobs | 1.25 |
| LL-19- Welder | CS - Cost | LR - Labor Regular Time | 1 | Jacobs | 8 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 4 | OHL NA | 32 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 4 | OHL NA | 5 |
| LL-19- Welder | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-19- Welder | CS - Cost | LO - Labor Overtime | 1 | OHL NA | 1.25 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 1 | OHL NA | 1.25 |
| LL-19- Welder | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-19- Welder | CS - Cost | LO - Labor Overtime | 1 | OHL NA | 1.25 |
| Flagman | CS - Cost | LR - Labor Regular Time | 1 | Jacobs | 8 |
| Flagman | CS - Cost | LO - Labor Overtime | 1 | Jacobs | 1.25 |
| Flagman | CS - Cost | LR - Labor Regular Time | 1 | Jacobs | 8 |
| Flagman | CS - Cost | LO - Labor Overtime | 1 | Jacobs | 1.25 |
| LE-32- Skytrak Forklift | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 9.25 |
| LE-114- Crane | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 9.25 |
| LE-32- Skytrak Forklift | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 9.25 |
| LE-114- Crane | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 9.25 |
| LE-51- Pickup Truck | CS - Cost | LR - Labor Regular Time | 1 | Jacobs | 8 |
| LE-23- Super 10 End Dump Truck | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 9.25 |
| LE-32- Skytrak Forklift | CS - Cost | LR - Labor Regular Time | 1 | Jacobs | 8 |
| LE-51- Pickup Truck | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 9.25 |
| LE-114- Crane | CS - Cost | LR - Labor Regular Time | 1 | Jacobs | 8 |
| LE-23- Super 10 End Dump Truck | CS - Cost | LR - Labor Regular Time | 1 | Jacobs | 8 |
| LE-51- Pickup Truck | CS - Cost | LR - Labor Regular Time | 1 | Jacobs | 8 |
| LE-23- Super 10 End Dump Truck | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 9.25 |
| LE-32- Skytrak Forklift | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 9.25 |
| LE-23- Super 10 End Dump Truck | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 9.25 |
| LE-114- Crane | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 9.25 |
| LE-32- Skytrak Forklift | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 9.25 |
| LE-51- Pickup Truck | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 9.25 |
| LE-51- Pickup Truck | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 9.25 |
| LE-23- Super 10 End Dump Truck | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 9.25 |
| LE-51- Pickup Truck | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 9.25 |
| LE-114- Crane | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 9.25 |
| LE-23- Super 10 End Dump Truck | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 9.25 |
| LE-23- Super 10 End Dump Truck | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 9.25 |
| LE-32- Skytrak Forklift | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 9.25 |
| LE-114- Crane | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 9.25 |
| LE-32- Skytrak Forklift | CS - Cost | LR - Labor Regular Time | 1 | Jacobs | 8 |
| LE-23- Super 10 End Dump Truck | CS - Cost | LR - Labor Regular Time | 1 | Jacobs | 8 |
| LE-114- Crane | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 9.25 |
| LE-32- Skytrak Forklift | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 9.25 |
| LE-114- Crane | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 9.25 |
| LE-51- Pickup Truck | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 9.25 |
| LE-23- Super 10 End Dump Truck | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 9.25 |
| LE-51- Pickup Truck | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 9.25 |
| LE-32- Skytrak Forklift | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 9.25 |
| LE-51- Pickup Truck | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 9.25 |
| LE-32- Skytrak Forklift | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 9.25 |
| LE-23- Super 10 End Dump Truck | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 9.25 |
| LE-51- Pickup Truck | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 9.25 |
| LE-114- Crane | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 9.25 |
| LE-114- Crane | CS - Cost | LR - Labor Regular Time | 1 | Jacobs | 8 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 0.75 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 0.75 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 0.75 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 0.75 |
| LL-19- Welder | CS - Cost | LR - Labor Regular Time | 1 | Jacobs | 8 |
| LL-19- Welder | CS - Cost | LR - Labor Regular Time | 1 | Deans Weldng | 1.5 |
| LL-09- PE | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 4 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 0.75 |
| LL-19- Welder | CS - Cost | LR - Labor Regular Time | 1 | Deans Weldng | 1.5 |
| LL-19- Welder | CS - Cost | LR - Labor Regular Time | 1 | Deans Weldng | 1.5 |
| LL-19- Welder | CS - Cost | LR - Labor Regular Time | 1 | Deans Weldng | 1.5 |
| LL-19- Welder | CS - Cost | LR - Labor Regular Time | 1 | Jacobs | 8 |
| LL-09- PE | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 4 |
| LL-19- Welder | CS - Cost | LR - Labor Regular Time | 1 | Deans Weldng | 1.5 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 0.75 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 0.75 |
| LL-19- Welder | CS - Cost | LR - Labor Regular Time | 1 | Deans Weldng | 1.5 |
| LL-19- Welder | CS - Cost | LR - Labor Regular Time | 1 | Deans Weldng | 1.5 |
| LL-19- Welder | CS - Cost | LR - Labor Regular Time | 1 | Deans Weldng | 1.5 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 0.75 |
| LE-58- Welding Truck | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 1.5 |
| LE-51- Pickup Truck | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 0.75 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 4 | OHL NA | 16 |
| LL-01- Superintendent | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 4 |
| LL-07- Engineer | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 2 |