DAILY FIELD REPORT - 04-07-2026

Project: Morena Conveyance North
Location: 805 Tunnel, Executive
Resident Engineer: Terry West
Weather: High: 70°F, Low: 55°F, Wind: W 7 mph, Sunny
Hours: 07:00 - 15:30

General Notes:

No work in Marian Bear Park today Crew was on the other side of the 805 freeway at the water rec plant! Cleaning up before they start working on blow off number 9. Near the end of the day they were back over at Executive pumping up the pipelines on Town Center and executive for the hydro test but they weren't holding pressure so having to check all the air vacs and blow offs for leaks

## Activities Detail

Executive - Pickette Fences / OHLA - Median Grading

•  Setup traffic control in the North and Southbound #1 lanes shifting traffic to the # 2 lanes
• Pickette Fences, assisted by OHLA, graded the median area on Executive in preparation for median improvements.
• Hauled off excess soil from the grading operation.
• Picked up traffic control and left for the day at 3:30 PM

Manpower:

LL-03- Laborers - QTY 2 - 0 HRS EA - Pick a Fence

LL-03- Laborers - QTY 1 - 0 HRS EA - OHLA

Equipment:

LE-23- Super 10 End Dump Truck - QTY 1 - 0 HRS EA - Pick a Fence

LE-125- Skid Steer - QTY 1 - 0 HRS EA - Pick a Fence

Various Locations - OHLA - Site Support & Material Handling

• Hauled pipe, trash, lagging, and miscellaneous material from around Blowoff #9.
• Completed site BMP corrections and maintenance.
• Set up traffic control on Executive Drive for Picket Fences 
• Cleaned and prepped flanges for installation at BO # 9
• Assisted landscapers by hauling excess material from the raised median.
• Fueled the generator at Rose Canyon.
• Dewatering at Rose Canyon is now complete.
• Performed cleanup around the Executive Drive for landscapers.
• Picked up traffic control at the end of the day.
• Ended the day at 6:00 PM

• Ttraffic control / BMP crew ended the day at 4:30 PM

Hours: 6:30 AM - 6:00 PM

Manpower:

LL-03- Laborers - QTY 1 - 11.5 HRS EA - OHLA

LL-03- Laborers - QTY 1 - 9 HRS EA - OHLA

LL-03- Laborers - QTY 1 - 8 HRS EA - OHLA

LL-03- Laborers - QTY 1 - 10 HRS EA - OHLA

LL-02- Foreman - QTY 1 - 11.5 HRS EA - OHLA

Equipment:

LE-51- Pickup Truck - QTY 1 - 8 HRS EA - OHL NA

LE-32- Skytrak Forklift - QTY 1 - 8 HRS EA - Herc - RENTAL

LE-23- Super 10 End Dump Truck - QTY 1 - 8 HRS EA - Herc - RENTAL

LE-125- Skid Steer - QTY 1 - 8 HRS EA - Herc - RENTAL

LE-09- Skip Loader - QTY 1 - 8 HRS EA - OHL NA - RENTAL

LE-70- Generator - QTY 1 - 4 HRS EA - Herc - RENTAL

LE-126- Baker Tank - QTY 1 - 8 HRS EA - Rain for Rent - RENTAL

## Consolidated Resources

| Resource | Pay Type | Class | Qty | Company | Total Hours |
| --- | --- | --- | --- | --- | --- |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 1 | OHL NA | 3.5 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 1 | OHL NA | 1 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 1 | OHL NA | 2 |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-02- Foreman | CS - Cost | LO - Labor Overtime | 1 | OHL NA | 3.5 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 1 | OHL NA | 2 |
| LE-51- Pickup Truck | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LE-32- Skytrak Forklift | CS - Cost | LR - Labor Regular Time | 1 | Herc | 8 |
| LE-23- Super 10 End Dump Truck | CS - Cost | LR - Labor Regular Time | 1 | Herc | 8 |
| LE-125- Skid Steer | CS - Cost | LR - Labor Regular Time | 1 | Herc | 8 |
| LE-09- Skip Loader | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LE-70- Generator | CS - Cost | LR - Labor Regular Time | 1 | Herc | 4 |
| LE-51- Pickup Truck | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LE-126- Baker Tank | CS - Cost | LR - Labor Regular Time | 1 | Rain for Rent | 8 |