DAILY FIELD REPORT - 04-08-2026

Project: Morena Conveyance North
Resident Engineer: Terry West
Weather: High: 88°F, Low: 53°F, Wind: ESE 3 mph, Sunny
Hours: 07:00 - 15:30

## Activities Detail

Executive - Picket Fences / OHLA - Median Landscaping

• Implemented a traffic control plan, shifting northbound and southbound traffic from the #1 lanes to the #2 lanes.
• Continued grading the median and hauled excess soil for off-site disposal.
• Located the point of connection for the existing water main and performed hand excavation to expose the main.
• Completed trenching for the new irrigation line along the south side of the median.
• Began installation of new irrigation pipe.
• Removed all traffic control and reopened all lanes to traffic at the end of the shift.

Hours: 6:00 AM - 4:30 PM

Manpower:

LL-03- Laborers - QTY 1 - 10 HRS EA - OHL NA

LL-02- Foreman - QTY 1 - 10 HRS EA - Pickette Fences

Equipment:

LE-125- Skid Steer - QTY 1 - 10 HRS EA - OHL NA

LE-125- Skid Steer - QTY 1 - 10 HRS EA - Pickette Fences

LE-23- Super 10 End Dump Truck - QTY 1 - 10 HRS EA - OHL NA

Water Reclamation Plant - OHLA - Blow Off # 9

• 3 OHLA laborers worked at BO # 9 at the Water Reclamation Plant prepping the reducing flanges to be installed on the pipe coming up into the vault. 
• Loaded up a pile of base that was in the middle of the work area
• used the forklift to lower the reducing flanges into the vault 
• valves were brought over to be installed on the reducing flanges and to be installed on the 4" drain line. 
• one of the valves was different then the other three that are to be installed on the drain line so they didnt install any. 
• got a count of parts and material they to figure out what was needed for the follwing day. 
• Ended the day at the plant at 5:00 PM 
• went through the site and did some BMP maintance before leaving for the day.

Hours: 6:00 AM - 5:30 PM

Manpower:

LL-03- Laborers - QTY 1 - 11 HRS EA - OHL NA

LL-02- Foreman - QTY 1 - 11 HRS EA - OHL NA

Equipment:

LE-51- Pickup Truck - QTY 2 - 11 HRS EA - OHL NA

LE-32- Skytrak Forklift - QTY 1 - 11 HRS EA - OHL NA

Marian Bear Park - OHLA - Wood Fence & Concrete Pour inside Bollards

• The traffic control and BMP crew worked at Marian Bear Park
• Completed the installation of the wood fence along Genesee Avenue on both sides of the gate at Marian Bear Park.
• Poured concrete into four (4) bollards to protect the blow-off vent and fiber pull box.
• Went back to traffic control and BMP maintenance for the remainder of the day

Hours: 6:00 AM - 4:30 PM

Manpower:

LL-03- Laborers - QTY 1 - 10 HRS EA - OHL NA

LL-03- Laborers - QTY 1 - 10 HRS EA - OHL NA

Equipment:

LE-42- Utility Truck - QTY 1 - 10 HRS EA - OHL NA

## Consolidated Resources

| Resource | Pay Type | Class | Qty | Company | Total Hours |
| --- | --- | --- | --- | --- | --- |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 1 | OHL NA | 2 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 1 | OHL NA | 2 |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 1 | Pickette Fences | 8 |
| LL-02- Foreman | CS - Cost | LO - Labor Overtime | 1 | Pickette Fences | 2 |
| LE-125- Skid Steer | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 10 |
| LE-125- Skid Steer | CS - Cost | LR - Labor Regular Time | 1 | Pickette Fences | 10 |
| LE-23- Super 10 End Dump Truck | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 10 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 1 | OHL NA | 3 |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-02- Foreman | CS - Cost | LO - Labor Overtime | 1 | OHL NA | 3 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 1 | OHL NA | 3 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 1 | OHL NA | 3 |
| LE-51- Pickup Truck | CS - Cost | LR - Labor Regular Time | 2 | OHL NA | 22 |
| LE-32- Skytrak Forklift | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 11 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 1 | OHL NA | 1 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 1 | OHL NA | 1 |
| LE-42- Utility Truck | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 9 |