DAILY FIELD REPORT - 05-16-2026

Project: Morena Conveyance North
Location: Rose Canyon, Water Reclamation Plant, Nobel Drive, Genesee, Town Center, Nobel
Resident Engineer: Terry West
Weather: 
Hours: 07:00 - 15:30

General Notes:

OHL crews performed demolition of a concrete shaft at Rose Canyon and began excavation for a 30-inch pipe tie-in at the Water Reclamation Plant. Demolition is approximately 75% complete, while the excavation is about 60% complete.
Crews performed excavation of previously placed base material in the median on Nobel Drive to correct a grade drop-off between traffic lanes. The new subgrade was then smoothed and compacted. Traffic control, including lane closures and a signal board, was maintained on Nobel Drive and at Genesee.
OHL crews performed hand excavation at the Phase 3 to Phase 4 connection located at Town Center, just north of Nobel. The crew cleared the south side and a portion of the north side of the excavation, reaching a final depth of approximately 15 feet. Existing traffic control with K-rail remained in place.

## Activities Detail

Rose Canyon - OHL - Concrete Shaft Demolition

• Performed demolition of the concrete shaft at the Rose Canyon OHL location.
• The structure was to be demolished to an elevation below the original grade of Rose Canyon.
• Completed approximately 75% of the total concrete demolition as of end of day saturday
• Performed site cleanup in preparation for demobilization throughout the day as well.

Hours: 6:00 AM - 2:30 PM

Manpower:

LL-04- Operator - QTY 1 - 8 HRS EA - OHL

LL-03- Laborers - QTY 3 - 8 HRS EA - OHL

Equipment:

LE-23- Super 10 End Dump Truck - QTY 1 - 8 HRS EA - Z-Trucking

LE-125- Skid Steer - QTY 1 - 8 HRS EA - OHL NA

LE-70- Generator - QTY 1 - 8 HRS EA - OHL NA

LE-32- Skytrak Forklift - QTY 1 - 8 HRS EA - OHL NA

LE-04- Mini Excavator - QTY 1 - 8 HRS EA - OHL NA

Water Reclamation Plant - OHL - Excavation

• Crew excavated for the 30-inch pipe that Kiewit installed.
• Started digging with the excavator at the location that was previously potholed.
• A shoring box was placed once the excavation was deep enough.
• Three laborers entered the trench to hand excavate around the pipe, clear the bottom, and expose the end of the existing pipe.
• At the end of the day, the operation was about 60% complete.
• The crew had just uncovered the top of the pipe and began hand excavation inside the shoring box when the day ended.

Hours: 6:00 AM - 4:00 PM

Manpower:

LL-04- Operator - QTY 1 - 10 HRS EA - OHL

LL-02- Foreman - QTY 1 - 10 HRS EA - OHL

LL-03- Laborers - QTY 3 - 10 HRS EA - OHL

Equipment:

LE-01- Crew Truck - QTY 1 - 10 HRS EA - OHL

LE-109- Excavator - QTY 1 - 10 HRS EA - OHL

LE-23- Super 10 End Dump Truck - QTY 1 - 10 HRS EA - OHL

Nobel Drive - Median - Excavation & Grading

• Crew excavated base material that was placed earlier in the week from the median area.
• Excavation was performed to remove a drop-off between the eastbound and westbound lanes.
• A mini excavator loaded the excavated base material into a dump truck for removal.
• Laborers smoothed the new subgrade and then compacted it using a wacker plate compactor.
• Traffic control was maintained with channelizers due to the drop-off hazard created by the base removal.
• The westbound #1 turn pocket and the eastbound #1 lane were kept closed.
• On the opposite side of Genesee, the eastbound #1 lane was also closed, managed with a signal board.

Hours: 6:00 AM - 2:30 PM

Manpower:

LL-04- Operator - QTY 1 - 8 HRS EA - OHL NA

LL-03- Laborers - QTY 2 - 8 HRS EA - OHL NA

Equipment:

LE-23- Super 10 End Dump Truck - QTY 1 - 8 HRS EA - OHL NA

LE-81- Mechanical Wacker - QTY 1 - 8 HRS EA - OHL NA

LE-04- Mini Excavator - QTY 1 - 8 HRS EA - OHL NA

Town Center north of Nobel - OHL - Hand Excavation

• OHL crew worked at the Phase 3 to Phase 4 connection.
• Laborers hand shoveled soil into an excavator bucket to expose the existing pipeline.
• An operator used the excavator to remove the soil from the excavation.
• The south side of the excavation was cleared completely back to the wall.
• Approximately 40% of the bottoms and sides of the north side of the excavation were cleared.
• The bottom of the excavation reached a depth of approximately 15 ft.
• The existing hard closure traffic control with K-rail was left in place.

Hours: 6:00 AM - 2:30 PM

Manpower:

LL-03- Laborers - QTY 3 - 8 HRS EA - OHL NA

LL-04- Operator - QTY 1 - 8 HRS EA - OHL NA

Equipment:

LE-109- Excavator - QTY 1 - 8 HRS EA - OHL NA

LE-01- Crew Truck - QTY 1 - 8 HRS EA - OHL NA

## Consolidated Resources

| Resource | Pay Type | Class | Qty | Company | Total Hours |
| --- | --- | --- | --- | --- | --- |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | OHL | 8 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 3 | OHL | 24 |
| LE-125- Skid Steer | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LE-70- Generator | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LE-32- Skytrak Forklift | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LE-04- Mini Excavator | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | OHL | 8 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 1 | OHL | 2 |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 1 | OHL | 8 |
| LL-02- Foreman | CS - Cost | LO - Labor Overtime | 1 | OHL | 2 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 3 | OHL | 24 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 3 | OHL | 6 |
| LE-01- Crew Truck | CS - Cost | LR - Labor Regular Time | 1 | OHL | 10 |
| LE-109- Excavator | CS - Cost | LR - Labor Regular Time | 1 | OHL | 10 |
| LE-23- Super 10 End Dump Truck | CS - Cost | LR - Labor Regular Time | 1 | OHL | 10 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 2 | OHL NA | 16 |
| LE-23- Super 10 End Dump Truck | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LE-81- Mechanical Wacker | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LE-04- Mini Excavator | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 3 | OHL NA | 24 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LE-109- Excavator | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LE-01- Crew Truck | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |