DAILY FIELD REPORT - 05-27-2026

Project: Morena Conveyance Northern
Location: Genesee Avenue, Governor Drive & Genesee Avenue, Genesee Avenue Median (South of Nobel Drive), Town Center Drive & Nobel Drive, Town Center Drive, Water Reclamation Plant
Resident Engineer: TERRY WEST
Weather: High: 65°F, Low: 57°F, Wind: 9 mph WSW, Drizzle
Hours: 06:30 - 15:00

General Notes:

Multiple contractors performed work across various locations. Activities included median landscaping and base preparation by Picket Fences and OHL, manhole blind flange torquing, pipe welding with Dean's Welding, cathodic protection and paving by SRK, and drain line installation at the Water Reclamation Plant.

## Activities Detail

Genesee Avenue - Picket Fences - Median Landscaping

• Picket Fences performed landscape work at Median 2 and Median 3 on Genesee Avenue.

• The crew completed asphalt demolition at Median 2.

• Demolished asphalt was loaded into a Super 10 truck provided by WestTruck Services, Inc. and hauled off-site.

• In Median 3, the crew focused on grading activities.

• The contractor plans to begin excavation for irrigation systems tomorrow.

Manpower:

LL-01- Superintendent - QTY 1 - 8 HRS EA - Picket Fences

LL-02- Foreman - QTY 1 - 8 HRS EA - Picket Fences

LL-03- Laborers - QTY 4 - 8 HRS EA - Picket Fences

Equipment:

LE-125- Skid Steer - QTY 2 - 8 HRS EA - Picket Fences

LE-51- Pickup Truck - QTY 1 - 8 HRS EA - Picket Fences

LE-23- Super 10 End Dump Truck - QTY 1 - 8 HRS EA - Picket Fences

Governor Drive & Genesee Avenue - Manhole blind Flange Torquing — 432+17 & 1098+34

• A crew worked to torque blind flanges on two manholes in preparation for final turnover.

• Work was performed at SMH #41, located at Sta 432+17, and SMH #42, located at Sta 1098+34.

• Both manholes were successfully buttoned up with all flanges torqued to specification.

• It was observed that the floors inside both manholes are covered with a significant amount of mud and water and will require cleaning.

Manpower:

LL-02- Foreman - QTY 1 - 8 HRS EA - OHL NA

LL-03- Laborers - QTY 2 - 8 HRS EA - OHL NA

Equipment:

LE-32- Skytrak Forklift - QTY 1 - 8 HRS EA - OHL NA

LE-01- Crew Truck - QTY 1 - 8 HRS EA - OHL NA

Genesee Avenue Median (Immediately South of Nobel Drive) - OHLA - Median Stamped Concrete Prep

• Set up traffic control, closing the #1 lane on southbound Genesee Avenue.

• Placed base in the median south of Nobel Drive using a skid steer.

• Spread the base.

• Added moisture to the base material with a water truck.

• Compacted the aggregate base using a Wacker plate compactor.

• Swept both sides of the median in the street.

• Picked up traffic control at. 5:00PM.

Manpower:

LL-04- Operator - QTY 1 - 10 HRS EA - OHL NA

LL-03- Laborers - QTY 3 - 10 HRS EA - OHL NA

Equipment:

LE-125- Skid Steer - QTY 1 - 10 HRS EA - OHL NA

LE-28- Water Truck - QTY 1 - 10 HRS EA - OHL NA

LE-23- Super 10 End Dump Truck - QTY 1 - 10 HRS EA - OHL NA

LE-81- Mechanical Wacker - QTY 1 - 10 HRS EA - OHL NA

Town Center Drive & Nobel Drive - OHL / Dean's Welding - Phase 3 to 4 connection

• Welding continued on the exterior pipe butt straps at this location.

• Both connection joints prepared yesterday are in place.

• The two welders from Dean's Welding completed a total of four butt strap welds today.

• A Certified Welding Inspector (CWI) was on-site for the duration of the work to inspect the welds as they were completed.

• Traffic control, consisting of a hard closure with K-rail, remains in place.

Manpower:

LL-04- Operator - QTY 1 - 8 HRS EA - OHL NA

LL-03- Laborers - QTY 2 - 8 HRS EA - OHL NA

LL-19- Welder - QTY 2 - 8 HRS EA - Dean's Welding

LL-20- Certified Welding Inspector (CWI) - QTY 1 - 8 HRS EA - IQC Infastructure

Equipment:

LE-109- Excavator - QTY 1 - 8 HRS EA - OHL NA

LE-32- Skytrak Forklift - QTY 1 - 8 HRS EA - OHL NA

LE-58- Welding Truck - QTY 2 - 8 HRS EA - OHL NA

LE-51- Pickup Truck - QTY 1 - 8 HRS EA - OHL NA

Town Center Drive - SRK - Cathodic Protection & Paving

• SRK performed work related to the ICCP-6 wellhead and surrounding asphalt.

• Traffic control was set up at Town Center Drive and Golden Haven, closing the southbound #1 and #2 lanes.

• The crew stripped the existing cold mix and prepared the subgrade.

• A section of the road at Sta 523+59 was paved.

• After the new asphalt cooled, traffic control was shifted to the #3 lane.

• The crew then stripped the cold mix in the #3 lane and removed the steel plate that was covering the ICCP anode bed.

• A permanent box was installed over the anode bed wellhead.

• The trench on the west side of the #3 lane was paved. The east side of this lane had been previously paved following earlier dig-out activities.

Manpower:

LL-02- Foreman - QTY 1 - 8 HRS EA - SRK Eng

LL-04- Operator - QTY 1 - 8 HRS EA - SRK Eng

LL-03- Laborers - QTY 2 - 8 HRS EA - SRK Eng

Equipment:

LE-04- Mini Excavator - QTY 1 - 8 HRS EA - SRK Eng

LE-23- Super 10 End Dump Truck - QTY 1 - 8 HRS EA - SRK Eng

LE-01- Crew Truck - QTY 1 - 8 HRS EA - SRK Eng

LE-81- Mechanical Wacker - QTY 1 - 8 HRS EA - SRK Eng

LE-13- Roller H222 - QTY 1 - 8 HRS EA - SRK Eng

Water Reclamation Plant - OHL - Drain Line Installation

• The OHL crew continued the installation of the 4-inch drain line for Blowoff #9.

• Flanges on the pipe spools located directly outside the vault were bolted, torqued, and wrapped.

• The crew fabricated an offset piece to connect the new drain line down to the required elevation of the existing sewer line tie-in.

• It was noted that the design for the drain line originating from the vault floor drain does not include an in-line valve. This is a concern, as the absence of a valve may allow sewer gases to travel up the pipe and accumulate inside the vault.

Manpower:

LL-04- Operator - QTY 1 - 8 HRS EA - OHL

LL-03- Laborers - QTY 3 - 8 HRS EA - OHL

Equipment:

LE-109- Excavator - QTY 1 - 8 HRS EA - OHL

LE-32- Skytrak Forklift - QTY 1 - 8 HRS EA - OHL

LE-51- Pickup Truck - QTY 1 - 8 HRS EA - OHL

## Consolidated Resources

| Resource | Pay Type | Class | Qty | Company | Total Hours |
| --- | --- | --- | --- | --- | --- |
| LL-01- Superintendent | CS - Cost | LR - Labor Regular Time | 1 | Picket Fences | 8 |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 1 | Picket Fences | 8 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 4 | Picket Fences | 32 |
| LE-125- Skid Steer | CS - Cost | LR - Labor Regular Time | 2 | Picket Fences | 16 |
| LE-51- Pickup Truck | CS - Cost | LR - Labor Regular Time | 1 | Picket Fences | 8 |
| LE-23- Super 10 End Dump Truck | CS - Cost | LR - Labor Regular Time | 1 | Picket Fences | 8 |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 2 | OHL NA | 16 |
| LE-32- Skytrak Forklift | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LE-01- Crew Truck | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 1 | OHL NA | 2 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 3 | OHL NA | 24 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 3 | OHL NA | 6 |
| LE-125- Skid Steer | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 10 |
| LE-28- Water Truck | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 10 |
| LE-23- Super 10 End Dump Truck | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 10 |
| LE-81- Mechanical Wacker | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 10 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 2 | OHL NA | 16 |
| LL-19- Welder | CS - Cost | LR - Labor Regular Time | 2 | Dean's Welding | 16 |
| LL-20- Certified Welding Inspector (CWI) | CS - Cost | LR - Labor Regular Time | 1 | IQC Infastructure | 8 |
| LE-109- Excavator | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LE-32- Skytrak Forklift | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LE-58- Welding Truck | CS - Cost | LR - Labor Regular Time | 2 | OHL NA | 16 |
| LE-51- Pickup Truck | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 1 | SRK Eng | 8 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | SRK Eng | 8 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 2 | SRK Eng | 16 |
| LE-04- Mini Excavator | CS - Cost | LR - Labor Regular Time | 1 | SRK Eng | 8 |
| LE-23- Super 10 End Dump Truck | CS - Cost | LR - Labor Regular Time | 1 | SRK Eng | 8 |
| LE-01- Crew Truck | CS - Cost | LR - Labor Regular Time | 1 | SRK Eng | 8 |
| LE-81- Mechanical Wacker | CS - Cost | LR - Labor Regular Time | 1 | SRK Eng | 8 |
| LE-13- Roller H222 | CS - Cost | LR - Labor Regular Time | 1 | SRK Eng | 8 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | OHL | 8 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 3 | OHL | 24 |
| LE-109- Excavator | CS - Cost | LR - Labor Regular Time | 1 | OHL | 8 |
| LE-32- Skytrak Forklift | CS - Cost | LR - Labor Regular Time | 1 | OHL | 8 |
| LE-51- Pickup Truck | CS - Cost | LR - Labor Regular Time | 1 | OHL | 8 |