DAILY FIELD REPORT - 06-07-2026

Project: Morena Conveyance Northern
Location: Genesee - SR 52/Marian Bear Park
Resident Engineer: Terry West
Weather: High: 70°F, Low: 60°F, Wind: 8 mph SW, Overcast, Clear
Hours: 20:00 - 05:30

General Notes:

Night work, limited traffic, clear skies, RJ Noble performed digouts near the SR 52 on Genesee

## Activities Detail

- RJ Noble – Dig Outs - GENESSEE AVE UTC / GENESSEE AVE SR 52 INT UTC

• Digout Schedule — 6/7/2026:

- DO#1 - SB #2 Lane — 1' depth × 12W × 12L = 144 SF (10.8 tons)

- DO #2 - SB #2 Lane — 1' depth × 17W × 27L = 459 SF (34.425 tons)

- DO #10 - SB #2 Lane — 1' depth × 7W × 6L = 42 SF (3.15 tons)

- DO #24 - SB #2 Lane — 1' depth × 7W × 106L = 742 SF (55.65 tons)

- DO #23 - SB #2 Lane — 1' depth × 14W × 28L = 392 SF (29.4 tons)

- DO #25 - SB #2 Lane — 1' depth × 7W × 36L = 252 SF (18.9 tons)

- DO #27 - SB #2 Lane — 1' depth × 14W × 60L = 840 SF (63 tons)

- DO #28 - SB #2 Lane — 1' depth × 12W × 105L = 1,260 SF (94.5 tons)

- DO #SR 52 - SB Outside — 0.5' depth × 0W × 0L = 0 SF (68 tons)

- DO #SR 52 - NB Outside — 0.5' depth × 0W × 0L = 0 SF (80 tons)

- DO #22 - NB #2 Lane — 1' depth × 12W × 55L = 660 SF (49.5 tons)

- DO #1 - NB # 1 & 2 Lanes — 1' depth × 15W × 30L = 450 SF (33.75 tons)

Total: 5,241 SF / 541.075 Tons

• Material: 530 TN 3/4" HMA

• Plant: MM MIRAMAR

Hours: 7:30 PM - 5:00 AM

Manpower:

LL-02- Foreman - QTY 1 - 9.5 HRS EA - OHLA

LL-04- Operator - QTY 1 - 9.5 HRS EA - OHLA

LL-03- Laborers - QTY 1 - 9.5 HRS EA - OHLA

LL-04- Operator - QTY 1 - 8.8 HRS EA - DIII

Equipment:

LE-13- Roller H222 - QTY 1 - 9.5 HRS EA - OHLA

LE-09- Skip Loader - QTY 1 - 9.5 HRS EA - OHLA

LE-125- Skid Steer - QTY 1 - 9.5 HRS EA - OHLA

LE-63- Asphalt Paver - QTY 1 - 9.5 HRS EA - OHLA

LE-51- Pickup Truck - QTY 1 - 9.5 HRS EA - OHLA

LE-01- Crew Truck - QTY 1 - 9.5 HRS EA - OHLA

LE-141- End Dump - QTY 1 - 8.8 HRS EA - DIII

LL-08- PM - QTY 1 - 9.5 HRS EA - OHLA - RENTAL

Extra Work Manpower:

LL-02- Foreman - QTY 1 - 9.5 HRS EA - OHLA

LL-04- Operator - QTY 1 - 9.5 HRS EA - OHLA

LL-03- Laborers - QTY 1 - 9.5 HRS EA - OHLA

LL-03- Laborers - QTY 1 - 7.5 HRS EA - OHLA

Extra Work Equipment:

LE-13- Roller H222 - QTY 1 - 9.5 HRS EA - OHLA

LE-09- Skip Loader - QTY 1 - 9.5 HRS EA - OHLA

LE-125- Skid Steer - QTY 1 - 9.5 HRS EA - OHLA

LE-63- Asphalt Paver - QTY 1 - 9.5 HRS EA - OHLA

LE-01- Crew Truck - QTY 1 - 9.5 HRS EA - OHLA

## Consolidated Resources

| Resource | Pay Type | Class | Qty | Company | Total Hours |
| --- | --- | --- | --- | --- | --- |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-02- Foreman | CS - Cost | LO - Labor Overtime | 1 | OHL NA | 1.5 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 1 | OHL NA | 1.5 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 1 | OHL NA | 1.5 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 1 | OHL NA | 1.5 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 1 | OHL NA | 1.5 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 1 | OHL NA | 1.5 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 1 | OHL NA | 1.5 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 1 | OHL NA | 1.5 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 1 | OHL NA | 1.5 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 1 | OHL NA | 1.5 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 1 | OHL NA | 1.5 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | DIII | 8 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 1 | DIII | 0.8 |
| LE-13- Roller H222 | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 9.5 |
| LE-09- Skip Loader | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 9.5 |
| LE-125- Skid Steer | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 9.5 |
| LE-13- Roller H222 | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 9.5 |
| LE-63- Asphalt Paver | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 9.5 |
| LE-13- Roller H222 | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 9.5 |
| LE-63- Asphalt Paver | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 9.5 |
| LE-13- Roller H222 | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 9.5 |
| LE-51- Pickup Truck | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 9.5 |
| LE-51- Pickup Truck | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 9.5 |
| LE-01- Crew Truck | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 9.5 |
| LE-141- End Dump | CS - Cost | LR - Labor Regular Time | 1 | DIII | 8.8 |
| LL-02- Foreman | EW - Extra Work | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-02- Foreman | EW - Extra Work | LO - Labor Overtime | 1 | OHL NA | 1.5 |
| LL-04- Operator | EW - Extra Work | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-04- Operator | EW - Extra Work | LO - Labor Overtime | 1 | OHL NA | 1.5 |
| LL-04- Operator | EW - Extra Work | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-04- Operator | EW - Extra Work | LO - Labor Overtime | 1 | OHL NA | 1.5 |
| LL-03- Laborers | EW - Extra Work | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-03- Laborers | EW - Extra Work | LO - Labor Overtime | 1 | OHL NA | 1.5 |
| LL-03- Laborers | EW - Extra Work | LR - Labor Regular Time | 1 | OHL NA | 7.5 |
| LE-13- Roller H222 | EW - Extra Work | LR - Labor Regular Time | 1 | OHL NA | 9.5 |
| LE-13- Roller H222 | EW - Extra Work | LR - Labor Regular Time | 1 | OHL NA | 9.5 |
| LE-09- Skip Loader | EW - Extra Work | LR - Labor Regular Time | 1 | OHL NA | 9.5 |
| LE-125- Skid Steer | EW - Extra Work | LR - Labor Regular Time | 1 | OHL NA | 9.5 |
| LE-13- Roller H222 | EW - Extra Work | LR - Labor Regular Time | 1 | OHL NA | 9.5 |
| LE-63- Asphalt Paver | EW - Extra Work | LR - Labor Regular Time | 1 | OHL NA | 9.5 |
| LE-63- Asphalt Paver | EW - Extra Work | LR - Labor Regular Time | 1 | OHL NA | 9.5 |
| LE-13- Roller H222 | EW - Extra Work | LR - Labor Regular Time | 1 | OHL NA | 9.5 |
| LE-01- Crew Truck | EW - Extra Work | LR - Labor Regular Time | 1 | OHL NA | 9.5 |