DAILY FIELD REPORT - 06-10-2026

Project: Morena Conveyance Northern
Resident Engineer: Terry West
Weather: High: 68°F, Low: 63°F, Wind: 5-9 MPH, Partly Cloudy, Overcast
Hours: 6:30 AM - 3:00 PM

## Activities Detail

SD MORENA CONVEYANCE - PAVE CREW / SD MORENA CONVEYANCE - POTHOLE CREW — GENESSEE AVE / CENTURION SQ - UTC

• Digout Schedule — 6/10/2026:

- DO #1 NB#2 — 1' depth × 236W × 14L = 3,304 SF (247.8 tons)

- DO #2 NB#2 — 1' depth × 160W × 11L = 1,760 SF (132 tons)

- DO #3 NB#2 — 1' depth × 184W × 14L = 2,576 SF (193.2 tons)

- DO #4 NB#2 — 1' depth × 58W × 13L = 754 SF (56.55 tons)

- DO #Centurion NB/SB Inside lanes — 0.5' depth = 2,181 SF (81.79 tons)

RJ Noble setup traffic control in the #2 NB lanes on Genesee between governor and centurion shifting taffic into the #1 lane

RJ noble started at digout #4 then worked there way south grinding out each dig out location then compacting the sub grade and repaving with ¾” asphalt.

Total: 10,575 SF / 711.34 Tons

• Material: 460 TN 3/4" HMA

• Plant: MM MIRAMAR

Hours: 7:30 PM - 5:00 AM

Manpower:

LL-02- Foreman - QTY 1 - 9.5 HRS EA - RJ NOBLE - SOUTH

LL-04- Operator - QTY 1 - 9.5 HRS EA - RJ NOBLE - SOUTH

LL-03- Laborers - QTY 1 - 9.5 HRS EA - RJ NOBLE - SOUTH

LL-04- Operator - QTY 1 - 8.5 HRS EA - DIII

LL-03- Laborers - QTY 1 - 5 HRS EA - RJ NOBLE - SOUTH

LL-04- Operator - QTY 6 - 5 HRS EA - DIII

LL-04- Operator - QTY 1 - 5 HRS EA - PRSI

LL-03- Laborers - QTY 1 - 9.5 HRS EA - HUDSON

Equipment:

LE-83- Equipment-Hauling Trailer - QTY 1 - 9.5 HRS EA - RJ NOBLE - SOUTH

LE-100- Liebherr LB20 Drill Rig - QTY 1 - 9.5 HRS EA - RJ NOBLE - SOUTH

LE-13- Roller H222 - QTY 1 - 9.5 HRS EA - RJ NOBLE - SOUTH

LE-09- Skip Loader - QTY 1 - 9.5 HRS EA - RJ NOBLE - SOUTH

LE-125- Skid Steer - QTY 1 - 9.5 HRS EA - RJ NOBLE - SOUTH

LE-63- Asphalt Paver - QTY 1 - 9.5 HRS EA - RJ NOBLE - SOUTH

LE-51- Pickup Truck - QTY 1 - 9.5 HRS EA - RJ NOBLE - SOUTH

LE-01- Crew Truck - QTY 1 - 9.5 HRS EA - RJ NOBLE - SOUTH

LE-141- End Dump - QTY 1 - 8.5 HRS EA - DIII

LL-08- PM - QTY 1 - 9.5 HRS EA - RJ NOBLE - SOUTH - RENTAL

LE-42- Utility Truck - QTY 1 - 9.5 HRS EA - RJ NOBLE - SOUTH

LE-19- Street sweeper - QTY 1 - 9.5 HRS EA - RJ NOBLE - SOUTH

LE-141- End Dump - QTY 6 - 5 HRS EA - DIII

LE-71- Pavement Grinder - QTY 1 - 5 HRS EA - PRSI

Extra Work Manpower:

LL-03- Laborers - QTY 1 - 9.5 HRS EA - RJ NOBLE - SOUTH

Extra Work Equipment:

LE-01- Crew Truck - QTY 1 - 9.5 HRS EA - RJ NOBLE - SOUTH

LE-157- Tack Truck - QTY 1 - 9.5 HRS EA - RJ NOBLE - SOUTH

## Consolidated Resources

| Resource | Pay Type | Class | Qty | Company | Total Hours |
| --- | --- | --- | --- | --- | --- |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 8 |
| LL-02- Foreman | CS - Cost | LO - Labor Overtime | 1 | RJ NOBLE - SOUTH | 1.5 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 8 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 1 | RJ NOBLE - SOUTH | 1.5 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 8 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 1 | RJ NOBLE - SOUTH | 1.5 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 8 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 1 | RJ NOBLE - SOUTH | 1.5 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 8 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 1 | RJ NOBLE - SOUTH | 1.5 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 8 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 1 | RJ NOBLE - SOUTH | 1.5 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 8 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 1 | RJ NOBLE - SOUTH | 1.5 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 8 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 1 | RJ NOBLE - SOUTH | 1.5 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 8 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 1 | RJ NOBLE - SOUTH | 1.5 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | DIII | 8 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 1 | DIII | 0.5 |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 8 |
| LL-02- Foreman | CS - Cost | LO - Labor Overtime | 1 | RJ NOBLE - SOUTH | 1.5 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 8 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 1 | RJ NOBLE - SOUTH | 1.5 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 8 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 1 | RJ NOBLE - SOUTH | 1.5 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 8 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 1 | RJ NOBLE - SOUTH | 1.5 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 8 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 1 | RJ NOBLE - SOUTH | 1.5 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 5 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 5 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 6 | DIII | 30 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | PRSI | 5 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | HUDSON | 8 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 1 | HUDSON | 1.5 |
| LE-83- Equipment-Hauling Trailer | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 9.5 |
| LE-100- Liebherr LB20 Drill Rig | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 9.5 |
| LE-13- Roller H222 | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 9.5 |
| LE-09- Skip Loader | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 9.5 |
| LE-125- Skid Steer | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 9.5 |
| LE-13- Roller H222 | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 9.5 |
| LE-63- Asphalt Paver | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 9.5 |
| LE-13- Roller H222 | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 9.5 |
| LE-63- Asphalt Paver | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 9.5 |
| LE-13- Roller H222 | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 9.5 |
| LE-51- Pickup Truck | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 9.5 |
| LE-51- Pickup Truck | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 9.5 |
| LE-01- Crew Truck | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 9.5 |
| LE-141- End Dump | CS - Cost | LR - Labor Regular Time | 1 | DIII | 8.5 |
| LE-42- Utility Truck | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 9.5 |
| LE-19- Street sweeper | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 9.5 |
| LE-42- Utility Truck | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 9.5 |
| LE-19- Street sweeper | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 9.5 |
| LE-51- Pickup Truck | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 9.5 |
| LE-141- End Dump | CS - Cost | LR - Labor Regular Time | 6 | DIII | 30 |
| LE-71- Pavement Grinder | CS - Cost | LR - Labor Regular Time | 1 | PRSI | 5 |
| LL-03- Laborers | EW - Extra Work | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 8 |
| LL-03- Laborers | EW - Extra Work | LO - Labor Overtime | 1 | RJ NOBLE - SOUTH | 1.5 |
| LL-03- Laborers | EW - Extra Work | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 8 |
| LL-03- Laborers | EW - Extra Work | LO - Labor Overtime | 1 | RJ NOBLE - SOUTH | 1.5 |
| LE-01- Crew Truck | EW - Extra Work | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 9.5 |
| LE-157- Tack Truck | EW - Extra Work | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 9.5 |