DAILY FIELD REPORT - 06-11-2026

Project: Morena Conveyance Northern
Resident Engineer: Terry West
Weather: 
Hours: 6:30 AM - 3:00 PM

## Activities Detail

SD MORENA CONVEYANCE - PAVE CREW / SD MORENA CONVEYANCE - POTHOLE CREW — GENESSEE AVE / GOVERNOR DR - UTC

• Digout Schedule — Thursday, June 11, 2026:

- DO #5 NB#2 — 1' depth × 177W × 13L = 2,301 SF (172.58 tons)

- DO #6 NB#2 — 1' depth × 135W × 11L = 1,485 SF (111.38 tons)

- DO #Governor NB/SB Inside lanes — 0.5' depth × 0W × 0L = 2,546 SF (95.475 tons)

- DO #Centurion NB outside Lane — 0.5' depth × 0W × 0L = 2,236 SF (83.85 tons)

- Total  8,568 SF (463.26 tons) - Estimated

-  413.62 Tons - Actual

• Material: 3/4" HMAR

Traffic control setup in the #2 lane on genesee in the Northbound lanes between governor and centurion.

RJ noble completed digouts #5 and #6 and the digouts in the intersections of centurion in the outside lanes and governor in the outside lanes

The Quality Firm on site taking compaction tests throughout

Hours: 7:00 PM - 5:00 AM

Manpower:

LL-02- Foreman - QTY 2 - 9.5 HRS EA - OHLA

LL-04- Operator - QTY 9 - 9.5 HRS EA - OHLA

LL-03- Laborers - QTY 5 - 9.5 HRS EA - OHLA

LL-04- Operator - QTY 1 - 8.5 HRS EA - DIII

LL-03- Laborers - QTY 2 - 10 HRS EA - OHLA

LL-04- Operator - QTY 6 - 9 HRS EA - DIII

LL-04- Operator - QTY 1 - 9 HRS EA - PRSI

LL-03- Laborers - QTY 1 - 9.5 HRS EA - HUDSON

Equipment:

LE-13- Roller H222 - QTY 4 - 9.5 HRS EA - OHLA

LE-09- Skip Loader - QTY 1 - 9.5 HRS EA - OHLA

LE-125- Skid Steer - QTY 1 - 9.5 HRS EA - OHLA

LE-63- Asphalt Paver - QTY 2 - 9.5 HRS EA - OHLA

LE-51- Pickup Truck - QTY 4 - 9.5 HRS EA - OHLA

LE-01- Crew Truck - QTY 1 - 9.5 HRS EA - OHLA

LE-141- End Dump - QTY 1 - 8.5 HRS EA - DIII

LL-03- Laborers - QTY 2 - 9.5 HRS EA - OHLA - RENTAL

LE-42- Utility Truck - QTY 2 - 9.5 HRS EA - OHLA

LE-19- Street sweeper - QTY 2 - 9.5 HRS EA - OHLA

LE-141- End Dump - QTY 6 - 9 HRS EA - DIII

LE-71- Pavement Grinder - QTY 1 - 9 HRS EA - PRSI

Extra Work Manpower:

LL-03- Laborers - QTY 2 - 9.5 HRS EA - OHLA

Extra Work Equipment:

LE-01- Crew Truck - QTY 1 - 9.5 HRS EA - OHLA

LE-157- Tack Truck - QTY 1 - 9.5 HRS EA - OHLA

## Consolidated Resources

| Resource | Pay Type | Class | Qty | Company | Total Hours |
| --- | --- | --- | --- | --- | --- |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 2 | OHL NA | 16 |
| LL-02- Foreman | CS - Cost | LO - Labor Overtime | 2 | OHL NA | 3 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 9 | OHL NA | 72 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 9 | OHL NA | 13.5 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 7 | OHL NA | 56 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 5 | OHL NA | 7.5 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 7 | DIII | 56 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 1 | DIII | 0.5 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 2 | OHL NA | 4 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 6 | DIII | 6 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | PRSI | 8 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 1 | PRSI | 1 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | HUDSON | 8 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 1 | HUDSON | 1.5 |
| LE-13- Roller H222 | CS - Cost | LR - Labor Regular Time | 4 | OHL NA | 38 |
| LE-09- Skip Loader | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 9.5 |
| LE-125- Skid Steer | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 9.5 |
| LE-63- Asphalt Paver | CS - Cost | LR - Labor Regular Time | 2 | OHL NA | 19 |
| LE-51- Pickup Truck | CS - Cost | LR - Labor Regular Time | 4 | OHL NA | 38 |
| LE-01- Crew Truck | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 9.5 |
| LE-141- End Dump | CS - Cost | LR - Labor Regular Time | 1 | DIII | 8.5 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 2 | OHL NA | 19 |
| LE-42- Utility Truck | CS - Cost | LR - Labor Regular Time | 2 | OHL NA | 19 |
| LE-19- Street sweeper | CS - Cost | LR - Labor Regular Time | 2 | OHL NA | 19 |
| LE-141- End Dump | CS - Cost | LR - Labor Regular Time | 6 | DIII | 54 |
| LE-71- Pavement Grinder | CS - Cost | LR - Labor Regular Time | 1 | PRSI | 9 |
| LL-03- Laborers | EW - Extra Work | LR - Labor Regular Time | 2 | OHL NA | 16 |
| LL-03- Laborers | EW - Extra Work | LO - Labor Overtime | 2 | OHL NA | 3 |
| LE-01- Crew Truck | EW - Extra Work | LR - Labor Regular Time | 1 | OHL NA | 9.5 |
| LE-157- Tack Truck | EW - Extra Work | LR - Labor Regular Time | 1 | OHL NA | 9.5 |