DAILY FIELD REPORT - 06-15-2026

Project: Morena Conveyance Northern
Location: Nobel and Genesee
Resident Engineer: Terry West
Weather: High: 71°F, Low: 64°F, Wind: NW less than 5MPH , Clear, Partly Cloudy
Hours: 19:30 - 03:30

## Activities Detail

Nobel and Genesee - RJ Noble - Dig outs — Genesee Ave and Nobel Dr.

• Traffic Control Setup in all for directions from the Nobel/Genesee intersection. East bound and west bound traffic closed and one lane each north and south open.

RJ Noble used an asphalt grinder to grind 0.5 feet of roadway in an area covering 3,336 square feet in the northbound outside lane on Nobel Drive, totaling 125.1 tons of material.

• Asphalt was excavated to a depth of 0.5 feet over 4,897 square feet in the southbound outside lane on Nobel Drive, totaling 183.6 tons of material.

• The estimated total HMA to be paced was 308.74 Tons.

• Actual qty placed - 310.6 Tons

• Overall Total since starting 6/7/2026 - 3844.76 Tons

• Paving completed at 3:30 AM and traffic control took about 30 minutes to pickup.

*Klienfelder and The Quality Firm on site

Hours: 7:30 PM - 3:30 AM

Manpower:

LL-02- Foreman - QTY 1 - 8 HRS EA - RJ Noble

LL-04- Operator - QTY 1 - 8 HRS EA - RJ Noble

LL-03- Laborers - QTY 1 - 8 HRS EA - RJ Noble

LL-11- Teamster - QTY 1 - 7 HRS EA - RJ Noble

LL-03- Laborers - QTY 1 - 3.5 HRS EA - RJ Noble

LL-11- Teamster - QTY 10 - 7.5 HRS EA - RJ Noble

LL-04- Operator - QTY 1 - 7.5 HRS EA - RJ Noble

LL-18- Visitor - QTY 1 - 5 HRS EA - OHL NA

Equipment:

LE-13- Roller H222 - QTY 1 - 8 HRS EA - RJ Noble

LE-09- Skip Loader - QTY 1 - 8 HRS EA - RJ Noble

LE-125- Skid Steer - QTY 1 - 8 HRS EA - RJ Noble

LE-63- Asphalt Paver - QTY 1 - 8 HRS EA - RJ Noble

LE-51- Pickup Truck - QTY 1 - 8 HRS EA - RJ Noble

LE-01- Crew Truck - QTY 1 - 8 HRS EA - RJ Noble

LE-23- Super 10 End Dump Truck - QTY 1 - 8 HRS EA - RJ Noble

LE-157- Tack Truck - QTY 1 - 8 HRS EA - RJ Noble

LE-42- Utility Truck - QTY 1 - 8 HRS EA - RJ Noble

LE-19- Street sweeper - QTY 1 - 8 HRS EA - RJ Noble

LE-23- Super 10 End Dump Truck - QTY 10 - 8 HRS EA - RJ Noble

LE-71- Pavement Grinder - QTY 1 - 8 HRS EA - RJ Noble

## Consolidated Resources

| Resource | Pay Type | Class | Qty | Company | Total Hours |
| --- | --- | --- | --- | --- | --- |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 1 | RJ Noble | 8 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | RJ Noble | 8 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | RJ Noble | 8 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | RJ Noble | 8 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | RJ Noble | 8 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | RJ Noble | 8 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | RJ Noble | 8 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | RJ Noble | 8 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | RJ Noble | 8 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | RJ Noble | 8 |
| LL-11- Teamster | CS - Cost | LR - Labor Regular Time | 1 | RJ Noble | 7 |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 1 | RJ Noble | 8 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | RJ Noble | 8 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | RJ Noble | 8 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | RJ Noble | 8 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | RJ Noble | 8 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | RJ Noble | 8 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | RJ Noble | 3.5 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | RJ Noble | 3.5 |
| LL-11- Teamster | CS - Cost | LR - Labor Regular Time | 10 | RJ Noble | 75 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | RJ Noble | 7.5 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | RJ Noble | 8 |
| LL-18- Visitor | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 5 |
| LE-13- Roller H222 | CS - Cost | LR - Labor Regular Time | 1 | RJ Noble | 8 |
| LE-09- Skip Loader | CS - Cost | LR - Labor Regular Time | 1 | RJ Noble | 8 |
| LE-125- Skid Steer | CS - Cost | LR - Labor Regular Time | 1 | RJ Noble | 8 |
| LE-13- Roller H222 | CS - Cost | LR - Labor Regular Time | 1 | RJ Noble | 8 |
| LE-63- Asphalt Paver | CS - Cost | LR - Labor Regular Time | 1 | RJ Noble | 8 |
| LE-13- Roller H222 | CS - Cost | LR - Labor Regular Time | 1 | RJ Noble | 8 |
| LE-63- Asphalt Paver | CS - Cost | LR - Labor Regular Time | 1 | RJ Noble | 8 |
| LE-13- Roller H222 | CS - Cost | LR - Labor Regular Time | 1 | RJ Noble | 8 |
| LE-51- Pickup Truck | CS - Cost | LR - Labor Regular Time | 1 | RJ Noble | 8 |
| LE-51- Pickup Truck | CS - Cost | LR - Labor Regular Time | 1 | RJ Noble | 8 |
| LE-01- Crew Truck | CS - Cost | LR - Labor Regular Time | 1 | RJ Noble | 8 |
| LE-23- Super 10 End Dump Truck | CS - Cost | LR - Labor Regular Time | 1 | RJ Noble | 8 |
| LE-51- Pickup Truck | CS - Cost | LR - Labor Regular Time | 1 | RJ Noble | 8 |
| LE-157- Tack Truck | CS - Cost | LR - Labor Regular Time | 1 | RJ Noble | 8 |
| LE-42- Utility Truck | CS - Cost | LR - Labor Regular Time | 1 | RJ Noble | 8 |
| LE-19- Street sweeper | CS - Cost | LR - Labor Regular Time | 1 | RJ Noble | 8 |
| LE-42- Utility Truck | CS - Cost | LR - Labor Regular Time | 1 | RJ Noble | 8 |
| LE-19- Street sweeper | CS - Cost | LR - Labor Regular Time | 1 | RJ Noble | 8 |
| LE-51- Pickup Truck | CS - Cost | LR - Labor Regular Time | 1 | RJ Noble | 8 |
| LE-51- Pickup Truck | CS - Cost | LR - Labor Regular Time | 1 | RJ Noble | 8 |
| LE-23- Super 10 End Dump Truck | CS - Cost | LR - Labor Regular Time | 10 | RJ Noble | 80 |
| LE-71- Pavement Grinder | CS - Cost | LR - Labor Regular Time | 1 | RJ Noble | 8 |
| LE-19- Street sweeper | CS - Cost | LR - Labor Regular Time | 1 | RJ Noble | 8 |