DAILY FIELD REPORT - 06-16-2026

Project: Morena Conveyance Northern
Resident Engineer: Terry West
Weather: 
Hours: 06:30 - 16:00

## Activities Detail

Nobel and Genesee - RJ Nobel - Dig Outs — Genesee / Nobel

• Traffic control in place at 8:00 PM, protecting the inside lanes in both North and South directions and blocking traffic from crossing Genesee on Nobel in either direction.

• Digout Schedule — 6/16/2026:

- DO #Nobel MB/SB Inside — 0.5' depth × 0W × 0L = 5,886 SF (220.7 tons)

Estimated Total: 5,886 SF / 220.7 Tons

Actual - 224.58 Tons

• Material:  3/4" HMA

• Paving completerd at 3:30 AM

• street sweeper swept the intersection while traffic control started to pull cones and pick up signs

• area clear by 4:00 AM

Hours: 7:30 AM - 4:00 AM

Manpower:

LL-02- Foreman - QTY 1 - 8.5 HRS EA - RJ Noble

LL-04- Operator - QTY 1 - 8.5 HRS EA - RJ Noble

LL-03- Laborers - QTY 1 - 8.5 HRS EA - RJ Noble

LL-11- Teamster - QTY 1 - 8.5 HRS EA - DIII

LL-11- Teamster - QTY 4 - 8.5 HRS EA - DIII

LL-04- Operator - QTY 1 - 8.5 HRS EA - PRSI

LL-03- Laborers - QTY 1 - 8.5 HRS EA - HUDSON

LL-11- Teamster - QTY 10 - 8.5 HRS EA - DIII

Equipment:

LE-83- Equipment-Hauling Trailer - QTY 1 - 8.5 HRS EA - RJ Noble

LE-100- Liebherr LB20 Drill Rig - QTY 1 - 8.5 HRS EA - RJ Noble

LE-13- Roller H222 - QTY 1 - 8.5 HRS EA - RJ Noble

LE-09- Skip Loader - QTY 1 - 8.5 HRS EA - RJ Noble

LE-125- Skid Steer - QTY 1 - 8.5 HRS EA - RJ Noble

LE-63- Asphalt Paver - QTY 1 - 8.5 HRS EA - RJ Noble

LE-51- Pickup Truck - QTY 1 - 8.5 HRS EA - RJ Noble

LE-01- Crew Truck - QTY 1 - 8.5 HRS EA - RJ Noble

LE-23- Super 10 End Dump Truck - QTY 1 - 8.5 HRS EA - DIII

LE-51- Pickup Truck - QTY 1 - 8.5 HRS EA - RJ NOBLE - SOUTH

LE-157- Tack Truck - QTY 1 - 8.5 HRS EA - RJ Noble

LE-42- Utility Truck - QTY 1 - 8.5 HRS EA - RJ Noble

LE-19- Street sweeper - QTY 1 - 8.5 HRS EA - RJ Noble

LE-23- Super 10 End Dump Truck - QTY 4 - 8.5 HRS EA - DIII

LE-71- Pavement Grinder - QTY 1 - 8.5 HRS EA - PRSI

LE-19- Street sweeper - QTY 1 - 8.5 HRS EA - CTI

LL-08- PM - QTY 1 - 8.5 HRS EA - RJ Noble - RENTAL

LE-23- Super 10 End Dump Truck - QTY 10 - 8.5 HRS EA - DIII

## Consolidated Resources

| Resource | Pay Type | Class | Qty | Company | Total Hours |
| --- | --- | --- | --- | --- | --- |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 1 | RJ Noble | 8 |
| LL-02- Foreman | CS - Cost | LO - Labor Overtime | 1 | RJ Noble | 0.5 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | RJ Noble | 8 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 1 | RJ Noble | 0.5 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | RJ Noble | 8 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 1 | RJ Noble | 0.5 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | RJ Noble | 8 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 1 | RJ Noble | 0.5 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | RJ Noble | 8 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 1 | RJ Noble | 0.5 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | RJ Noble | 8 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 1 | RJ Noble | 0.5 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | RJ Noble | 8 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 1 | RJ Noble | 0.5 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | RJ Noble | 8 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 1 | RJ Noble | 0.5 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | RJ Noble | 8 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 1 | RJ Noble | 0.5 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | RJ Noble | 8 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 1 | RJ Noble | 0.5 |
| LL-11- Teamster | CS - Cost | LR - Labor Regular Time | 1 | DIII | 8 |
| LL-11- Teamster | CS - Cost | LO - Labor Overtime | 1 | DIII | 0.5 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | RJ Noble | 8 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 1 | RJ Noble | 0.5 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | RJ Noble | 8 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 1 | RJ Noble | 0.5 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | RJ Noble | 8 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 1 | RJ Noble | 0.5 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | RJ Noble | 8 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 1 | RJ Noble | 0.5 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | RJ Noble | 8 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 1 | RJ Noble | 0.5 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | RJ Noble | 8 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 1 | RJ Noble | 0.5 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | RJ Noble | 8 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 1 | RJ Noble | 0.5 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | RJ Noble | 8 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 1 | RJ Noble | 0.5 |
| LL-11- Teamster | CS - Cost | LR - Labor Regular Time | 4 | DIII | 32 |
| LL-11- Teamster | CS - Cost | LO - Labor Overtime | 4 | DIII | 2 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | PRSI | 8 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 1 | PRSI | 0.5 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | HUDSON | 8 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 1 | HUDSON | 0.5 |
| LL-11- Teamster | CS - Cost | LR - Labor Regular Time | 10 | DIII | 80 |
| LL-11- Teamster | CS - Cost | LO - Labor Overtime | 10 | DIII | 5 |
| LE-83- Equipment-Hauling Trailer | CS - Cost | LR - Labor Regular Time | 1 | RJ Noble | 8.5 |
| LE-100- Liebherr LB20 Drill Rig | CS - Cost | LR - Labor Regular Time | 1 | RJ Noble | 8.5 |
| LE-13- Roller H222 | CS - Cost | LR - Labor Regular Time | 1 | RJ Noble | 8.5 |
| LE-09- Skip Loader | CS - Cost | LR - Labor Regular Time | 1 | RJ Noble | 8.5 |
| LE-125- Skid Steer | CS - Cost | LR - Labor Regular Time | 1 | RJ Noble | 8.5 |
| LE-13- Roller H222 | CS - Cost | LR - Labor Regular Time | 1 | RJ Noble | 8.5 |
| LE-63- Asphalt Paver | CS - Cost | LR - Labor Regular Time | 1 | RJ Noble | 8.5 |
| LE-13- Roller H222 | CS - Cost | LR - Labor Regular Time | 1 | RJ Noble | 8.5 |
| LE-63- Asphalt Paver | CS - Cost | LR - Labor Regular Time | 1 | RJ Noble | 8.5 |
| LE-13- Roller H222 | CS - Cost | LR - Labor Regular Time | 1 | RJ Noble | 8.5 |
| LE-51- Pickup Truck | CS - Cost | LR - Labor Regular Time | 1 | RJ Noble | 8.5 |
| LE-51- Pickup Truck | CS - Cost | LR - Labor Regular Time | 1 | RJ Noble | 8.5 |
| LE-01- Crew Truck | CS - Cost | LR - Labor Regular Time | 1 | RJ Noble | 8.5 |
| LE-23- Super 10 End Dump Truck | CS - Cost | LR - Labor Regular Time | 1 | DIII | 8.5 |
| LE-51- Pickup Truck | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 8.5 |
| LE-157- Tack Truck | CS - Cost | LR - Labor Regular Time | 1 | RJ Noble | 8.5 |
| LE-42- Utility Truck | CS - Cost | LR - Labor Regular Time | 1 | RJ Noble | 8.5 |
| LE-19- Street sweeper | CS - Cost | LR - Labor Regular Time | 1 | RJ Noble | 8.5 |
| LE-42- Utility Truck | CS - Cost | LR - Labor Regular Time | 1 | RJ Noble | 8.5 |
| LE-19- Street sweeper | CS - Cost | LR - Labor Regular Time | 1 | RJ Noble | 8.5 |
| LE-51- Pickup Truck | CS - Cost | LR - Labor Regular Time | 1 | RJ Noble | 8.5 |
| LE-51- Pickup Truck | CS - Cost | LR - Labor Regular Time | 1 | RJ Noble | 8.5 |
| LE-23- Super 10 End Dump Truck | CS - Cost | LR - Labor Regular Time | 4 | DIII | 34 |
| LE-71- Pavement Grinder | CS - Cost | LR - Labor Regular Time | 1 | PRSI | 8.5 |
| LE-19- Street sweeper | CS - Cost | LR - Labor Regular Time | 1 | CTI | 8.5 |
| LE-23- Super 10 End Dump Truck | CS - Cost | LR - Labor Regular Time | 10 | DIII | 85 |