DAILY FIELD REPORT - 06-19-2026

Project: Morena Conveyance Northern
Location: Genesee NB and Nobel EB and WB - RJ Noble - Grind and Overlay
Resident Engineer: Terry West
Weather: High: 71°F, Low: 62°F, Wind: 11 mph WNW, Overcast
Hours: 06:30 - 15:00

## Activities Detail

SD MORENA CONVEYANCE - SOUTH PAVE CREW / SD MORENA CONVEYANCE - SOUTH GRIND CREW — GENESEE AVE / CENTRUION SQ - UTC

• Digout Schedule — Friday, July 3, 2026:

- DO #0 NB OUTSIDE TOWN CENTER — 0' depth × 0W × 0L = 43,518 SF (816 tons)

- DO #0 EB OUTSIDE EXECUTIVE — 0' depth × 0W × 0L = 19,068 SF (358 tons)

Total: 62,586 SF / 1,174 Tons

• Material: 1/2" FIBER MIX ID#21242163F

• Plant: MM LAKESIDE

Hours: 7:00 PM - 5:00 AM

Manpower:

LL-02- Foreman - QTY 2 - 9.5 HRS EA - RJ NOBLE

LL-04- Operator - QTY 10 - 9.5 HRS EA - RJ NOBLE

LL-03- Laborers - QTY 8 - 9.5 HRS EA - RJ NOBLE

LL-11- Teamster - QTY 6 - 8.8 HRS EA - DIII

LL-03- Laborers - QTY 2 - 10 HRS EA - RJ NOBLE

LL-04- Operator - QTY 2 - 9 HRS EA - PRSI

Equipment:

LE-83- Equipment-Hauling Trailer - QTY 1 - 9.5 HRS EA - RJ NOBLE

ESPLANADE CT - QTY 1 - 9.5 HRS EA - RJ NOBLE

LE-13- Roller H222 - QTY 3 - 9.5 HRS EA - RJ NOBLE

LE-09- Skip Loader - QTY 1 - 9.5 HRS EA - RJ NOBLE

LE-125- Skid Steer - QTY 1 - 9.5 HRS EA - RJ NOBLE

LE-63- Asphalt Paver - QTY 2 - 9.5 HRS EA - RJ NOBLE

LE-160- Pup Roller - QTY 1 - 9.5 HRS EA - RJ NOBLE

LE-51- Pickup Truck - QTY 4 - 9.5 HRS EA - RJ NOBLE

LE-01- Crew Truck - QTY 2 - 9.5 HRS EA - RJ NOBLE

LE-23- Super 10 End Dump Truck - QTY 6 - 8.8 HRS EA - DIII

LL-03- Laborers - QTY 3 - 9.5 HRS EA - RJ NOBLE - RENTAL

LE-157- Tack Truck - QTY 1 - 9.5 HRS EA - RJ NOBLE

LE-42- Utility Truck - QTY 2 - 9.5 HRS EA - RJ NOBLE

LE-19- Street sweeper - QTY 2 - 9.5 HRS EA - RJ NOBLE

LE-71- Pavement Grinder - QTY 2 - 9 HRS EA - PRSI

## Consolidated Resources

| Resource | Pay Type | Class | Qty | Company | Total Hours |
| --- | --- | --- | --- | --- | --- |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 2 | RJ NOBLE | 16 |
| LL-02- Foreman | CS - Cost | LO - Labor Overtime | 2 | RJ NOBLE | 3 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 10 | RJ NOBLE | 80 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 10 | RJ NOBLE | 15 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 10 | RJ NOBLE | 80 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 8 | RJ NOBLE | 12 |
| LL-11- Teamster | CS - Cost | LR - Labor Regular Time | 6 | DIII | 48 |
| LL-11- Teamster | CS - Cost | LO - Labor Overtime | 6 | DIII | 4.8 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 2 | RJ NOBLE | 4 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 2 | PRSI | 16 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 2 | PRSI | 2 |
| LE-83- Equipment-Hauling Trailer | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE | 9.5 |
| ESPLANADE CT | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE | 9.5 |
| LE-13- Roller H222 | CS - Cost | LR - Labor Regular Time | 3 | RJ NOBLE | 28.5 |
| LE-09- Skip Loader | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE | 9.5 |
| LE-125- Skid Steer | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE | 9.5 |
| LE-63- Asphalt Paver | CS - Cost | LR - Labor Regular Time | 2 | RJ NOBLE | 19 |
| LE-160- Pup Roller | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE | 9.5 |
| LE-51- Pickup Truck | CS - Cost | LR - Labor Regular Time | 4 | RJ NOBLE | 38 |
| LE-01- Crew Truck | CS - Cost | LR - Labor Regular Time | 2 | RJ NOBLE | 19 |
| LE-23- Super 10 End Dump Truck | CS - Cost | LR - Labor Regular Time | 6 | DIII | 52.8 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 3 | RJ NOBLE | 28.5 |
| LE-157- Tack Truck | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE | 9.5 |
| LE-42- Utility Truck | CS - Cost | LR - Labor Regular Time | 2 | RJ NOBLE | 19 |
| LE-19- Street sweeper | CS - Cost | LR - Labor Regular Time | 2 | RJ NOBLE | 19 |
| LE-71- Pavement Grinder | CS - Cost | LR - Labor Regular Time | 2 | PRSI | 18 |