DAILY FIELD REPORT - 06-23-2026

Project: Morena Conveyance Northern
Location: Genesee, Town Centre
Resident Engineer: Terry West
Weather: High: 72°F, Low: 61°F, Wind: 8 mph W, Overcast
Hours: 20:30 - 04:30

## Activities Detail

RJ Noble - Dig Outs - and — GENESSEE AVE / CENTURION SQ - UTC

• Paving Schedule — Tuesday, June 23, 2026:

- SB OUTSIDE GENESEE — 0' depth × 0W × 0L = 33,643 SF (631 tons)

- SB OUTSIDE GENESEE — 0' depth × 0W × 0L = 47,763 SF (896 tons)

Total: 81,406 SF / 1,527 Tons

• Material: 1/2" FIBER MIX ID#21242163F

• Plant: MM LAKESIDE

31018 Sq Ft of concrete encountered

The quality firm on site throughout the night taking compaction tests

RJ noble had traffic control setup in the # 2 lane from SR 52 West bound on ramp to 100' short of the south end of the project at 369+00

shifting traffic into the #1 lane. the westbound on ramp from genesee was also closed

RJ noble worked from the westbound on ramp south down genesee towards the south end of the project with the grind and pave.

Hours: 8:30 PM - 4:30 AM

Manpower:

LL-02- Foreman - QTY 2 - 8 HRS EA - RJ NOBLE

LL-04- Operator - QTY 10 - 8 HRS EA - RJ NOBLE

LL-03- Laborers - QTY 6 - 8 HRS EA - RJ NOBLE

LL-11- Teamster - QTY 10 - 7.3 HRS EA - DIII

LL-03- Laborers - QTY 2 - 8.5 HRS EA - RJ NOBLE

LL-11- Teamster - QTY 22 - 7.5 HRS EA - DIII

LL-04- Operator - QTY 2 - 7.5 HRS EA - PRSI

LL-03- Laborers - QTY 2 - 8 HRS EA - HUDSON

Equipment:

LE-158- CCTV Truck - QTY 1 - 8 HRS EA - RJ NOBLE

LE-13- Roller H222 - QTY 4 - 8 HRS EA - RJ NOBLE

LE-09- Skip Loader - QTY 1 - 8 HRS EA - RJ NOBLE

LE-125- Skid Steer - QTY 1 - 8 HRS EA - RJ NOBLE

LE-63- Asphalt Paver - QTY 2 - 8 HRS EA - RJ NOBLE

LE-51- Pickup Truck - QTY 5 - 8 HRS EA - RJ NOBLE

LE-01- Crew Truck - QTY 1 - 8 HRS EA - RJ NOBLE

LE-23- Super 10 End Dump Truck - QTY 32 - 8 HRS EA - DIII

LL-03- Laborers - QTY 4 - 8 HRS EA - RJ NOBLE - RENTAL

LE-157- Tack Truck - QTY 1 - 8 HRS EA - RJ NOBLE

LE-23- Super 10 End Dump Truck - QTY 1 - 8 HRS EA - RJ NOBLE

LE-42- Utility Truck - QTY 2 - 8 HRS EA - RJ NOBLE

LE-19- Street sweeper - QTY 2 - 8 HRS EA - RJ NOBLE

LE-71- Pavement Grinder - QTY 2 - 8 HRS EA - PRSI

LE-19- Street sweeper - QTY 1 - 8 HRS EA - CTI

Consultants:

LL-42- Asphalt QC Tech - QTY 1 - 8 HRS EA - OHL NA

## Consolidated Resources

| Resource | Pay Type | Class | Qty | Company | Total Hours |
| --- | --- | --- | --- | --- | --- |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 2 | RJ NOBLE | 16 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 10 | RJ NOBLE | 80 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 12 | RJ NOBLE | 96 |
| LL-11- Teamster | CS - Cost | LR - Labor Regular Time | 10 | DIII | 73 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 2 | RJ NOBLE | 1 |
| LL-11- Teamster | CS - Cost | LR - Labor Regular Time | 22 | DIII | 165 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 2 | PRSI | 15 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 2 | HUDSON | 16 |
| LE-158- CCTV Truck | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE | 8 |
| LE-13- Roller H222 | CS - Cost | LR - Labor Regular Time | 4 | RJ NOBLE | 32 |
| LE-09- Skip Loader | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE | 8 |
| LE-125- Skid Steer | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE | 8 |
| LE-63- Asphalt Paver | CS - Cost | LR - Labor Regular Time | 2 | RJ NOBLE | 16 |
| LE-51- Pickup Truck | CS - Cost | LR - Labor Regular Time | 5 | RJ NOBLE | 40 |
| LE-01- Crew Truck | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE | 8 |
| LE-23- Super 10 End Dump Truck | CS - Cost | LR - Labor Regular Time | 32 | DIII | 256 |
| LE-157- Tack Truck | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE | 8 |
| LE-23- Super 10 End Dump Truck | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE | 8 |
| LE-42- Utility Truck | CS - Cost | LR - Labor Regular Time | 2 | RJ NOBLE | 16 |
| LE-19- Street sweeper | CS - Cost | LR - Labor Regular Time | 2 | RJ NOBLE | 16 |
| LE-71- Pavement Grinder | CS - Cost | LR - Labor Regular Time | 2 | PRSI | 16 |
| LE-19- Street sweeper | CS - Cost | LR - Labor Regular Time | 1 | CTI | 8 |
| LL-42- Asphalt QC Tech | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |