DAILY FIELD REPORT - 06-29-2026

Project: Morena Conveyance Northern
Location: Northbound Genesee from Appleton to Governor
Resident Engineer: Terry West
Weather: High: 70°F, Low: 56°F, Wind: 10 mph S, Overcast
Hours: 19:30 - 05:45

## Activities Detail

NB Genesee Inside Lanes - pipeline start to Governor - 1.18 Miles  - RJ Noble - Grind and Overlay — 369+00 to 432+32

• Grind & Overlay — Monday, June 29, 2026:

Location	Area                           (SF)	Notes	Tons

NB INSIDE GENESEE	30,630	CR	574.00

NB INSIDE GENESEE	62,734	CR	1,176.00

Shift Total	                93,364		1,750.00 (estimated)

• Material 1/2" FIBER MIX ID#21242163F

• Plant: MM LAKESIDE

• Material: GRINDS TO MIRAMAR

• Actual Asphalt Laid: 1673.70 tons

• The quality firm on site testing compaction through out the night.

• Traffic Control: NB Inside lanes (#1 lane and turn pockets) closed, shifting all traffic into the #2 lanes in both directions from south of the Governor/Genesee Intersection to the south end of the ROW. The Govorner intersection remained open.

• RJ Noble began their grind @ 369+00 and worked North. The overlay stareted up 15 minutes after and both crews worked from 369+00 to 432+32,, a total 1.18 miles. wrapped up the overlay at 5:00 AM and street sweeping in the final area was completed at 5:30AM, and traffic control was pulled by 5:45AM

Hours: 7:30 PM - 5:00 AM

Manpower:

LL-02- Foreman - QTY 2 - 9.5 HRS EA - RJ NOBLE

LL-04- Operator - QTY 10 - 9.5 HRS EA - RJ NOBLE

LL-03- Laborers - QTY 4 - 9.5 HRS EA - RJ NOBLE

LL-03- Laborers - QTY 2 - 10 HRS EA - RJ NOBLE

LL-04- Operator - QTY 2 - 9 HRS EA - PRSI

LL-03- Laborers - QTY 3 - 9.5 HRS EA – HUDSON

LL-42- Asphalt QC – QTY 1 – 9 HRS EA – THE QUALITY FIRM

Equipment:

LE-13- Roller H222 - QTY 3 - 9.5 HRS EA - RJ NOBLE

LE-09- Skip Loader - QTY 1 - 9.5 HRS EA - RJ NOBLE

LE-125- Skid Steer - QTY 1 - 9.5 HRS EA - RJ NOBLE

LE-63- Asphalt Paver - QTY 2 - 9.5 HRS EA - RJ NOBLE

LE-160- Pup Roller - QTY 1 - 9.5 HRS EA - RJ NOBLE

LE-30- Deere 210L Skip Loader - QTY 1 - 9.5 HRS EA - RJ NOBLE

LE-51- Pickup Truck - QTY 4 - 9.5 HRS EA - RJ NOBLE

LE-01- Crew Truck - QTY 2 - 9.5 HRS EA - RJ NOBLE

LL-03- Laborers - QTY 4 - 9.5 HRS EA - RJ NOBLE - RENTAL

LE-157- Tack Truck - QTY 1 - 9.5 HRS EA - RJ NOBLE

LE-23- Super 10 End Dump Truck - QTY 1 - 9.5 HRS EA - RJ NOBLE

LE-42- Utility Truck - QTY 2 - 9.5 HRS EA - RJ NOBLE

LE-19- Street sweeper - QTY 2 - 9.5 HRS EA - RJ NOBLE

LE-71- Pavement Grinder - QTY 2 - 9 HRS EA - PRSI

LE-19- Street sweeper - QTY 1 - 9.5 HRS EA - CTI

## Consolidated Resources

| Resource | Pay Type | Class | Qty | Company | Total Hours |
| --- | --- | --- | --- | --- | --- |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 2 | RJ NOBLE | 16 |
| LL-02- Foreman | CS - Cost | LO - Labor Overtime | 2 | RJ NOBLE | 3 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 10 | RJ NOBLE | 80 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 10 | RJ NOBLE | 15 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 6 | RJ NOBLE | 48 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 4 | RJ NOBLE | 6 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 2 | RJ NOBLE | 4 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 2 | PRSI | 16 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 2 | PRSI | 2 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 3 | HUDSON | 24 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 3 | HUDSON | 4.5 |
| LE-13- Roller H222 | CS - Cost | LR - Labor Regular Time | 3 | RJ NOBLE | 28.5 |
| LE-09- Skip Loader | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE | 9.5 |
| LE-125- Skid Steer | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE | 9.5 |
| LE-63- Asphalt Paver | CS - Cost | LR - Labor Regular Time | 2 | RJ NOBLE | 19 |
| LE-160- Pup Roller | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE | 9.5 |
| LE-30- Deere 210L Skip Loader | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE | 9.5 |
| LE-51- Pickup Truck | CS - Cost | LR - Labor Regular Time | 4 | RJ NOBLE | 38 |
| LE-01- Crew Truck | CS - Cost | LR - Labor Regular Time | 2 | RJ NOBLE | 19 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 4 | RJ NOBLE | 38 |
| LE-157- Tack Truck | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE | 9.5 |
| LE-23- Super 10 End Dump Truck | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE | 9.5 |
| LE-42- Utility Truck | CS - Cost | LR - Labor Regular Time | 2 | RJ NOBLE | 19 |
| LE-19- Street sweeper | CS - Cost | LR - Labor Regular Time | 2 | RJ NOBLE | 19 |
| LE-71- Pavement Grinder | CS - Cost | LR - Labor Regular Time | 2 | PRSI | 18 |
| LE-19- Street sweeper | CS - Cost | LR - Labor Regular Time | 1 | CTI | 9.5 |