DAILY FIELD REPORT - 06-30-2026

Project: Morena Conveyance Northern
Location: Nobel Dr Eastbound #2 Lane
Resident Engineer: Terry West
Weather: High: 70°F, Low: 62°F, Wind: 9 mph WSW, Drizzle
Hours: 19:30 - 03:30

## Activities Detail

Nobel Dr. - RJ Noble - Grind and Overlay — 489+00 to 506+60

• Grind & Overlay — Tuesday, June 30, 2026:

489+00 to 506+60

Actual Asphalt qtys and Actual lengths below

- Nobel Eastbound #2 lane + turn pockets — 1424.1 tons

- .36 Miles or 1922 Ft

Total: 76,506 SF / 1,424 Tons

• Material: 1/2" FIBER MIX ID#21242163F

• Plant: MM LAKESIDE

• Material: GRINDS TO MIRAMAR

• Asphalt Laid: 1424.10 tons

• Traffic Control: Traffic control was setup from West of genesee on Nobel heading east all the way through the town centre dr/nobel intersection, closing the #2 lane and any turn pockets. no travel North and South through Genesee and Nobel intersection. 3 cars were parked in the no park zone east of Lombard; however it was determined the No Parks had the incorrect time written on them. The PD was able to contact the owners however and the cars were moved, work went as planned

• The grind and overlay started approx 20' West of the nobel/genesee intersection, traveled East through Nobel #2 lane and ended at the east side of nobel town centre intersection.

31428 SF of concrete was encountered and documented by RJ Noble.

Work asphalt was laid through by 3:05 AM and street sweeping and traffic control removal was completed by 3:30 AM.

Hours: 7:30 PM - 3:00 AM

Manpower:

LL-02- Foreman - QTY 2 - 7.5 HRS EA - RJ NOBLE

LL-04- Operator - QTY 10 - 7.5 HRS EA - RJ NOBLE

LL-03- Laborers - QTY 6 - 7.5 HRS EA - RJ NOBLE

LL-11- Teamster - QTY 8 - 6.8 HRS EA - DIII

LL-03- Laborers - QTY 2 - 8 HRS EA - RJ NOBLE

LL-11- Teamster - QTY 22 - 7 HRS EA - DIII

LL-04- Operator - QTY 2 - 7 HRS EA - PRSI

LL-03- Laborers - QTY 1 - 7.5 HRS EA - HUDSON

Equipment:

LE-13- Roller H222 - QTY 4 - 7.5 HRS EA - RJ NOBLE

LE-09- Skip Loader - QTY 1 - 7.5 HRS EA - RJ NOBLE

LE-125- Skid Steer - QTY 1 - 7.5 HRS EA - RJ NOBLE

LE-63- Asphalt Paver - QTY 2 - 7.5 HRS EA - RJ NOBLE

LE-30- Deere 210L Skip Loader - QTY 1 - 7.5 HRS EA - RJ NOBLE

LE-51- Pickup Truck - QTY 5 - 7.5 HRS EA - RJ NOBLE

LE-01- Crew Truck - QTY 1 - 7.5 HRS EA - RJ NOBLE

LE-23- Super 10 End Dump Truck - QTY 8 - 6.8 HRS EA - DIII

LL-03- Laborers - QTY 4 - 7.5 HRS EA - RJ NOBLE - RENTAL

LE-157- Tack Truck - QTY 1 - 7.5 HRS EA - RJ NOBLE

LE-23- Super 10 End Dump Truck - QTY 1 - 7.5 HRS EA - RJ NOBLE

LE-42- Utility Truck - QTY 2 - 7.5 HRS EA - RJ NOBLE

LE-19- Street sweeper - QTY 2 - 7.5 HRS EA - RJ NOBLE

LE-23- Super 10 End Dump Truck - QTY 22 - 7 HRS EA - DIII

LE-71- Pavement Grinder - QTY 2 - 7 HRS EA - PRSI

LE-19- Street sweeper - QTY 1 - 7.5 HRS EA - CTI

## Consolidated Resources

| Resource | Pay Type | Class | Qty | Company | Total Hours |
| --- | --- | --- | --- | --- | --- |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 2 | RJ NOBLE | 15 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 10 | RJ NOBLE | 75 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 10 | RJ NOBLE | 75 |
| LL-11- Teamster | CS - Cost | LR - Labor Regular Time | 8 | DIII | 54.4 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 2 | RJ NOBLE | 16 |
| LL-11- Teamster | CS - Cost | LR - Labor Regular Time | 22 | DIII | 154 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 2 | PRSI | 14 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | HUDSON | 7.5 |
| LE-13- Roller H222 | CS - Cost | LR - Labor Regular Time | 4 | RJ NOBLE | 30 |
| LE-09- Skip Loader | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE | 7.5 |
| LE-125- Skid Steer | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE | 7.5 |
| LE-63- Asphalt Paver | CS - Cost | LR - Labor Regular Time | 2 | RJ NOBLE | 15 |
| LE-30- Deere 210L Skip Loader | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE | 7.5 |
| LE-51- Pickup Truck | CS - Cost | LR - Labor Regular Time | 5 | RJ NOBLE | 37.5 |
| LE-01- Crew Truck | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE | 7.5 |
| LE-23- Super 10 End Dump Truck | CS - Cost | LR - Labor Regular Time | 8 | DIII | 54.4 |
| LE-157- Tack Truck | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE | 7.5 |
| LE-23- Super 10 End Dump Truck | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE | 7.5 |
| LE-42- Utility Truck | CS - Cost | LR - Labor Regular Time | 2 | RJ NOBLE | 15 |
| LE-19- Street sweeper | CS - Cost | LR - Labor Regular Time | 2 | RJ NOBLE | 15 |
| LE-23- Super 10 End Dump Truck | CS - Cost | LR - Labor Regular Time | 22 | DIII | 154 |
| LE-71- Pavement Grinder | CS - Cost | LR - Labor Regular Time | 2 | PRSI | 14 |
| LE-19- Street sweeper | CS - Cost | LR - Labor Regular Time | 1 | CTI | 7.5 |