DAILY FIELD REPORT - 06-08-2026

Project: Morena Conveyance Northern
Location: Genesee @ SR-52/Marian Bear Park
Resident Engineer: Terry West
Weather: High: 74°F, Low: 59°F, Wind: 1 mph NNE, Partly Cloudy, Clear, Overcast
Hours: 20:00 - 06:00

## Activities Detail

SD MORENA CONVEYANCE - PAVE CREW / SD MORENA CONVEYANCE - POTHOLE CREW — GENESSEE AVE / SR 52 INT - UTC

• Digout Schedule — Monday, June 8, 2026:

- DO #Added 1 NB #1 — 1' depth × 8W × 40L = 320 SF (24 tons)

- DO # 26 NB #1 — 0.5' depth × 11W × 110L = 1,210 SF (90.75 tons)

- DO #SR-52 Inside lanes — 0.5' depth × 0W × 0L = 0 SF (152 tons)

- DO #29 SB #2 — 1' depth × 13W × 250L = 3,250 SF (243.75 tons)

- DO #31 SB #3 — 1' depth × 7W × 23L = 161 SF (12.075 tons)

- DO #32 SB #4 — 1' depth × 12W × 32L = 384 SF (28.8 tons)

Total: 5,325 SF / 551.375 Tons

• Material: 580 TN 3/4" HMA

• Plant: MM MIRAMAR

Hours: 8:30 PM - 5:30 AM

Manpower:

LL-02- Foreman - QTY 1 - 9 HRS EA - RJ NOBLE - SOUTH

LL-04- Operator - QTY 1 - 9 HRS EA - RJ NOBLE - SOUTH

LL-03- Laborers - QTY 1 - 9 HRS EA - RJ NOBLE - SOUTH

LL-04- Operator - QTY 1 - 8 HRS EA - DIII

LL-03- Laborers - QTY 1 - 5.5 HRS EA - RJ NOBLE - SOUTH

LL-04- Operator - QTY 1 - 5.5 HRS EA - DIII

LL-04- Operator - QTY 1 - 5.5 HRS EA - PRSI

LL-03- Laborers - QTY 1 - 9 HRS EA - HUDSON

Equipment:

LE-13- Roller H222 - QTY 1 - 9 HRS EA - RJ NOBLE - SOUTH

LE-09- Skip Loader - QTY 1 - 9 HRS EA - RJ NOBLE - SOUTH

LE-125- Skid Steer - QTY 1 - 9 HRS EA - RJ NOBLE - SOUTH

LE-63- Asphalt Paver - QTY 1 - 9 HRS EA - RJ NOBLE - SOUTH

LE-51- Pickup Truck - QTY 1 - 9 HRS EA - RJ NOBLE - SOUTH

LE-01- Crew Truck - QTY 1 - 9 HRS EA - RJ NOBLE - SOUTH

LE-141- End Dump - QTY 1 - 8 HRS EA - DIII

LE-42- Utility Truck - QTY 1 - 9 HRS EA - RJ NOBLE - SOUTH

LE-19- Street sweeper - QTY 1 - 9 HRS EA - RJ NOBLE - SOUTH

LE-141- End Dump - QTY 1 - 5.5 HRS EA - DIII

LE-71- Pavement Grinder - QTY 1 - 5.5 HRS EA - PRSI

LL-08- PM - QTY 1 - 9 HRS EA - RJ NOBLE - SOUTH - RENTAL

Extra Work Manpower:

LL-03- Laborers - QTY 1 - 9 HRS EA - RJ NOBLE - SOUTH

Extra Work Equipment:

LE-01- Crew Truck - QTY 1 - 9 HRS EA - RJ NOBLE - SOUTH

## Consolidated Resources

| Resource | Pay Type | Class | Qty | Company | Total Hours |
| --- | --- | --- | --- | --- | --- |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 8 |
| LL-02- Foreman | CS - Cost | LO - Labor Overtime | 1 | RJ NOBLE - SOUTH | 1 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 8 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 1 | RJ NOBLE - SOUTH | 1 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 8 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 1 | RJ NOBLE - SOUTH | 1 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 8 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 1 | RJ NOBLE - SOUTH | 1 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 8 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 1 | RJ NOBLE - SOUTH | 1 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 8 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 1 | RJ NOBLE - SOUTH | 1 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 8 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 1 | RJ NOBLE - SOUTH | 1 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 8 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 1 | RJ NOBLE - SOUTH | 1 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 8 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 1 | RJ NOBLE - SOUTH | 1 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 8 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 1 | RJ NOBLE - SOUTH | 1 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 8 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 1 | RJ NOBLE - SOUTH | 1 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | DIII | 8 |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 8 |
| LL-02- Foreman | CS - Cost | LO - Labor Overtime | 1 | RJ NOBLE - SOUTH | 1 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 8 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 1 | RJ NOBLE - SOUTH | 1 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 8 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 1 | RJ NOBLE - SOUTH | 1 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 8 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 1 | RJ NOBLE - SOUTH | 1 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 8 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 1 | RJ NOBLE - SOUTH | 1 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 5.5 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 5.5 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 8 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 1 | RJ NOBLE - SOUTH | 1 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | DIII | 5.5 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | PRSI | 5.5 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | HUDSON | 8 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 1 | HUDSON | 1 |
| LE-13- Roller H222 | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 9 |
| LE-09- Skip Loader | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 9 |
| LE-125- Skid Steer | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 9 |
| LE-13- Roller H222 | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 9 |
| LE-63- Asphalt Paver | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 9 |
| LE-13- Roller H222 | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 9 |
| LE-63- Asphalt Paver | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 9 |
| LE-13- Roller H222 | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 9 |
| LE-51- Pickup Truck | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 9 |
| LE-51- Pickup Truck | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 9 |
| LE-01- Crew Truck | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 9 |
| LE-141- End Dump | CS - Cost | LR - Labor Regular Time | 1 | DIII | 8 |
| LE-42- Utility Truck | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 9 |
| LE-19- Street sweeper | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 9 |
| LE-42- Utility Truck | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 9 |
| LE-19- Street sweeper | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 9 |
| LE-51- Pickup Truck | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 9 |
| LE-51- Pickup Truck | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 9 |
| LE-141- End Dump | CS - Cost | LR - Labor Regular Time | 1 | DIII | 5.5 |
| LE-71- Pavement Grinder | CS - Cost | LR - Labor Regular Time | 1 | PRSI | 5.5 |
| LL-03- Laborers | EW - Extra Work | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 8 |
| LL-03- Laborers | EW - Extra Work | LO - Labor Overtime | 1 | RJ NOBLE - SOUTH | 1 |
| LL-03- Laborers | EW - Extra Work | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 8 |
| LL-03- Laborers | EW - Extra Work | LO - Labor Overtime | 1 | RJ NOBLE - SOUTH | 1 |
| LE-01- Crew Truck | EW - Extra Work | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 9 |