DAILY FIELD REPORT - 07-01-2026

Project: Morena Conveyance Northern
Location: Vicinity of AV 13
Resident Engineer: Terry West
Weather: 
Hours: 19:30 - 18:45

General Notes:

OHL Crew performed overnight asphalt patching in the southbound lanes of Town Center Drive. The work involved traffic control, removal of an existing patch, and placement of new asphalt in multiple lifts. RJ Nobel performed grind and pave on Nobel Westbound outside lanes and Genesee Southbound outside lanes

## Activities Detail

Vicinity of AV 13 - OHL - Base Pave — Vicinity of AV 13

• Traffic control was established for the work area in the southbound lanes of Town Center Drive.

• The traffic control setup extended from La Jolla Village Drive to Town Center Gateway.

• The turn pocket and the number one lane were closed, with traffic shifted into the number two lane.

• OHL's crew began by stripping and removing the existing cold mix patch from the excavation area around AV 13.

• Following the removal of the old material, the crew awaited the delivery of new asphalt.

• The asphalt delivery truck arrived on-site at approximately 4:30 AM.

• The crew proceeded to place the new asphalt into the excavation in three distinct lifts.

• A skid steer was utilized to place the asphalt into the excavation, while rakes and shovels were used to spread the material evenly prior to compaction.

• The first two lifts of asphalt were compacted using a wacker.

• The final lift, or cap, was compacted using a vibratory plate.

• Upon completion of paving activities, the crew wrapped up the work at 6:30 AM.

• All traffic control devices were picked up, and the crew was off the road by 6:45 AM.

Hours: 10:00 PM - 6:30 AM

Manpower:

LL-02- Foreman - QTY 1 - 8.5 HRS EA - OHL

LL-03- Laborers - QTY 3 - 8.5 HRS EA - OHL

LL-04- Operator - QTY 1 - 8.5 HRS EA - OHL

Equipment:

LE-01- Crew Truck - QTY 1 - 8 HRS EA - OHL NA

Light Plant - QTY 1 - 8 HRS EA - OHL NA

LE-125- Skid Steer - QTY 1 - 8 HRS EA - OHL NA

LE-23- Super 10 End Dump Truck - QTY 1 - 8 HRS EA - OHL NA

LE-155- Wacker Neuson RTLx-SC3 Trench Roller - QTY 1 - 8 HRS EA - OHL NA

Vibratory Plate - QTY 1 - 8 HRS EA - OHL NA

LE-111- Trailer Mounted Blower - QTY 1 - 8 HRS EA - OHL NA

Nobel and Genesee - RJ Noble - Grind and Pave — SB GENESSEE AVE / NOBEL DR - UTC

• Grind & Overlay — Tuesday, June 30, 2026:

- WB OUTSIDE NOBEL — 54,991 SF (1031 tons)

- SB OUTSIDE GENESEE — 21,515 SF (403 tons)

Total: 76,506 SF / 1,434 Tons

• Material: 1/2" FIBER MIX ID#21242163F

• Plant: MM LAKESIDE

• Material: GRINDS TO MIRAMAR

• Asphalt Laid: 1317.33 tons

• Traffic Control: Traffic control was setup per plan, closing the Westbound #2 lane on Nobel. The closure started from the east side of Town Centre all the way down to the west side of genesee. The North/South travel was blocked at Town Centre and at Genesee. The #2 lane on South bound Genesee was also closed from Nobel to Decoro

• The grind and overlay work started at east end where RJ Noble left off last Friday after the plant had to shut down. Starting point Sta. 505+16.48 and ending 489+48 on Nobel. Then a second run started at 488+66 on Genesee, and ended at 480+92.

Asphalt laid - 1317.33 Tons.

RJ Nobel encountered 29071 SQ FT of concrete while grinding.

The quality firm was on site taking compaction tests thorughout the night.

RJ noble finished the evening work and was off site at 5:00 AM.

Hours: 7:30 PM - 5:00 AM

Manpower:

LL-02- Foreman - QTY 2 - 9.5 HRS EA - RJ NOBLE

LL-04- Operator - QTY 10 - 9.5 HRS EA - RJ NOBLE

LL-03- Laborers - QTY 6 - 9.5 HRS EA - RJ NOBLE

LL-11- Teamster - QTY 6 - 8.8 HRS EA - DIII & MTS/STM

LL-03- Laborers - QTY 2 - 10 HRS EA - RJ NOBLE

LL-11- Teamster - QTY 18 - 9 HRS EA - DIII

LL-04- Operator - QTY 2 - 9 HRS EA - PRSI

LL-03- Laborers - QTY 1 - 9.5 HRS EA - HUDSON

LL-42- Asphalt QC Tech - QTY 1 - 9.5 HRS EA - THE QUALITY FIRM

Equipment:

LE-13- Roller H222 - QTY 3 - 9.5 HRS EA - RJ NOBLE

LE-09- Skip Loader - QTY 1 - 9.5 HRS EA - RJ NOBLE

LE-125- Skid Steer - QTY 1 - 9.5 HRS EA - RJ NOBLE

LE-63- Asphalt Paver - QTY 2 - 9.5 HRS EA - RJ NOBLE

LE-160- Pup Roller - QTY 1 - 9.5 HRS EA - RJ NOBLE

LE-30- Deere 210L Skip Loader - QTY 1 - 9.5 HRS EA - RJ NOBLE

LE-51- Pickup Truck - QTY 4 - 9.5 HRS EA - RJ NOBLE

LE-01- Crew Truck - QTY 2 - 9.5 HRS EA - RJ NOBLE

LE-23- Super 10 End Dump Truck - QTY 6 - 8.8 HRS EA - DIII & MTS/STM

LL-03- Laborers - QTY 4 - 9.5 HRS EA - RJ NOBLE - RENTAL

LE-157- Tack Truck - QTY 1 - 9.5 HRS EA - RJ NOBLE

LE-23- Super 10 End Dump Truck - QTY 1 - 9.5 HRS EA - RJ NOBLE

LE-42- Utility Truck - QTY 2 - 9.5 HRS EA - RJ NOBLE

LE-19- Street sweeper - QTY 2 - 9.5 HRS EA - RJ NOBLE

LE-23- Super 10 End Dump Truck - QTY 18 - 9 HRS EA - DIII

LE-71- Pavement Grinder - QTY 2 - 9 HRS EA - PRSI

LE-19- Street sweeper - QTY 1 - 9.5 HRS EA - CTI

## Consolidated Resources

| Resource | Pay Type | Class | Qty | Company | Total Hours |
| --- | --- | --- | --- | --- | --- |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 1 | OHL | 8 |
| LL-02- Foreman | CS - Cost | LO - Labor Overtime | 1 | OHL | 0.5 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 3 | OHL | 24 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 3 | OHL | 1.5 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | OHL | 8 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 1 | OHL | 0.5 |
| LE-01- Crew Truck | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| Light Plant | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LE-125- Skid Steer | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LE-23- Super 10 End Dump Truck | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LE-155- Wacker Neuson RTLx-SC3 Trench Roller | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| Vibratory Plate | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LE-111- Trailer Mounted Blower | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 2 | RJ NOBLE | 16 |
| LL-02- Foreman | CS - Cost | LO - Labor Overtime | 2 | RJ NOBLE | 3 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 10 | RJ NOBLE | 80 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 10 | RJ NOBLE | 15 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 8 | RJ NOBLE | 64 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 6 | RJ NOBLE | 9 |
| LL-11- Teamster | CS - Cost | LR - Labor Regular Time | 6 | DIII & MTS/STM | 48 |
| LL-11- Teamster | CS - Cost | LO - Labor Overtime | 6 | DIII & MTS/STM | 4.8 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 2 | RJ NOBLE | 4 |
| LL-11- Teamster | CS - Cost | LR - Labor Regular Time | 18 | DIII | 144 |
| LL-11- Teamster | CS - Cost | LO - Labor Overtime | 18 | DIII | 18 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 2 | PRSI | 16 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 2 | PRSI | 2 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | HUDSON | 8 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 1 | HUDSON | 1.5 |
| LL-42- Asphalt QC Tech | CS - Cost | LR - Labor Regular Time | 1 | THE QUALITY FIRM | 8 |
| LL-42- Asphalt QC Tech | CS - Cost | LO - Labor Overtime | 1 | THE QUALITY FIRM | 1.5 |
| LE-13- Roller H222 | CS - Cost | LR - Labor Regular Time | 3 | RJ NOBLE | 28.5 |
| LE-09- Skip Loader | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE | 9.5 |
| LE-125- Skid Steer | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE | 9.5 |
| LE-63- Asphalt Paver | CS - Cost | LR - Labor Regular Time | 2 | RJ NOBLE | 19 |
| LE-160- Pup Roller | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE | 9.5 |
| LE-30- Deere 210L Skip Loader | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE | 9.5 |
| LE-51- Pickup Truck | CS - Cost | LR - Labor Regular Time | 4 | RJ NOBLE | 38 |
| LE-01- Crew Truck | CS - Cost | LR - Labor Regular Time | 2 | RJ NOBLE | 19 |
| LE-23- Super 10 End Dump Truck | CS - Cost | LR - Labor Regular Time | 6 | DIII & MTS/STM | 52.8 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 4 | RJ NOBLE | 38 |
| LE-157- Tack Truck | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE | 9.5 |
| LE-23- Super 10 End Dump Truck | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE | 9.5 |
| LE-42- Utility Truck | CS - Cost | LR - Labor Regular Time | 2 | RJ NOBLE | 19 |
| LE-19- Street sweeper | CS - Cost | LR - Labor Regular Time | 2 | RJ NOBLE | 19 |
| LE-23- Super 10 End Dump Truck | CS - Cost | LR - Labor Regular Time | 18 | DIII | 162 |
| LE-71- Pavement Grinder | CS - Cost | LR - Labor Regular Time | 2 | PRSI | 18 |
| LE-19- Street sweeper | CS - Cost | LR - Labor Regular Time | 1 | CTI | 9.5 |