DAILY FIELD REPORT - 07-08-2026

Project: Morena Conveyance Northern
Resident Engineer: Terry West
Weather: High: 100°F, Low: 65°F, Wind: 10 mph S, Clear
Hours: 19:30 - 03:30

## Activities Detail

Town Centre and Executive - RJ Noble - Grind and Overlay — 528+17 to 556+45

• Grind & Overlay — Wednesday, July 8, 2026:

Estimated

- NB INSIDE TOWN CENTER — 31,701 SF (594 tons)

- CENTER LANES EXECUTIVE — 32,000 SF (600 tons)

Total: 63,701 SF / 1,194 Tons

-------------------------------------------------------------

• Material:  1/2" FIBER MIX ID#21242163F

• Plant: MM LAKESIDE

• Material: GRINDS TO MIRAMAR

-------------------------------------------------------------

•Actual Asphalt Laid: 1126.23 tons

• Traffic Control: Traffic control Setup: Traffic control setup on Town Centre and Executive - On Town Centre the # 1 lane NB was closed to pedestrian traffic, they were routed into the # 2 lane from town centre gateway to executive. La Jolla Village drive left hand turn lane and through traffic was closed, with the through traffic being opened up as soon as the asphalt was ok to drive on.

On executive the # 1 lane was closed in both directions with through traffic blocked for judicial dr. and town centre southbound lanes.

• Description of work: RJ Noble started at town centre gateway with the grind crew, followed by the paving crew. The work progressed North up town centre then East down executive #1 lane until reacing judicial. once at judicial they turned around and got the #1 Westbound lane.

The paving wrapped up at 330 am with street sweeping and traffic control finishing at 4:30AM

The quality firm and kleinfelder were both on site taking compaction tests

Hours: 7:30 PM - 4:30 AM

Manpower:

LL-02- Foreman - QTY 2 - 9 HRS EA - RJ NOBLE

LL-04- Operator - QTY 11 - 9 HRS EA - RJ NOBLE

LL-03- Laborers - QTY 11 - 9 HRS EA - RJ NOBLE

LL-11- Teamster - QTY 24 - 9 HRS EA - DIII

LL-04- Operator - QTY 2 - 9 HRS EA - PRSI

Equipment:

LE-13- Roller H222 - QTY 3 - 9 HRS EA - RJ NOBLE

LE-30- Deere 210L Skip Loader - QTY 1 - 9 HRS EA - RJ NOBLE

LE-125- Skid Steer - QTY 1 - 9 HRS EA - RJ NOBLE

LE-160- Pup Roller - QTY 1 - 9 HRS EA - RJ NOBLE

LE-63- Asphalt Paver - QTY 2 - 9 HRS EA - RJ NOBLE

LE-51- Pickup Truck - QTY 5 - 9 HRS EA - RJ NOBLE

LE-19- Street sweeper - QTY 2 - 9 HRS EA - RJ NOBLE

LE-01- Crew Truck - QTY 24 - 9 HRS EA - RJ NOBLE

LE-42- Utility Truck - QTY 1 - 9 HRS EA - RJ NOBLE

LE-71- Pavement Grinder - QTY 2 - 9 HRS EA - RJ NOBLE

Consultants:

## Consolidated Resources

| Resource | Pay Type | Class | Qty | Company | Total Hours |
| --- | --- | --- | --- | --- | --- |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 2 | RJ NOBLE | 16 |
| LL-02- Foreman | CS - Cost | LO - Labor Overtime | 2 | RJ NOBLE | 2 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 11 | RJ NOBLE | 88 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 11 | RJ NOBLE | 11 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 11 | RJ NOBLE | 88 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 11 | RJ NOBLE | 11 |
| LL-11- Teamster | CS - Cost | LR - Labor Regular Time | 24 | DIII | 192 |
| LL-11- Teamster | CS - Cost | LO - Labor Overtime | 24 | DIII | 24 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 2 | PRSI | 16 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 2 | PRSI | 2 |
| LE-13- Roller H222 | CS - Cost | LR - Labor Regular Time | 3 | RJ NOBLE | 27 |
| LE-30- Deere 210L Skip Loader | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE | 9 |
| LE-125- Skid Steer | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE | 9 |
| LE-160- Pup Roller | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE | 9 |
| LE-63- Asphalt Paver | CS - Cost | LR - Labor Regular Time | 2 | RJ NOBLE | 18 |
| LE-51- Pickup Truck | CS - Cost | LR - Labor Regular Time | 5 | RJ NOBLE | 45 |
| LE-19- Street sweeper | CS - Cost | LR - Labor Regular Time | 2 | RJ NOBLE | 18 |
| LE-01- Crew Truck | CS - Cost | LR - Labor Regular Time | 24 | RJ NOBLE | 216 |
| LE-42- Utility Truck | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE | 9 |
| LE-71- Pavement Grinder | CS - Cost | LR - Labor Regular Time | 2 | RJ NOBLE | 18 |