DAILY FIELD REPORT - 07-09-2026

Project: Morena Conveyance Northern
Resident Engineer: Terry West
Weather: 
Hours: 06:30 - 15:00

## Activities Detail

SD MORENA CONVEYANCE - PAVE CREW / SD MORENA CONVEYANCE - GRIND CREW — 548+49 to 507+05

• Grind & Overlay — Wednesday, July 8, 2026:

548+49 to 507+05

- SB INSIDE TOWNE CENTER — 82,876 SF (1554 tons)

Total: 82,876 SF / 1,554 Tons - estimated

• Material: 1550 TONS 1/2" FIBER MIX ID#21242163F

• Plant: MM LAKESIDE

• Material: GRINDS TO MIRAMAR

• Asphalt Laid: 1484.69 tons - Actual

• Traffic Control: • RJ Noble established a traffic control plan on the southbound lanes of Town Center Drive, extending from Executive Drive to Nobel Drive.

• The setup involved closing the #1 lane and the left-hand turn lanes.

• The left-hand turn lanes at the intersections of La Jolla, Golden Haven, and Renaissance were closed.

• All southbound traffic was shifted over to the #2 lane through the work area.

• Detour signage was set up for all affected side streets.

• • RJ Noble began grind and pave operations, starting at Executive.

• The crew worked in the southbound direction, proceeding down the southbound inside lanes.

• Work was performed in the #1 lane and the left-hand turn lanes.

• The grinding operation was followed by the asphalt overlay, which commenced approximately 15 minutes behind the grinder.

• The crew progressed from Executive all the way down to Nobel, where they stopped.

• Paving activities were completed by 3:45 PM.

• Street sweeping was completed by 4:20 PM.

• All traffic control was removed, and the streets were reopened to traffic by 4:30 PM. Kleinfelder and the quality firm were on site throughout the night testing compaction on the asphalt.

No additional concrete was found

Hours: 7:30 PM - 4:30 AM

Manpower:

LL-02- Foreman - QTY 2 - 9 HRS EA - RJ NOBLE

LL-04- Operator - QTY 10 - 9 HRS EA - RJ NOBLE

LL-03- Laborers - QTY 9 - 9 HRS EA - RJ NOBLE

LL-11- Teamster - QTY 10 - 8.3 HRS EA - DIII / SD GOLD

LL-03- Laborers - QTY 2 - 9.5 HRS EA - RJ NOBLE

LL-11- Teamster - QTY 22 - 8.5 HRS EA - DIII

LL-04- Operator - QTY 2 - 8.5 HRS EA - PRSI

Equipment:

LE-83- Equipment-Hauling Trailer - QTY 1 - 9 HRS EA - RJ NOBLE

LE-113- McElroy Tracstar 16-inch Fusion Machine - QTY 1 - 9 HRS EA - RJ NOBLE

LE-13- Roller H222 - QTY 2 - 9 HRS EA - RJ NOBLE

LE-09- Skip Loader - QTY 1 - 9 HRS EA - RJ NOBLE

LE-125- Skid Steer - QTY 1 - 9 HRS EA - RJ NOBLE

LE-160- Pup Roller - QTY 1 - 9 HRS EA - RJ NOBLE

LE-63- Asphalt Paver - QTY 2 - 9 HRS EA - RJ NOBLE

LE-51- Pickup Truck - QTY 5 - 9 HRS EA - RJ NOBLE

LE-19- Street sweeper - QTY 2 - 9 HRS EA - RJ NOBLE

LE-01- Crew Truck - QTY 10 - 9 HRS EA - DIII

LE-42- Utility Truck - QTY 1 - 9 HRS EA - RJ NOBLE

LE-01- Crew Truck - QTY 22 - 9 HRS EA - RJ NOBLE

LE-71- Pavement Grinder - QTY 2 - 9 HRS EA - RJ NOBLE

## Consolidated Resources

| Resource | Pay Type | Class | Qty | Company | Total Hours |
| --- | --- | --- | --- | --- | --- |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 2 | RJ NOBLE | 16 |
| LL-02- Foreman | CS - Cost | LO - Labor Overtime | 2 | RJ NOBLE | 2 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 10 | RJ NOBLE | 80 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 10 | RJ NOBLE | 10 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 11 | RJ NOBLE | 88 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 9 | RJ NOBLE | 9 |
| LL-11- Teamster | CS - Cost | LR - Labor Regular Time | 10 | DIII / SD GOLD | 80 |
| LL-11- Teamster | CS - Cost | LO - Labor Overtime | 10 | DIII / SD GOLD | 3 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 2 | RJ NOBLE | 3 |
| LL-11- Teamster | CS - Cost | LR - Labor Regular Time | 22 | DIII | 176 |
| LL-11- Teamster | CS - Cost | LO - Labor Overtime | 22 | DIII | 11 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 2 | PRSI | 16 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 2 | PRSI | 1 |
| LE-83- Equipment-Hauling Trailer | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE | 9 |
| LE-113- McElroy Tracstar 16-inch Fusion Machine | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE | 9 |
| LE-13- Roller H222 | CS - Cost | LR - Labor Regular Time | 2 | RJ NOBLE | 18 |
| LE-09- Skip Loader | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE | 9 |
| LE-125- Skid Steer | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE | 9 |
| LE-160- Pup Roller | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE | 9 |
| LE-63- Asphalt Paver | CS - Cost | LR - Labor Regular Time | 2 | RJ NOBLE | 18 |
| LE-51- Pickup Truck | CS - Cost | LR - Labor Regular Time | 5 | RJ NOBLE | 45 |
| LE-19- Street sweeper | CS - Cost | LR - Labor Regular Time | 2 | RJ NOBLE | 18 |
| LE-01- Crew Truck | CS - Cost | LR - Labor Regular Time | 10 | DIII | 90 |
| LE-42- Utility Truck | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE | 9 |
| LE-01- Crew Truck | CS - Cost | LR - Labor Regular Time | 22 | RJ NOBLE | 198 |
| LE-71- Pavement Grinder | CS - Cost | LR - Labor Regular Time | 2 | RJ NOBLE | 18 |