DAILY FIELD REPORT - 02-27-2026

Project: Morena Conveyance North
Resident Engineer: 
Weather: High: 79°F, Low: 43°F, Sunny
Hours: 07:00 - 15:30

## Activities Detail

Morena Conveyance North - OHL - Concrete, Demo, and Site Maintenance

Performing multiple restoration tasks today.
• A first aid incident occurred involving a worker's finger; project safety personnel were notified.
• Placed concrete collars around the Bid Item #5 drain valve boxes located within Marian Bear Park.
• Demolished concrete from the base of existing fence posts to facilitate removal.
• Cut removed chain-link fence fabric into sections for transport and recycling.
• Performed general site housekeeping and Best Management Practice (BMP) maintenance.

Hours: 7:00 AM - 5:30 PM

Manpower:

LL-03- Laborers - QTY 1 - 9.5 HRS EA - OHLA

LL-03- Laborers - QTY 1 - 9.5 HRS EA - OHLA

LL-02- Foreman - QTY 1 - 10 HRS EA - OHLA

LL-04- Operator - QTY 1 - 8 HRS EA - OHLA

LL-03- Laborers - QTY 1 - 9.5 HRS EA - OHLA

LL-03- Laborers - QTY 1 - 9.5 HRS EA - OHLA

Equipment:

LE-51- Pickup Truck - QTY 1 - 9.5 HRS EA - OHL NA

LE-32- Skytrak Forklift - QTY 1 - 8 HRS EA - Herc

Town Centre Dr & La Jolla Village Dr - OHLA - Traffic Control & Dewatering

oh and *   Mobilized one (1) forklift from the Marian Bear Park yard to the Executive Drive location.
*   Established traffic control on Town Centre Drive for the inspection and cleaning of the existing 30-inch pipeline.
*   Set up a dewatering pump and began pumping water from the pipeline into a water truck.
*   Removed all traffic control at 3:30 PM.

Hours: 7:00 AM - 4:30 PM

Manpower:

LL-02- Foreman - QTY 1 - 9 HRS EA - OHLA

LL-03- Laborers - QTY 1 - 8 HRS EA - OHLA

LL-03- Laborers - QTY 1 - 7 HRS EA - OHLA

LL-03- Laborers - QTY 1 - 9 HRS EA - OHL NA

LL-03- Laborers - QTY 1 - 7 HRS EA - OHLA

Equipment:

LE-111- Trailer Mounted Blower - QTY 1 - 8 HRS EA - United Rentals - RENTAL

LE-01- Crew Truck - QTY 1 - 8 HRS EA - OHLA

## Consolidated Resources

| Resource | Pay Type | Class | Qty | Company | Total Hours |
| --- | --- | --- | --- | --- | --- |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | OHLA | 8 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 1 | OHLA | 1.5 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | OHLA | 8 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 1 | OHLA | 1.5 |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 1 | OHLA | 8 |
| LL-02- Foreman | CS - Cost | LO - Labor Overtime | 1 | OHLA | 2 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | OHLA | 8 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | OHLA | 8 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 1 | OHLA | 1.5 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | OHLA | 8 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 1 | OHLA | 1.5 |
| LE-51- Pickup Truck | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LE-51- Pickup Truck | CS - Cost | LO - Labor Overtime | 1 | OHL NA | 1.5 |
| LE-32- Skytrak Forklift | CS - Cost | LR - Labor Regular Time | 1 | Herc | 8 |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 1 | OHLA | 8 |
| LL-02- Foreman | CS - Cost | LO - Labor Overtime | 1 | OHLA | 1 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | OHLA | 8 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | OHLA | 7 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 1 | OHL NA | 1 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | OHLA | 7 |
| LE-111- Trailer Mounted Blower | CS - Cost | LR - Labor Regular Time | 1 | United Rentals | 8 |
| LE-01- Crew Truck | CS - Cost | LR - Labor Regular Time | 1 | OHLA | 8 |