DAILY FIELD REPORT - 03-10-2026

Project: Morena Conveyance North
Resident Engineer: Terry West
Weather: High: 66°F, Low: 54°F, Cloudy
Hours: 07:00 - 15:30

## Activities Detail

Town Centre - Sta 540+10 to Sta 523+52 - OHLA / Norcal Pipeline Services- Traffic Control & CCTV Support

• Set up traffic control for the CCTV crew, at Town Centre and La Jolla Village
• Set up traffic control for Blow off # 7
• A crew went to the launch shaft to pick up the forklift.
• Set up the jobsite, started to repair joints, and clean the pipe at blow off # 7 heading towards noble. 
•picked up traffic control at BO 7 at 330 PM. 
• The CCTV inspection went from Sta 540+10 to Sta 523+52.

Hours: 6:30 AM - 4:00 PM

Manpower:

LL-03- Laborers - QTY 1 - 8 HRS EA - OHL NA

LL-02- Foreman - QTY 1 - 9 HRS EA - OHL NA

LL-03- Laborers - QTY 1 - 9 HRS EA - OHL NA

LL-04- Operator - QTY 2 - 9 HRS EA - NorCal Pipeline

Equipment:

LE-01- Crew Truck - QTY 1 - 8 HRS EA - OHL NA

LE-72- Arrow Board - QTY 1 - 8 HRS EA - OHL NA

LE-158- CCTV Truck - QTY 1 - 9 HRS EA - NorCal Pipeline

Genesee Ave & Nobel Bear Trail - Trenching & Dewatering

• Set up traffic control and laid out the 4-inch fiber optic trench.
• Saw cut the cathodic protection trench line at Genesee Avenue at the SL S2.
• Guided traffic while continuing layout to the sidewalk.
• Laid out the trench for cathodic protection north of the SR 52 manway.
• Dewatered the 48-inch and 30-inch pipelines at bleed off BO #5.
• Hauled the excavator from Town Center to Marian Bear Park to excavate around the vault lid to shift the lid.
Picked up traffic control at 4:30PM

Hours: 6:30 AM - 5:00 PM

Manpower:

LL-02- Foreman - QTY 1 - 10 HRS EA - OHL NA

LL-03- Laborers - QTY 1 - 10 HRS EA - OHL NA

LL-03- Laborers - QTY 1 - 8 HRS EA - OHL NA

LL-04- Operator - QTY 1 - 8 HRS EA - OHL NA

Equipment:

LE-51- Pickup Truck - QTY 1 - 8 HRS EA - OHL NA

LE-51- Pickup Truck - QTY 1 - 8 HRS EA - OHL NA

## Consolidated Resources

| Resource | Pay Type | Class | Qty | Company | Total Hours |
| --- | --- | --- | --- | --- | --- |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-02- Foreman | CS - Cost | LO - Labor Overtime | 1 | OHL NA | 1 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 1 | OHL NA | 1 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 2 | NorCal Pipeline | 16 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 2 | NorCal Pipeline | 2 |
| LE-01- Crew Truck | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LE-72- Arrow Board | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LE-158- CCTV Truck | CS - Cost | LR - Labor Regular Time | 1 | NorCal Pipeline | 9 |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-02- Foreman | CS - Cost | LO - Labor Overtime | 1 | OHL NA | 2 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 1 | OHL NA | 2 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LE-51- Pickup Truck | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |