DAILY FIELD REPORT - 03-28-2026

Project: Morena Conveyance North
Location: Marian Bear Park
Resident Engineer: Terry West
Weather: High: 75°F, Low: 60°F, Wind: W 2 mph, Cloudy
Hours: 07:00 - 15:30

General Notes:

Worked Saturday to get work at the park completed. Foreman wont be on site Mon-Wed next week.

## Activities Detail

Bear Park & Town Center - OHLA - Concrete Curb & Pipeline Work

• Performed subgrade preparation for a new curb at the Bear Park entrance.
• Demolished the existing asphalt driveway and off-hauled all resulting material.
• Formed and placed 4 cubic yards of concrete for a new curb, tying into the existing curb.
• Imported, placed, and compacted Class II base in preparation for asphalt paving.
• Imported and placed material to fine grade the area behind the sidewalk and the newly placed curb within Marian Bear Park in preparation for hydroseeding.
• Picked up materials required for concrete placement.

Hours: 6:30 AM - 3:00 PM

Manpower:

LL-03- Laborers - QTY 5 - 8 HRS EA - OHL NA

LL-04- Operator - QTY 1 - 8 HRS EA - OHL NA

LL-02- Foreman - QTY 2 - 8 HRS EA - OHL NA

Equipment:

LE-04- Mini Excavator - QTY 1 - 8 HRS EA - Prime

LE-159- Roller - QTY 1 - 8 HRS EA - Prime

LE-125- Skid Steer - QTY 1 - 8 HRS EA - Herc

LE-23- Super 10 End Dump Truck - QTY 1 - 8 HRS EA - Herc

LE-51- Pickup Truck - QTY 1 - 8 HRS EA - OHL NA

## Consolidated Resources

| Resource | Pay Type | Class | Qty | Company | Total Hours |
| --- | --- | --- | --- | --- | --- |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 5 | OHL NA | 40 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 2 | OHL NA | 16 |
| LE-04- Mini Excavator | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LE-159- Roller | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LE-125- Skid Steer | CS - Cost | LR - Labor Regular Time | 1 | Herc | 8 |
| LE-23- Super 10 End Dump Truck | CS - Cost | LR - Labor Regular Time | 1 | Herc | 8 |
| LE-51- Pickup Truck | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LE-51- Pickup Truck | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |