DAILY FIELD REPORT - 03-31-2026

Project: Morena Conveyance North
Resident Engineer: Terry West
Weather: High: 73°F, Low: 60°F, Wind: NE 4 mph, Cloudy
Hours: 07:00 - 15:30

## Activities Detail

Decoro and Genesee - AR Concrete - Curb Ramp Pour

• OHLA setup traffic control in the #2 southbound lane and the # 2 westbound and southbound lanes on decoro west of genesee
• AR Concrete was on site to pour and finish the curb ramps at Governor on the NW and NE corners of Governor and Genesee.
• Demolition was completed the previous day.
• A soils technician inspected and approved the subgrade prior to the concrete pour.
• AR Concrete arrived at 11:00 AM, the pour started at 12:00 PM.
Concrete was poured and finished  by 4:45 PM. 
used cones and snow fence to secure the area while it cured over night.
Traffic control was removed by OHLA traffic control crew. 
all work was completed by 5:30 PM.

Hours: 6:00 AM - 3:00 PM

Manpower:

LL-03- Laborers - QTY 4 - 10 HRS EA - AR Concrete

LL-01- Superintendent - QTY 1 - 10 HRS EA - AR Concrete

LL-18- Visitor - QTY 1 - 8 HRS EA - Prime

LL-02- Foreman - QTY 1 - 10 HRS EA - AR Concrete

LL-15- Cement Mason - QTY 2 - 10 HRS EA - AR Concrete

Marian Bear Park - GC Fence - Fence Installation

• Continued installation of the Caltrans-type fence at Marian Bear Park.
• Completed boring the final two holes for the fence posts using a skid steer with an auger attachment.
• Began setting fence posts and placing concrete at each post location.
• Set and placed concrete for all but the final five posts at the north end of the fence alignment.

Hours: 7:00 AM - 3:30 PM

Manpower:

LL-03- Laborers - QTY 2 - 8 HRS EA - GC Fence

Equipment:

LE-51- Pickup Truck - QTY 1 - 8 HRS EA - GC Fence

LE-66- Concrete Mixer - QTY 1 - 8 HRS EA - GC Fence

LE-125- Skid Steer - QTY 1 - 8 HRS EA - GC Fence

Marian Bear Park, Genesee - SRK Engineering - Mandrel Fiber Optic Cable

• Jetted two  4-inch conduits between Station 396+09 and Station 390+94 to remove dirt and debris.
• Dewatered the conduits using compressed air and pumps.
• Blew a rope through, then pulled a mandrel through both conduits to prove they were clear.

Hours: 7:00 AM - 3:30 PM

Manpower:

LL-04- Operator - QTY 1 - 8 HRS EA - SRK Eng

LL-03- Laborers - QTY 3 - 8 HRS EA - SRK Eng

LL-02- Foreman - QTY 1 - 8 HRS EA - SRK Eng

Equipment:

LE-42- Utility Truck - QTY 2 - 8 HRS EA - SRK Eng

LE-04- Mini Excavator - QTY 1 - 8 HRS EA - SRK Eng

LE-81- Mechanical Wacker - QTY 1 - 8 HRS EA - SRK Eng

LE-23- Super 10 End Dump Truck - QTY 1 - 8 HRS EA - SRK Eng

Towne Centre & Marian Bear Park - OHLA - T&M and SWPPP

• The crew went to Marian Bear Park to clean up concrete for SWPPP.
• Three laborers setup traffic control at Towne Centre across from UTC to finish T&M work, cleaned up cold patch, formed a curb, and cleaned up traffic control signs
• They set up traffic control on Towne Centre to Nobel to finish draining a 48-inch pipe.
• They finished the work and picked up the traffic control at 3:00 PM

Hours: 6:30 AM - 3:00 PM

Manpower:

LL-03- Laborers - QTY 1 - 8 HRS EA - OHL NA

LL-04- Operator - QTY 1 - 4 HRS EA - OHL NA

LL-02- Foreman - QTY 1 - 9 HRS EA - OHL NA

LL-04- Operator - QTY 1 - 8 HRS EA - OHL NA

Equipment:

LE-28- Water Truck - QTY 1 - 8 HRS EA - Herc - RENTAL

LE-01- Crew Truck - QTY 1 - 4 HRS EA - OHLA

LE-23- Super 10 End Dump Truck - QTY 1 - 2 HRS EA - Herc - RENTAL

LE-01- Crew Truck - QTY 1 - 2 HRS EA - OHLA

LE-125- Skid Steer - QTY 1 - 6 HRS EA - Herc - RENTAL

LE-72- Arrow Board - QTY 1 - 8 HRS EA - OHLA

## Consolidated Resources

| Resource | Pay Type | Class | Qty | Company | Total Hours |
| --- | --- | --- | --- | --- | --- |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 4 | AR Concrete | 32 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 4 | AR Concrete | 8 |
| LL-01- Superintendent | CS - Cost | LR - Labor Regular Time | 1 | AR Concrete | 8 |
| LL-01- Superintendent | CS - Cost | LO - Labor Overtime | 1 | AR Concrete | 2 |
| LL-18- Visitor | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 1 | AR Concrete | 8 |
| LL-02- Foreman | CS - Cost | LO - Labor Overtime | 1 | AR Concrete | 2 |
| LL-15- Cement Mason | CS - Cost | LR - Labor Regular Time | 2 | AR Concrete | 16 |
| LL-15- Cement Mason | CS - Cost | LO - Labor Overtime | 2 | AR Concrete | 4 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 2 | GC Fence | 16 |
| LE-51- Pickup Truck | CS - Cost | LR - Labor Regular Time | 1 | GC Fence | 8 |
| LE-66- Concrete Mixer | CS - Cost | LR - Labor Regular Time | 1 | GC Fence | 8 |
| LE-125- Skid Steer | CS - Cost | LR - Labor Regular Time | 1 | GC Fence | 8 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | SRK Eng | 8 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 3 | SRK Eng | 24 |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 1 | SRK Eng | 8 |
| LE-42- Utility Truck | CS - Cost | LR - Labor Regular Time | 2 | SRK Eng | 16 |
| LE-04- Mini Excavator | CS - Cost | LR - Labor Regular Time | 1 | SRK Eng | 8 |
| LE-81- Mechanical Wacker | CS - Cost | LR - Labor Regular Time | 1 | SRK Eng | 8 |
| LE-23- Super 10 End Dump Truck | CS - Cost | LR - Labor Regular Time | 1 | SRK Eng | 8 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 4 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-02- Foreman | CS - Cost | LO - Labor Overtime | 1 | OHL NA | 1 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 4 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-04- Operator | EW - Extra Work | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-04- Operator | EW - Extra Work | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-04- Operator | EW - Extra Work | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 4 |
| LE-28- Water Truck | CS - Cost | LR - Labor Regular Time | 1 | Herc | 8 |
| LE-01- Crew Truck | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 4 |
| LE-23- Super 10 End Dump Truck | CS - Cost | LR - Labor Regular Time | 1 | Herc | 2 |
| LE-01- Crew Truck | EW - Extra Work | LR - Labor Regular Time | 1 | OHL NA | 2 |
| LE-125- Skid Steer | CS - Cost | LR - Labor Regular Time | 1 | Herc | 6 |
| LE-72- Arrow Board | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |