DAILY FIELD REPORT - 03-06-2026

Project: Morena Conveyance North
Resident Engineer: 
Weather: High: 72°F, Low: 45°F, Sunny, Fog
Hours: 07:00 - 15:30

## Activities Detail

Town Centre and Renaissance- OHLA - Dewatering Piplines

OHLA -crew of 1 foreman and 3 laborers start the day on town centre at blow off # 7. 
setup traffic control in the southbound #2 lane, shifting traffic into the #1 lane. 
Norcal pipeline services was on site with a vacuum truck to pull the water our of the pipeline.
- finished clearing the 48" line today
started on the 30"
Norcal pipeline will be back on monday to continue
picked up traffic contorl at 330PM and left for the day.

Hours: 7:00 AM - 3:30 PM

Manpower:

LL-02- Foreman - QTY 1 - 8 HRS EA - OHL NA

LL-03- Laborers - QTY 3 - 8 HRS EA - OHL NA

Equipment:

LE-111- Trailer Mounted Blower - QTY 1 - 8 HRS EA - OHL NA

LE-51- Pickup Truck - QTY 1 - 8 HRS EA - OHL NA

Marian Bear Park - OHLA - Valve boxes, Concrete Pads, Park Restoration

1 foreman, 3 laborers and an operator worked at marian bear park.
first thing in the moring a welder from deans welding, welded the valve box frame to the valve can. 
exavated around the two valve cans without a pad around them as well as the camlock connection.
they grouted the top section of the camlock connection manhole to the base
poured the concrete pads around the valve cans 
poured the concrete pad around the camlock connection
brough more base in and filled in two low spots
wrapped up the day at 330 PM

Hours: 7:00 AM - 3:30 PM

Manpower:

LL-19- Welder - QTY 1 - 2 HRS EA - Deans Weldng

LL-03- Laborers - QTY 5 - 8 HRS EA - OHL NA

LL-04- Operator - QTY 1 - 8 HRS EA - OHL NA

LL-02- Foreman - QTY 1 - 8 HRS EA - OHL NA

Equipment:

LE-51- Pickup Truck - QTY 1 - 8 HRS EA - OHL NA

LE-32- Skytrak Forklift - QTY 1 - 8 HRS EA - Herc

LE-58- Welding Truck - QTY 1 - 2 HRS EA - Deans Weldng

## Consolidated Resources

| Resource | Pay Type | Class | Qty | Company | Total Hours |
| --- | --- | --- | --- | --- | --- |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 3 | OHL NA | 24 |
| LE-111- Trailer Mounted Blower | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LE-51- Pickup Truck | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-19- Welder | CS - Cost | LR - Labor Regular Time | 1 | Deans Weldng | 2 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 5 | OHL NA | 40 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LE-51- Pickup Truck | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LE-32- Skytrak Forklift | CS - Cost | LR - Labor Regular Time | 1 | Herc | 8 |
| LE-58- Welding Truck | CS - Cost | LR - Labor Regular Time | 1 | Deans Weldng | 2 |