DAILY FIELD REPORT - 04-14-2026

Project: Morena Conveyance North
Resident Engineer: Terry West
Weather: High: 68°F, Low: 50°F, Wind: SSE 4 mph, Partly Cloudy, Cloudy
Hours: 07:00 - 15:30

## Activities Detail

Decoro and Genesee - OHLA - Curb Ramp & Cross Gutter Demolition and Forming

• Subcontractor AR Concrete implemented traffic control for the work area. OHL's traffic control crew later supplemented the setup with additional signs to comply with the approved traffic control plan.
• Placed concrete for the new curb ramp and cross gutter at the southwest corner of the intersection. The pour began at 11:45 AM and was completed at approximately 4:00 PM.
• Following placement, protective cones were installed around the new concrete in the Eastbound right-hand turn lane.
• Base paving for the adjacent areas was postponed to the following day due to the late completion of the concrete pour.

Hours: 11:30 AM - 4:00 PM

Manpower:

LL-15- Cement Mason - QTY 2 - 4.5 HRS EA - AR Concrete

LL-03- Laborers - QTY 3 - 4.5 HRS EA - AR Concrete

LL-01- Superintendent - QTY 1 - 4.5 HRS EA - AR Concrete

LL-02- Foreman - QTY 1 - 4.5 HRS EA - AR Concrete

Equipment:

LE-42- Utility Truck - QTY 1 - 4.5 HRS EA - AR Concrete

LE-125- Skid Steer - QTY 1 - 4.5 HRS EA - AR Concrete

LE-51- Pickup Truck - QTY 1 - 4.5 HRS EA - AR Concrete

LE-23- Super 10 End Dump Truck - QTY 1 - 4.5 HRS EA - AR Concrete

LE-83- Equipment-Hauling Trailer - QTY 1 - 4.5 HRS EA - AR Concrete

LE-01- Crew Truck - QTY 1 - 4.5 HRS EA - AR Concrete

Executive - Picket Fences - Median Landscaping

• OHLA set up a traffic control closure in the #1 lane for both eastbound and westbound traffic, shifting vehicles to the #2 lane.
• Picket Fences excavated down on the South side of executive to find the other end of the sleeves, found them stubbed out at 3.5 ft down.
• Tried to insert a new pvc pipe into the sleeve however, they got stuck about 5' before the south edge of the street. 
• They continued backfilling the laterals and installing sprinkler valves and one more valve box
• "Reclaimed Water" warning tape was placed above the pipe before backfilling to grade and compacting.
• Picket Fences wrapped up for the day and was gone at 3:30 p.m.
• OHLA picked up traffic control at 3:45 PM

Hours: 7:00 AM - 3:30 PM

Manpower:

LL-03- Laborers - QTY 1 - 8 HRS EA - Pickette Fences

LL-02- Foreman - QTY 1 - 8 HRS EA - Pickette Fences

Equipment:

LE-70- Generator - QTY 1 - 8 HRS EA - Pickette Fences

LE-51- Pickup Truck - QTY 2 - 8 HRS EA - Pickette Fences

Marian Bear Park - Western Gardens - Irrigation System Installation

• Western Gardens continued installation of the new irrigation system at Marian Bear Park. 
• They finished installing all piping and installed the risers at both hydroseed locations.
• The remaining work consists of installing the sprinkler heads and connecting the system to the water source.

Hours: 8:00 AM - 2:00 PM

Manpower:

LL-01- Superintendent - QTY 1 - 6 HRS EA - Western Gardens Landscape Inc.

Equipment:

LE-51- Pickup Truck - QTY 0 - 0 HRS EA - Western Gardens Landscape Inc.

Rose Canyon, Genesee, Executive, Water Reclamation Plant

• Setup Picket Fences traffic control on Executive
• Performed job site BMP maintenance.
• Excavated trench and set trench boxes for the installation of 4-inch pipe at blowoff #9.
• Setup a 2nd traffic control for Picket Fences on Genesee
• Completed fit-up and welding on cut-in manways for the 30-inch and 42-inch connection pieces at Rose Canyon.
• filling 48" and pressurizing and bleeding air on 30" for phase 4 piping pre-hydrostatic testing
• Removed traffic control for Picket Fences

Hours: 6:00 AM - 5:30 PM

Manpower:

LL-03- Laborers - QTY 1 - 12 HRS EA - OHLA

LL-03- Laborers - QTY 1 - 9 HRS EA - OHLA

LL-03- Laborers - QTY 1 - 8.5 HRS EA - OHLA

LL-02- Foreman - QTY 1 - 11.5 HRS EA - OHLA

LL-03- Laborers - QTY 1 - 8 HRS EA - OHLA

LL-03- Laborers - QTY 1 - 11 HRS EA - OHLA

LL-04- Operator - QTY 1 - 9 HRS EA - OHLA

LL-04- Operator - QTY 1 - 10 HRS EA - OHLA

LL-11- Teamster - QTY 1 - 8 HRS EA - OHLA

Equipment:

LE-32- Skytrak Forklift - QTY 1 - 8 HRS EA - Herc - RENTAL

LE-01- Crew Truck - QTY 1 - 8 HRS EA - A.A. Trucking

LE-51- Pickup Truck - QTY 1 - 8 HRS EA - OHLA

LE-09- Skip Loader - QTY 1 - 8 HRS EA - Herc - RENTAL

LE-28- Water Truck - QTY 1 - 8 HRS EA - Herc - RENTAL

LE-109- Excavator - QTY 1 - 8 HRS EA - Trinity - RENTAL

## Consolidated Resources

| Resource | Pay Type | Class | Qty | Company | Total Hours |
| --- | --- | --- | --- | --- | --- |
| LL-15- Cement Mason | CS - Cost | LR - Labor Regular Time | 2 | AR Concrete | 9 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 3 | AR Concrete | 13.5 |
| LL-01- Superintendent | CS - Cost | LR - Labor Regular Time | 1 | AR Concrete | 4.5 |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 1 | AR Concrete | 4.5 |
| LE-42- Utility Truck | CS - Cost | LR - Labor Regular Time | 1 | AR Concrete | 4.5 |
| LE-125- Skid Steer | CS - Cost | LR - Labor Regular Time | 1 | AR Concrete | 4.5 |
| LE-51- Pickup Truck | CS - Cost | LR - Labor Regular Time | 1 | AR Concrete | 4.5 |
| LE-23- Super 10 End Dump Truck | CS - Cost | LR - Labor Regular Time | 1 | AR Concrete | 4.5 |
| LE-83- Equipment-Hauling Trailer | CS - Cost | LR - Labor Regular Time | 1 | AR Concrete | 4.5 |
| LE-01- Crew Truck | CS - Cost | LR - Labor Regular Time | 1 | AR Concrete | 4.5 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | Pickette Fences | 8 |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 1 | Pickette Fences | 8 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | Pickette Fences | 8 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | Pickette Fences | 8 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | Pickette Fences | 8 |
| LE-70- Generator | CS - Cost | LR - Labor Regular Time | 1 | Pickette Fences | 8 |
| LE-51- Pickup Truck | CS - Cost | LR - Labor Regular Time | 2 | Pickette Fences | 16 |
| LL-01- Superintendent | CS - Cost | LR - Labor Regular Time | 1 | Western Gardens Landscape Inc. | 6 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 1 | OHL NA | 4 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 1 | OHL NA | 1 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 1 | OHL NA | 4 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 1 | OHL NA | 0.5 |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-02- Foreman | CS - Cost | LO - Labor Overtime | 1 | OHL NA | 3.5 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 1 | OHL NA | 3 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 1 | OHL NA | 1 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 1 | OHL NA | 3 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 1 | OHL NA | 2 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 1 | OHL NA | 3 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 1 | OHL NA | 3 |
| LL-11- Teamster | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LE-32- Skytrak Forklift | CS - Cost | LR - Labor Regular Time | 1 | Herc | 8 |
| LE-01- Crew Truck | CS - Cost | LR - Labor Regular Time | 1 | A.A. Trucking | 8 |
| LE-51- Pickup Truck | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LE-09- Skip Loader | CS - Cost | LR - Labor Regular Time | 1 | Herc | 8 |
| LE-28- Water Truck | CS - Cost | LR - Labor Regular Time | 1 | Herc | 8 |
| LE-51- Pickup Truck | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LE-109- Excavator | CS - Cost | LR - Labor Regular Time | 1 | Trinity | 8 |