DAILY FIELD REPORT - 04-16-2026

Project: Morena Conveyance North
Location: Executive, Genesee, Marian Bear Park, water reclamation plant
Resident Engineer: Terry West
Weather: High: 76°F, Low: 50°F, Wind: SSE 7 mph, Sunny
Hours: 07:00 - 15:30

General Notes:

OHL was working at the water reclamation plant excavating for the 4" drain line, at executive on the hydro test, and at Marian Bear Park on the concrete slabs around the cathodic test station boxes along the fence. Picket Fences is started at Executive looking at the connection to the irrigation system, then moved over to Genesee withthe whole crew to continue grading. Found the water line that was previously feeding the median irrigaiton; it had been capped about 25 feet away from the south side of the road. They are opting to install a new line through the sleeve. Water will be fed from the meter box to the immediate east at 556+48

## Activities Detail

Executive & Genesee - Picket Fences - Locating Main Line & Cleanup

• picket fences began the day briefly at executive to discussa plan to connect the water line. 

They want to run a new line over to the median through the existing sleeve.

The plan is to open up the street right next to the sidewalk and get to the sleeve and cleear the blockage. then run a new line to the median. they will connect to the meter box at 556+48 just outside the sidewalk along the south edge of the road for the water source.

After about 930 am the whole crew moved to Genesee to contnue grading and clearing out debris.

Hours: 7:00 AM - 3:30 PM

Manpower:

LL-02- Foreman - QTY 1 - 8 HRS EA - Pickette Fences

LL-03- Laborers - QTY 1 - 8 HRS EA - Pickette Fences

Equipment:

LE-69- Jackhammer - QTY 1 - 8 HRS EA - Pickette Fences

Inspection Camera - QTY 1 - 8 HRS EA - Pickette Fences

Blowoff #9, Executive, Marian Bear Park - OHLA - Hydrostatic Testing & Excavation

• Excavated at Blowoff #9 for a 4-inch drain line to locate a 4-inch PVC stub-out from the sewer manhole. The excavation stopped before locating the 4" line, as a pump was not delivered with the shoring.
• Pressurized the 30-inch pipeline in Phase 4 to 230 psi for a hydrostatic pre-test, and bleed the system at AV # 13.
• Performed site-wide Best Management Practices (BMP) maintenance.
• Demolished two (2) concrete pads at Marian Bear Park.
• Raised existing cathodic protection (CP) test station boxes and poured new concrete pads at Marian Bear Park.

Hours: 6:00 AM - 7:00 PM

Manpower:

LL-02- Foreman - QTY 1 - 9.5 HRS EA - OHLA

LL-03- Laborers - QTY 1 - 11.5 HRS EA - OHLA

LL-03- Laborers - QTY 1 - 9 HRS EA - OHLA

LL-03- Laborers - QTY 1 - 12.5 HRS EA - OHLA

LL-04- Operator - QTY 1 - 8 HRS EA - OHLA

LL-04- Operator - QTY 1 - 12.5 HRS EA - OHLA

LL-04- Operator - QTY 1 - 8.5 HRS EA - OHLA

LL-03- Laborers - QTY 1 - 9.5 HRS EA - OHLA

Equipment:

LE-51- Pickup Truck - QTY 1 - 8 HRS EA - OHLA

LE-109- Excavator - QTY 1 - 6 HRS EA - Herc Rentals

## Consolidated Resources

| Resource | Pay Type | Class | Qty | Company | Total Hours |
| --- | --- | --- | --- | --- | --- |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 1 | Pickette Fences | 8 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | Pickette Fences | 8 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | Pickette Fences | 8 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | Pickette Fences | 8 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | Pickette Fences | 8 |
| LE-69- Jackhammer | CS - Cost | LR - Labor Regular Time | 1 | Pickette Fences | 8 |
| LL-09- PE | CS - Cost | LR - Labor Regular Time | 1 | Pickette Fences | 8 |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-02- Foreman | CS - Cost | LO - Labor Overtime | 1 | OHL NA | 1.5 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 1 | OHL NA | 3.5 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 1 | OHL NA | 3.5 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 1 | OHL NA | 1 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 1 | OHL NA | 4.5 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 1 | OHL NA | 4.5 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 1 | OHL NA | 4.5 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 1 | OHL NA | 0.5 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 1 | OHL NA | 4.5 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 1 | OHL NA | 1.5 |
| LE-51- Pickup Truck | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LE-51- Pickup Truck | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LE-109- Excavator | CS - Cost | LR - Labor Regular Time | 1 | Herc Rentals | 6 |