DAILY FIELD REPORT - 04-29-2026

Project: Morena Conveyance North
Location: Water reclamation plant executive Town Center Genesee Media # 6 Rose Canyon and Marian Bear Park, Rose Canyon, Executive Dr, Genesee Ave, Medeans, Marian Bear Park, Water Reclamation Plant, Town Center, OHL Yard, Governor and Genesee
Resident Engineer: Terry West
Weather: High: 77°F, Low: 46°F, Wind: ESE 2 mph, Sunny
Hours: 07:00 - 15:30

General Notes:

Water reclamation plant excavating for the 48-in to tie in the existing to the new executive excavating for water line connection was Town Center base paving for airvac number 13 Genesee Media number 6 continue grading for landscaping and forms to get ready for concrete Rose Canyon excavating the bottom of the trench to find existing concrete and Marion Bear Park grading and forms for concrete at valve boxes
OHL crews performed shaft excavation and dewatering at Rose Canyon. At Executive Drive, OHL handled excavation and backfill for a utility repair, while Pickett Fences installed new water piping and connections through a broken sleeve.
Picket Fences crews performed grading at Genesee Avenue and repaired a water line sleeve on Executive Drive. OHL crews conducted final grading and formwork at Marian Bear Park, performed deep excavation at the Water Reclamation Plant to expose a 42-inch pipe, and completed sidewalk demolition and form setting at the south end of Genesee Avenue.
SRK crews performed base paving at Airvac #13 in Town Center, working in two separate traffic control phases to complete the trench restoration. After finishing the paving, the crew visited a future work site at Governor and Genesee before demobilizing.

## Activities Detail

Rose Canyon - OHL - Shaft Excavation

• Crew started work at 6:30 AM.
• Excavated in the shaft down to the bottom of the encasement using a mini excavator.
• A crane with a shaft kibble was used to remove excavated soil.
• Excavated down approximately 5 ft and located the top of the concrete.
• Groundwater was continuously pumped from the excavation throughout the day.
• Crew finished work at 5:30 PM.

Hours: 6:30 AM - 5:30 PM

Manpower:

LL-04- Operator - QTY 2 - 10.5 HRS EA - OHL

LL-03- Laborers - QTY 4 - 10.5 HRS EA - OHL

Equipment:

LE-125- Skid Steer - QTY 1 - 10.5 HRS EA - OHL

LE-32- Skytrak Forklift - QTY 1 - 10.5 HRS EA - OHL

LE-114- Crane - QTY 1 - 10.5 HRS EA - OHL

LE-04- Mini Excavator - QTY 1 - 10.5 HRS EA - OHL

Genesee Ave & Executive Dr - Picket Fences - Grading, Concrete Prep & Water Connection

• Performed grading at Genesee Ave.
• Made a water connection at Executive Dr.
• Hired additional laborers to perform concrete work at Medeans.
• Laid out forms for concrete at Medeans but did not have exact coordinates for the curb tie-in, so forms were placed in the general location.
• Had questions regarding the concrete mix design and were referred to OHL.
• Expected a survey crew on site, but the request was not followed through by OHL.
• At Executive Dr, repaired a broken sleeve for a 3-inch water line.
• Cleared dirt from inside the sleeve and ran the 3-inch pipe through.
• Cut in a tee on the water line after the meter box.
• The new line ran to another box installed to the west of the meter box, then dropped down to connect to the new sleeve.
• At Genesee Ave, the crew continued grading and compacting areas in preparation for concrete.
• The crew picked up traffic control and left the site at 3:30 PM.

Manpower:

LL-02- Foreman - QTY 1 - 8 HRS EA - Picket Fences

LL-03- Laborers - QTY 5 - 8 HRS EA - Picket Fences

Marian Bear Park - OHL - Final Grading & Formwork

• An OHLA crew performed final grading in the park.
• Graded base for final grade.
• A second crew set forms for valve boxes above the vault in preparation for a concrete pour.

Hours: 7:00 AM - 3:30 PM

Manpower:

LL-03- Laborers - QTY 2 - 8 HRS EA - OHL

LL-02- Foreman - QTY 1 - 8 HRS EA - OHL

LL-02- Foreman - QTY 1 - 2 HRS EA - OHL

LL-04- Operator - QTY 1 - 8 HRS EA - OHL

Equipment:

LE-51- Pickup Truck - QTY 2 - 8 HRS EA - OHL

LE-125- Skid Steer - QTY 1 - 8 HRS EA - OHL

Water Reclamation Plant - OHL - Deep Excavation

• Crew started at 6:30 AM and cleared the work area.
• Used a vac truck to locate the top of the 42-inch pipe previously installed by Kiewit.
• Set trench boxes and began mass excavation with the 330 excavator.
• As excavation progressed, laborers entered the trench to perform hand excavation around the pipe.
• The shoring box and shields were readjusted as the excavation deepened to approximately 12-13 feet.
• Crew continued hand excavation, moving to an adjacent shoring box and loading spoil into the excavator bucket.
• The site was secured and the crew left at 7:00 PM.

Hours: 6:30 AM - 7:00 PM

Manpower:

LL-02- Foreman - QTY 1 - 12.5 HRS EA - OHL

LL-03- Laborers - QTY 4 - 12.5 HRS EA - OHL

LL-04- Operator - QTY 1 - 12.5 HRS EA - OHL

Equipment:

LE-01- Crew Truck - QTY 1 - 12.5 HRS EA - OHL

LE-40- Badger Vac Truck - QTY 1 - 0 HRS EA - OHL

LE-109- Excavator - QTY 1 - 12.5 HRS EA - OHL

LE-125- Skid Steer - QTY 1 - 12.5 HRS EA - OHL

South End of Genesee Ave - OHL - Sidewalk Demolition & Formwork

• Set up traffic control on the shoulder and in half of the #2 lane, beginning at 10:00 AM.
• The right-hand turn lane remained open.
• Demolished two sidewalk panels that had been filled with cold mix.
• Removed the cold mix and set forms for the new sidewalk pour.
• Picked up traffic control at 1:00 PM.
• After this work, the crew mobilized to check on Airvacs in preparation for upcoming concrete pours.

Hours: 10:00 AM - 1:00 PM

Manpower:

LL-02- Foreman - QTY 1 - 3 HRS EA - OHL

Town Center & Governor/Genesee - SRK - Base Paving and Site Visit

• Set up traffic control at Town Center for work at Airvac #13 on the southbound side, starting in the number 1 lane and shifting traffic to the number 2 lane.
• In the number 1 lane, the crew removed the existing cold mix from the trench.
• Placed and compacted a first lift of hot mix asphalt.
• Placed and compacted a second lift of hot mix asphalt using a roller.
• After allowing the asphalt to cool, traffic control was shifted to perform work in the number 2 lane.
• In the number 2 lane, the crew removed the existing cold mix patch.
• Placed and compacted two lifts of hot mix asphalt.
• A dump truck hauled the old cold mix to the OHL yard for disposal.
• At approximately 1:30 PM, the crew picked up traffic control.
• Crew drove to the intersection of Governor and Genesee to inspect a trench for future paving work before demobilizing.

Hours: 7:00 AM - 3:30 PM

Manpower:

LL-02- Foreman - QTY 1 - 8 HRS EA - SRK

LL-04- Operator - QTY 1 - 8 HRS EA - SRK

LL-03- Laborers - QTY 2 - 8 HRS EA - SRK

Equipment:

LE-23- Super 10 End Dump Truck - QTY 1 - 8 HRS EA - SRK

LE-04- Mini Excavator - QTY 1 - 8 HRS EA - SRK

LE-42- Utility Truck - QTY 1 - 8 HRS EA - SRK

LE-159- Roller - QTY 1 - 8 HRS EA - SRK

## Consolidated Resources

| Resource | Pay Type | Class | Qty | Company | Total Hours |
| --- | --- | --- | --- | --- | --- |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 2 | OHL | 16 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 2 | OHL | 5 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 4 | OHL | 32 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 4 | OHL | 10 |
| LE-125- Skid Steer | CS - Cost | LR - Labor Regular Time | 1 | OHL | 10.5 |
| LE-32- Skytrak Forklift | CS - Cost | LR - Labor Regular Time | 1 | OHL | 10.5 |
| LE-114- Crane | CS - Cost | LR - Labor Regular Time | 1 | OHL | 10.5 |
| LE-04- Mini Excavator | CS - Cost | LR - Labor Regular Time | 1 | OHL | 10.5 |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 1 | Picket Fences | 8 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 5 | Picket Fences | 40 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 2 | OHL | 16 |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 1 | OHL | 8 |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 1 | OHL | 2 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | OHL | 8 |
| LE-51- Pickup Truck | CS - Cost | LR - Labor Regular Time | 2 | OHL | 16 |
| LE-125- Skid Steer | CS - Cost | LR - Labor Regular Time | 1 | OHL | 8 |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 1 | OHL | 8 |
| LL-02- Foreman | CS - Cost | LO - Labor Overtime | 1 | OHL | 4.5 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 4 | OHL | 32 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 4 | OHL | 18 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | OHL | 8 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 1 | OHL | 4.5 |
| LE-01- Crew Truck | CS - Cost | LR - Labor Regular Time | 1 | OHL | 12.5 |
| LE-109- Excavator | CS - Cost | LR - Labor Regular Time | 1 | OHL | 12.5 |
| LE-125- Skid Steer | CS - Cost | LR - Labor Regular Time | 1 | OHL | 12.5 |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 1 | OHL | 3 |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 1 | SRK | 8 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | SRK | 8 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 2 | SRK | 16 |
| LE-23- Super 10 End Dump Truck | CS - Cost | LR - Labor Regular Time | 1 | SRK | 8 |
| LE-04- Mini Excavator | CS - Cost | LR - Labor Regular Time | 1 | SRK | 8 |
| LE-42- Utility Truck | CS - Cost | LR - Labor Regular Time | 1 | SRK | 8 |
| LE-159- Roller | CS - Cost | LR - Labor Regular Time | 1 | SRK | 8 |