DAILY FIELD REPORT - 04-09-2026

Project: Morena Conveyance North
Resident Engineer: Terry West
Weather: High: 81°F, Low: 54°F, Wind: ESE 4 mph, Partly Cloudy, Cloudy
Hours: 07:00 - 15:30

## Activities Detail

Executive Median - Picket Fences - Median Landscape
•   Continued trench excavation along the south side of the median.
•   Installed irrigation piping and stub-ups along both the north and south sides of the median.
•   Completed the irrigation pipe installation and backfilled the trench along the north side of the median.
•   Performed exploratory excavation to locate the water main connection at the west end of the median.
•   Located the existing water main connection at STA 556+45 at the very end of the day
•   The trench along the south side of the median was still open as the pipe installation had not been completed
•   Removed temporary traffic control and secured the work area with caution tape.

Hours: 6:00 AM - 6:00 PM

Manpower:

LL-02- Foreman - QTY 1 - 10.5 HRS EA - Pickette Fences

LL-03- Laborers - QTY 1 - 11.5 HRS EA - OHL NA

LL-04- Operator - QTY 1 - 11.5 HRS EA - OHL NA

Equipment:

LE-51- Pickup Truck - QTY 1 - 10.5 HRS EA - Pickette Fences

LE-125- Skid Steer - QTY 1 - 11.5 HRS EA - OHL NA

Marian Bear Park - Western Gardens Landscaping - Irrigation Installation

• Western Gardens Landscaping started at Marian Bear Park today at 7:00 am
•Llaid out above-ground irrigation piping for the hydroseed area.
• Laid and connected all piping in the area south of the driveway.
• Laid out all piping in the area north of the driveway and connected approximately 70% of it.
• Ended the day at 1:30 PM

Hours: 7:00 AM - 1:30 PM

Manpower:

LL-03- Laborers - QTY 1 - 6 HRS EA - Western Gardens Landscape Inc.

Equipment:

LE-51- Pickup Truck - QTY 1 - 2 HRS EA - Western Gardens Landscape Inc.

Executive, Town Centre, Water Reclamation Plant - OHLA - BO # 9, & Hydro Test

- First thing in the morning, turned on the pump at Executive Dr. to continue pressurizing the Phase 4, 30-inch line for the hydro pre-test.

- Crew then mobilized to Blow-off #9 and installed 6 valves: 2 on each drain line, and 1 on each of the reducing flanges on the vertical pipe..

- At approximately 3:45 PM, the crew relocated back to Executive Dr. after being notified the line wouldn't build past 120 PSI.

- Walked the line to track down the pressure loss, starting at the manway west of the dish head and checking every blind flange and valve downstream down to AR # 13.

- Bled trapped air at Air Release #14 for about 5 minutes before the air flow finally stopped by opening a ball valve on a blind flange.

- Bled additional air at Air Release #13 by cracking a ball valve on the blind flange here. Additionally, found the plug valves installed were not installed to per plan.

- The 4-inch plug valves at Air Release #13 were the wrong configuration, were installed at the incorrect orientation, and installed with one against the flow. These must be swapped out before re-pressurizing the line.

Hours: 6:00 AM - 6:00 PM

Manpower:

LL-10- GF - QTY 1 - 11.5 HRS EA - OHL NA

LL-03- Laborers - QTY 3 - 11.5 HRS EA - OHL NA

LL-03- Laborers - QTY 2 - 11.5 HRS EA - OHL NA

Equipment:

LE-51- Pickup Truck - QTY 1 - 11.5 HRS EA - OHL NA

LE-109- Excavator - QTY 1 - 11.5 HRS EA - OHL NA

LE-42- Utility Truck - QTY 1 - 11.5 HRS EA - OHL NA

## Consolidated Resources

| Resource | Pay Type | Class | Qty | Company | Total Hours |
| --- | --- | --- | --- | --- | --- |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 1 | Pickette Fences | 8 |
| LL-02- Foreman | CS - Cost | LO - Labor Overtime | 1 | Pickette Fences | 2.5 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 1 | OHL NA | 3.5 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 1 | OHL NA | 3.5 |
| LE-51- Pickup Truck | CS - Cost | LR - Labor Regular Time | 1 | Pickette Fences | 10.5 |
| LE-125- Skid Steer | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 11.5 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | Western Gardens Landscape Inc. | 6 |
| LE-51- Pickup Truck | CS - Cost | LR - Labor Regular Time | 1 | Western Gardens Landscape Inc. | 2 |
| LL-10- GF | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-10- GF | CS - Cost | LO - Labor Overtime | 1 | OHL NA | 3.5 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 3 | OHL NA | 24 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 3 | OHL NA | 10.5 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 2 | OHL NA | 16 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 2 | OHL NA | 7 |
| LE-51- Pickup Truck | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 11.5 |
| LE-51- Pickup Truck | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 11.5 |
| LE-109- Excavator | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 11.5 |
| LE-42- Utility Truck | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 11.5 |