DAILY FIELD REPORT - 05-02-2026

Project: Morena Conveyance North
Location: Marian Bear Park, Water Reclamation Plant
Resident Engineer: Terry West
Weather: 
Hours: 07:00 - 15:30

General Notes:

OHL had two crews working on Saturday. One crew was at Marian Bear Park performing fine grading and installing a Camlock fitting in a vault. The second crew worked at the Water Reclamation Plant, backfilling a previous excavation and excavating to uncover an existing 30-inch pipe. Both crews worked 8-hour shifts.

## Activities Detail

Marian Bear Park - OHL - Grading and Vault Work

• Operator performed fine grading at the start of the day.
• The crew started work on the Camlock port connection.
• The vault was cleaned up.
• The flange was installed for the Camlock fitting to attach to.
• Crew entered the vault to start on final work items.

I went with two OHL laborers that were there and showed them what work was remaining to keep all in the loop on what’s needed. Brandon was not on site to show but will be walking it with him Monday and sending an email out over the weekend.

Hours: 6:30 AM - 3:00 PM

Manpower:

LL-03- Laborers - QTY 3 - 8 HRS EA - OHL NA

LL-04- Operator - QTY 1 - 4 HRS EA - OHL NA

Equipment:

LE-125- Skid Steer - QTY 1 - 8 HRS EA - OHL NA

LE-70- Generator - QTY 1 - 8 HRS EA - OHL NA

LE-28- Water Truck - QTY 1 - 8 HRS EA - OHL NA

LE-51- Pickup Truck - QTY 1 - 8 HRS EA - OHL NA

Water Reclamation Plant - OHL - Excavation and Backfill

• NorCal pipeline on site with the vac truck again. Continued exploration, searched for and located the the end of the 42” installed by OHLA and the 20” for the bypass. Wrapped up around 1:00 PM and started rolling up the truck 
• OHLA laborers and operator spent the day excavating for the tie in to the 30” installed by Kiewit. Went home at 3:00 PM

Hours: 7:00 AM - 3:00 PM

Manpower:

LL-03- Laborers - QTY 2 - 8 HRS EA - OHL

LL-02- Foreman - QTY 1 - 8 HRS EA - OHL

LL-04- Operator - QTY 1 - 8 HRS EA – OHL

LL-16- Vac Truck Operator - QTY 1 - 6 HRS EA – NorCal Pipline

Equipment:

LE-01- Crew Truck - QTY 1 - 8 HRS EA - OHL

LE-109- Excavator - QTY 1 - 8 HRS EA – OHL

LE- 82- Vactor Truck - QTY 1 - 6 HRS EA – NorCal Pipline

## Consolidated Resources

| Resource | Pay Type | Class | Qty | Company | Total Hours |
| --- | --- | --- | --- | --- | --- |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 3 | OHL NA | 24 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LE-125- Skid Steer | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LE-70- Generator | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LE-28- Water Truck | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LE-51- Pickup Truck | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 2 | OHL | 16 |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 1 | OHL | 8 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | OHL | 8 |
| LE-01- Crew Truck | CS - Cost | LR - Labor Regular Time | 1 | OHL | 8 |
| LE-109- Excavator | CS - Cost | LR - Labor Regular Time | 1 | OHL | 8 |