DAILY FIELD REPORT - 06-09-2026

Project: Morena Conveyance Northern
Location: Genesee @ SR-52/Marian Bear Park
Resident Engineer: Terry West
Weather: High: 74°F, Low: 59°F, Wind: 1 mph NNE, Partly Cloudy, Clear, Overcast
Hours: 20:00 - 06:00

## Activities Detail

RJ Noble – Dig Outs - GENESSEE AVE / GOVERNOR DR - UTC

• Digout Schedule — Tuesday, June 9, 2026:

- DO #Governor NB outside — 0.5' depth  = 3,197 SF (119.89 tons)

- DO #Governor SB outside — 0.5' depth = 2,462 SF (92.325 tons)

- DO #37 NB#2 — 1' depth × 12W × 135L = 1,620 SF (121.5 tons)

- DO #39 NB#2 — 1' depth × 7W × 68L = 476 SF (35.7 tons)

- DO #? NB#2 — 1' depth × 236W × 14L = 3,304 SF (247.8 tons)

Total: 11,059 SF / 617.215 Tons

• Material: 620 TN 3/4" HMA

• Plant: MM MIRAMAR

Hours: 7:00 PM - 6:00 AM

Manpower:

LL-02- Foreman - QTY 1 - 10.5 HRS EA - RJ NOBLE - SOUTH

LL-04- Operator - QTY 1 - 10.5 HRS EA - RJ NOBLE - SOUTH

LL-03- Laborers - QTY 1 - 10.5 HRS EA - RJ NOBLE - SOUTH

LL-04- Operator - QTY 1 - 9.5 HRS EA - DIII

LL-03- Laborers - QTY 1 - 11 HRS EA - RJ NOBLE - SOUTH

LL-04- Operator - QTY 13 - 10 HRS EA - DIII

LL-04- Operator - QTY 1 - 10 HRS EA - PRSI

LL-03- Laborers - QTY 1 - 10.5 HRS EA - HUDSON

Equipment:

LE-83- Equipment-Hauling Trailer - QTY 1 - 10.5 HRS EA - RJ NOBLE - SOUTH

LE-100- Liebherr LB20 Drill Rig - QTY 1 - 10.5 HRS EA - RJ NOBLE - SOUTH

LE-13- Roller H222 - QTY 1 - 10.5 HRS EA - RJ NOBLE - SOUTH

LE-09- Skip Loader - QTY 1 - 10.5 HRS EA - RJ NOBLE - SOUTH

LE-125- Skid Steer - QTY 1 - 10.5 HRS EA - RJ NOBLE - SOUTH

LE-63- Asphalt Paver - QTY 1 - 10.5 HRS EA - RJ NOBLE - SOUTH

LE-51- Pickup Truck - QTY 1 - 10.5 HRS EA - RJ NOBLE - SOUTH

LE-01- Crew Truck - QTY 1 - 10.5 HRS EA - RJ NOBLE - SOUTH

LE-141- End Dump - QTY 1 - 9.5 HRS EA - DIII

LE-42- Utility Truck - QTY 1 - 10.5 HRS EA - RJ NOBLE - SOUTH

LE-19- Street sweeper - QTY 1 - 10.5 HRS EA - RJ NOBLE - SOUTH

LE-141- End Dump - QTY 13 - 10 HRS EA - DIII

LE-71- Pavement Grinder - QTY 1 - 10 HRS EA - PRSI

LE-28- Water Truck - QTY 1 - 10.5 HRS EA - RJ NOBLE - SOUTH - RENTAL

Extra Work Manpower:

LL-03- Laborers - QTY 1 - 10.5 HRS EA - RJ NOBLE - SOUTH

Extra Work Equipment:

LE-01- Crew Truck - QTY 1 - 10.5 HRS EA - RJ NOBLE - SOUTH

## Consolidated Resources

| Resource | Pay Type | Class | Qty | Company | Total Hours |
| --- | --- | --- | --- | --- | --- |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 8 |
| LL-02- Foreman | CS - Cost | LO - Labor Overtime | 1 | RJ NOBLE - SOUTH | 2.5 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 8 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 1 | RJ NOBLE - SOUTH | 2.5 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 8 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 1 | RJ NOBLE - SOUTH | 2.5 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 8 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 1 | RJ NOBLE - SOUTH | 2.5 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 8 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 1 | RJ NOBLE - SOUTH | 2.5 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 8 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 1 | RJ NOBLE - SOUTH | 2.5 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 8 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 1 | RJ NOBLE - SOUTH | 2.5 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 8 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 1 | RJ NOBLE - SOUTH | 2.5 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 8 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 1 | RJ NOBLE - SOUTH | 2.5 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 8 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 1 | RJ NOBLE - SOUTH | 2.5 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 8 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 1 | RJ NOBLE - SOUTH | 2.5 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 8 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 1 | RJ NOBLE - SOUTH | 2.5 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | DIII | 8 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 1 | DIII | 1.5 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 8 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 1 | RJ NOBLE - SOUTH | 2.5 |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 8 |
| LL-02- Foreman | CS - Cost | LO - Labor Overtime | 1 | RJ NOBLE - SOUTH | 2.5 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 8 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 1 | RJ NOBLE - SOUTH | 2.5 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 8 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 1 | RJ NOBLE - SOUTH | 2.5 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 8 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 1 | RJ NOBLE - SOUTH | 2.5 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 8 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 1 | RJ NOBLE - SOUTH | 2.5 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 8 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 1 | RJ NOBLE - SOUTH | 3 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 8 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 1 | RJ NOBLE - SOUTH | 3 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 13 | DIII | 104 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 13 | DIII | 26 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | PRSI | 8 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 1 | PRSI | 2 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | HUDSON | 8 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 1 | HUDSON | 2.5 |
| LE-83- Equipment-Hauling Trailer | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 10.5 |
| LE-100- Liebherr LB20 Drill Rig | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 10.5 |
| LE-13- Roller H222 | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 10.5 |
| LE-09- Skip Loader | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 10.5 |
| LE-125- Skid Steer | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 10.5 |
| LE-13- Roller H222 | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 10.5 |
| LE-63- Asphalt Paver | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 10.5 |
| LE-13- Roller H222 | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 10.5 |
| LE-63- Asphalt Paver | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 10.5 |
| LE-13- Roller H222 | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 10.5 |
| LE-51- Pickup Truck | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 10.5 |
| LE-51- Pickup Truck | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 10.5 |
| LE-01- Crew Truck | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 10.5 |
| LE-141- End Dump | CS - Cost | LR - Labor Regular Time | 1 | DIII | 9.5 |
| LE-42- Utility Truck | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 10.5 |
| LE-19- Street sweeper | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 10.5 |
| LE-42- Utility Truck | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 10.5 |
| LE-19- Street sweeper | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 10.5 |
| LE-51- Pickup Truck | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 10.5 |
| LE-51- Pickup Truck | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 10.5 |
| LE-141- End Dump | CS - Cost | LR - Labor Regular Time | 13 | DIII | 130 |
| LE-71- Pavement Grinder | CS - Cost | LR - Labor Regular Time | 1 | PRSI | 10 |
| LE-28- Water Truck | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 10.5 |
| LL-03- Laborers | EW - Extra Work | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 8 |
| LL-03- Laborers | EW - Extra Work | LO - Labor Overtime | 1 | RJ NOBLE - SOUTH | 2.5 |
| LL-03- Laborers | EW - Extra Work | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 8 |
| LL-03- Laborers | EW - Extra Work | LO - Labor Overtime | 1 | RJ NOBLE - SOUTH | 2.5 |
| LE-01- Crew Truck | EW - Extra Work | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 10.5 |