DAILY FIELD REPORT - 06-14-2026

Project: Morena Conveyance Northern
Resident Engineer: Terry West
Weather: High: 96°F, Low: 66°F, Wind: 12 mph NW, Clear
Hours: 19:30 - 03:30

## Activities Detail

Genesee / Centurion - RJ Noble - Dig Outs — GENESEE AVE / CENTURION SQ. - UTC

• Crews performed asphalt concrete (AC) digouts in the southbound #2 lane, including Digouts #27 (130 SF), #28 (320 SF), #29 (2,310 SF), and #30 (2,085 SF), all excavated to a depth of 1 foot.

• An additional 1,551 SF digout was completed to a depth of 0.5 feet in the southbound outside lane at the Centurion Intersection.

• Total AC excavation for the shift amounted to 6,396 SF, yielding 422 tons of material.

• Following the digouts, the crew placed 420 tons of 3/4-inch HMA, which was supplied by the MM Miramar plant.

Hours: 7:30 PM - 3:30 AM

Manpower:

LL-02- Foreman - QTY 1 - 8 HRS EA - RJ NOBLE

LL-04- Operator - QTY 1 - 8 HRS EA - RJ NOBLE

LL-03- Laborers - QTY 1 - 8 HRS EA - RJ NOBLE

LL-04- Operator - QTY 1 - 7 HRS EA - DIII

LL-04- Operator - QTY 1 - 8 HRS EA - DIII

LL-04- Operator - QTY 1 - 8 HRS EA - PRSI

LL-03- Laborers - QTY 1 - 8 HRS EA - HUDSON

Equipment:

LE-83- Equipment-Hauling Trailer - QTY 1 - 8 HRS EA - RJ NOBLE

LE-100- Liebherr LB20 Drill Rig - QTY 1 - 8 HRS EA - RJ NOBLE

LE-13- Roller H222 - QTY 1 - 8 HRS EA - RJ NOBLE

LE-09- Skip Loader - QTY 1 - 8 HRS EA - RJ NOBLE

LE-125- Skid Steer - QTY 1 - 8 HRS EA - RJ NOBLE

LE-63- Asphalt Paver - QTY 1 - 8 HRS EA - RJ NOBLE

LE-51- Pickup Truck - QTY 1 - 8 HRS EA - RJ NOBLE

LE-01- Crew Truck - QTY 1 - 8 HRS EA - RJ NOBLE

LE-141- End Dump - QTY 1 - 7 HRS EA - DIII

LE-157- Tack Truck - QTY 1 - 8 HRS EA - RJ NOBLE

LE-42- Utility Truck - QTY 1 - 8 HRS EA - RJ NOBLE

LE-19- Street sweeper - QTY 1 - 8 HRS EA - RJ NOBLE

LE-141- End Dump - QTY 1 - 3.5 HRS EA - DIII

LE-71- Pavement Grinder - QTY 1 - 3.5 HRS EA - PRSI

LL-09- PE - QTY 1 - 8 HRS EA - CTI

LL-08- PM - QTY 1 - 8 HRS EA - RJ NOBLE - RENTAL

## Consolidated Resources

| Resource | Pay Type | Class | Qty | Company | Total Hours |
| --- | --- | --- | --- | --- | --- |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE | 8 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE | 8 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE | 8 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE | 8 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE | 8 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE | 8 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE | 8 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE | 8 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE | 8 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE | 8 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | DIII | 7 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE | 8 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE | 8 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE | 8 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE | 8 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE | 8 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE | 8 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE | 8 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | DIII | 8 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | PRSI | 8 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | HUDSON | 8 |
| LE-83- Equipment-Hauling Trailer | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE | 8 |
| LE-100- Liebherr LB20 Drill Rig | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE | 8 |
| LE-13- Roller H222 | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE | 8 |
| LE-09- Skip Loader | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE | 8 |
| LE-125- Skid Steer | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE | 8 |
| LE-13- Roller H222 | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE | 8 |
| LE-63- Asphalt Paver | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE | 8 |
| LE-13- Roller H222 | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE | 8 |
| LE-63- Asphalt Paver | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE | 8 |
| LE-13- Roller H222 | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE | 8 |
| LE-51- Pickup Truck | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE | 8 |
| LE-51- Pickup Truck | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE | 8 |
| LE-01- Crew Truck | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE | 8 |
| LE-141- End Dump | CS - Cost | LR - Labor Regular Time | 1 | DIII | 7 |
| LE-01- Crew Truck | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE | 8 |
| LE-157- Tack Truck | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE | 8 |
| LE-42- Utility Truck | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE | 8 |
| LE-19- Street sweeper | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE | 8 |
| LE-42- Utility Truck | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE | 8 |
| LE-19- Street sweeper | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE | 8 |
| LE-51- Pickup Truck | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE | 8 |
| LE-51- Pickup Truck | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE | 8 |
| LE-141- End Dump | CS - Cost | LR - Labor Regular Time | 1 | DIII | 3.5 |
| LE-71- Pavement Grinder | CS - Cost | LR - Labor Regular Time | 1 | PRSI | 3.5 |
| LL-09- PE | CS - Cost | LR - Labor Regular Time | 1 | CTI | 8 |