DAILY FIELD REPORT - 06-24-2026

Project: Morena Conveyance Northern
Location: Intersection of Town Center Drive and Nobel Drive (AV-13)
Resident Engineer: Terry West
Weather: High: 72°F, Low: 62°F, Wind: 8 mph W, Drizzle, Partly Cloudy
Hours: 19:30 - 17:00

General Notes:

OHL crews performed a night shift to adjust an existing vault structure to match the road contour, which included implementing a single lane closure for traffic control.

## Activities Detail

Town Center Drive @  (AV-13) - OHLA - Air Release Vault 13 Adjustment  — 531+17

• OHL was on-site for a night shift beginning at 7:30 PM at Town Center Dr(AV-13).

• The crew’s objective was to adjust an existing vault wall height to allowthe vault frame on top of the walls to match the road's contour and elevation.

• Work involved lowering the west side of the vaults walls and raising the east side of the frame and then patch both sides. this would establish proper fall from east to west.

• To accomplish this, the crew first lifted the west side of the vault lid and chipped out the concrete underneath.

• Subsequently, they lifted the east side and placed dobes underneath the lid to create the correct pitch, there laser level was out of batteries so they will verify everything tomorrow and then patch everything after that.

• Traffic control was established, shifting traffic from the number one lane into the number two lane.

• The lane closure began at La Jolla Village Drive, extended southbound, and ended at Town Center Gateway.

• Work hours for the shift were from 7:30 PM to 5:00 AM

Hours: 7:30 PM - 5:00 AM

Manpower:

LL-03- Laborers - QTY 4 - 9.5 HRS EA - OHL

LL-04- Operator - QTY 2 - 9.5 HRS EA - OHL

Equipment:

LE-125- Skid Steer - QTY 1 - 9.5 HRS EA - OHL

LE-51- Pickup Truck - QTY 1 - 9.5 HRS EA - OHL

LE-109- Excavator - QTY 1 - 9.5 HRS EA - OHL

LE-01- Crew Truck - QTY 1 - 9.5 HRS EA - OHL

Light Plant - QTY 1 - 9.5 HRS EA - OHL

LE-23- Super 10 End Dump Truck - QTY 1 - 9.5 HRS EA - OHL

Genesee Appleton to North of SR 52 - RJ Noble - Grind and Overlay — Genesee 368+65 to 406+48 - UTC

• Grind & Overlay — Wednesday, June 24, 2026:

- NB OUTSIDE GENESEE — undefined' depth — 45,887 SF (860 tons)

- NB OUTSIDE GENESEE — undefined' depth — 35,062 SF (657 tons)

Total: 80,949 SF / 1,517 Tons

Actual asphalt placed - 1477 Tons

• Material: 1/2" FIBER MIX ID#21242163F

• Plant: MM LAKESIDE

RJ Noble had traffic control setup from appleton to the top of the hill on the north side of the SR  52 in the northbound lanes

The grind and overlay started approx 65 feet North of the planned start location after being notified that CTS # 30 wires were damaged.

they wrapped up work the paving just before 4:00 AM, ran street sweeper through the area. Traffic control was pulled after street sweeping. the work area was clear around 4:45 AM

I notified RJ noble and OHLA that CTS # 33 was also an issue that would need to be addressed after speaking with Brandon after he walked the area with Cor Pro. I told them that Kris with corpro said the same thing. I then showed them the 4 wire with anodes test station or the 48" and the 6 wire casing test station at the location (CTS # 32 and CTS # 34) CTS # 33 another 5 wire with anodes test station is not installed.

tested both sets of wires that were visible to confirm theywere reading how they should based on what they were labled as, both sets tested how they should.

Even with all this information OHLA still insisted on not skipping the area. I let them know that they would be responsible for any extra work incurred.

Hours: 8:30 PM - 5:00 AM

Manpower:

LL-02- Foreman - QTY 2 - 8.5 HRS EA - RJ NOBLE

LL-04- Operator - QTY 10 - 8.5 HRS EA - RJ NOBLE

LL-03- Laborers - QTY 5 - 8.5 HRS EA - RJ NOBLE

LL-11- Teamster - QTY 10 - 7.8 HRS EA - DIII

LL-03- Laborers - QTY 2 - 9 HRS EA - RJ NOBLE

LL-11- Teamster - QTY 22 - 8 HRS EA - DIII

LL-04- Operator - QTY 2 - 8 HRS EA - PRSI

LL-03- Laborers - QTY 2 - 8.5 HRS EA - HUDSON

Equipment:

LE-13- Roller H222 - QTY 3 - 8.5 HRS EA - RJ NOBLE

LE-09- Skip Loader - QTY 1 - 8.5 HRS EA - RJ NOBLE

LE-125- Skid Steer - QTY 1 - 8.5 HRS EA - RJ NOBLE

LE-63- Asphalt Paver - QTY 2 - 8.5 HRS EA - RJ NOBLE

LE-160- Pup Roller - QTY 1 - 8.5 HRS EA - RJ NOBLE

LE-51- Pickup Truck - QTY 4 - 8.5 HRS EA - RJ NOBLE

LE-01- Crew Truck - QTY 2 - 8.5 HRS EA - RJ NOBLE

LE-23- Super 10 End Dump Truck - QTY 10 - 7.8 HRS EA - DIII

LL-03- Laborers - QTY 4 - 8.5 HRS EA - RJ NOBLE - RENTAL

LE-157- Tack Truck - QTY 1 - 8.5 HRS EA - RJ NOBLE

LE-23- Super 10 End Dump Truck - QTY 1 - 8.5 HRS EA - RJ NOBLE

LE-42- Utility Truck - QTY 2 - 8.5 HRS EA - RJ NOBLE

LE-19- Street sweeper - QTY 2 - 8.5 HRS EA - RJ NOBLE

LE-23- Super 10 End Dump Truck - QTY 22 - 8 HRS EA - DIII

LE-71- Pavement Grinder - QTY 2 - 8 HRS EA - PRSI

LE-19- Street sweeper - QTY 1 - 8.5 HRS EA - CTI

## Consolidated Resources

| Resource | Pay Type | Class | Qty | Company | Total Hours |
| --- | --- | --- | --- | --- | --- |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 4 | OHL | 32 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 4 | OHL | 6 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 2 | OHL | 16 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 2 | OHL | 3 |
| LE-125- Skid Steer | CS - Cost | LR - Labor Regular Time | 1 | OHL | 9.5 |
| LE-51- Pickup Truck | CS - Cost | LR - Labor Regular Time | 1 | OHL | 9.5 |
| LE-109- Excavator | CS - Cost | LR - Labor Regular Time | 1 | OHL | 9.5 |
| LE-01- Crew Truck | CS - Cost | LR - Labor Regular Time | 1 | OHL | 9.5 |
| Light Plant | CS - Cost | LR - Labor Regular Time | 1 | OHL | 9.5 |
| LE-23- Super 10 End Dump Truck | CS - Cost | LR - Labor Regular Time | 1 | OHL | 9.5 |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 2 | RJ NOBLE | 16 |
| LL-02- Foreman | CS - Cost | LO - Labor Overtime | 2 | RJ NOBLE | 1 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 10 | RJ NOBLE | 80 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 10 | RJ NOBLE | 5 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 7 | RJ NOBLE | 56 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 5 | RJ NOBLE | 2.5 |
| LL-11- Teamster | CS - Cost | LR - Labor Regular Time | 10 | DIII | 78 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 2 | RJ NOBLE | 2 |
| LL-11- Teamster | CS - Cost | LR - Labor Regular Time | 22 | DIII | 176 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 2 | PRSI | 16 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 2 | HUDSON | 16 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 2 | HUDSON | 1 |
| LE-13- Roller H222 | CS - Cost | LR - Labor Regular Time | 3 | RJ NOBLE | 25.5 |
| LE-09- Skip Loader | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE | 8.5 |
| LE-125- Skid Steer | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE | 8.5 |
| LE-63- Asphalt Paver | CS - Cost | LR - Labor Regular Time | 2 | RJ NOBLE | 17 |
| LE-160- Pup Roller | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE | 8.5 |
| LE-51- Pickup Truck | CS - Cost | LR - Labor Regular Time | 4 | RJ NOBLE | 34 |
| LE-01- Crew Truck | CS - Cost | LR - Labor Regular Time | 2 | RJ NOBLE | 17 |
| LE-23- Super 10 End Dump Truck | CS - Cost | LR - Labor Regular Time | 10 | DIII | 78 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 4 | RJ NOBLE | 34 |
| LE-157- Tack Truck | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE | 8.5 |
| LE-23- Super 10 End Dump Truck | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE | 8.5 |
| LE-42- Utility Truck | CS - Cost | LR - Labor Regular Time | 2 | RJ NOBLE | 17 |
| LE-19- Street sweeper | CS - Cost | LR - Labor Regular Time | 2 | RJ NOBLE | 17 |
| LE-23- Super 10 End Dump Truck | CS - Cost | LR - Labor Regular Time | 22 | DIII | 176 |
| LE-71- Pavement Grinder | CS - Cost | LR - Labor Regular Time | 2 | PRSI | 16 |
| LE-19- Street sweeper | CS - Cost | LR - Labor Regular Time | 1 | CTI | 8.5 |