DAILY FIELD REPORT - 06-25-2026

Project: Morena Conveyance Northern
Location: GENESEE, EXECUTIVE
Resident Engineer: Terry West
Weather: High: 71°F, Low: 61°F, Wind: 9 mph WNW, Overcast
Hours: 19:30 - 05:00

General Notes:

OHL performed excavation to expose a short conduit wire at Cathodic Test Station #38, preparing the area for a future connection by another contractor.

## Activities Detail

RJ NOBEL - GRIND AND OVERLAY - NB GENESEE OUTSIDE LANE SR 52 EB OFF RAMP TO NORTH OF GOVERNOR — NB GENESSEE AVE / HWY 52 RAMPS - UTC

• Grind & Overlay — Thursday, June 25, 2026:

NB OUTSIDE GENESEE GRIND AND OVERLAY STA.  79,211 SF (1485 tons)

ACTUAL TOTAL: 1,490.76 Tons

• Material: 1/2" FIBER MIX ID#21242163F

• Plant: MM LAKESIDE

STARTED PAVING AT STATION 410+11

TRAFFIC CONTROL WAS SETUP ON THE NORTHBOUND LANES AND AT CROSS STREETS PROTECTING THE #2 LANE, SHIFTING TRAFFIC INTO THE # 1 LANE. THE SR2 WESTBOUND OFFRAMP WAS CLOSED AS WELL.

THE GRIND CREW STARTED UP FIRST MOVING SOUTH TO NORTH UP GENESEE

THE PAVING CREW FOLLOWED BEHIND PAVING THE NUMBER 2 LANE.

ROLLERS FOLLOWED THE PAVING CREW COMPACTING AFTER EACH LIFT.

FINISHED THE EVENING AT STATION 442+08

APPROX 3186 FT PAVED

Hours: 8:30 PM - 5:00 AM

Manpower:

LL-02- Foreman - QTY 2 - 8.5 HRS EA - RJ NOBLE

LL-04- Operator - QTY 10 - 8.5 HRS EA - RJ NOBLE

LL-03- Laborers - QTY 5 - 8.5 HRS EA - RJ NOBLE

LL-11- Teamster - QTY 10 - 7.8 HRS EA - DIII

LL-03- Laborers - QTY 2 - 9 HRS EA - RJ NOBLE

LL-11- Teamster - QTY 22 - 8 HRS EA - DIII

LL-04- Operator - QTY 2 - 8 HRS EA - PRSI

LL-03- Laborers - QTY 2 - 8.5 HRS EA - HUDSON

Equipment:

LE-13- Roller H222 - QTY 3 - 8.5 HRS EA - RJ NOBLE

LE-30- Deere 210L Skip Loader - QTY 1 - 8.5 HRS EA - RJ NOBLE

LE-125- Skid Steer - QTY 1 - 8.5 HRS EA - RJ NOBLE

LE-63- Asphalt Paver - QTY 2 - 8.5 HRS EA - RJ NOBLE

LE-160- Pup Roller - QTY 1 - 8.5 HRS EA - RJ NOBLE

LE-51- Pickup Truck - QTY 4 - 8.5 HRS EA - RJ NOBLE

LE-01- Crew Truck - QTY 2 - 8.5 HRS EA - RJ NOBLE

LE-23- Super 10 End Dump Truck - QTY 10 - 7.8 HRS EA - DIII

LL-03- Laborers - QTY 4 - 8.5 HRS EA - RJ NOBLE - RENTAL

LE-157- Tack Truck - QTY 1 - 8.5 HRS EA - RJ NOBLE

LE-23- Super 10 End Dump Truck - QTY 1 - 8.5 HRS EA - RJ NOBLE

LE-42- Utility Truck - QTY 2 - 8.5 HRS EA - RJ NOBLE

LE-19- Street sweeper - QTY 2 - 8.5 HRS EA - RJ NOBLE

LE-23- Super 10 End Dump Truck - QTY 22 - 8 HRS EA - DIII

LE-71- Pavement Grinder - QTY 2 - 8 HRS EA - PRSI

LE-19- Street sweeper - QTY 1 - 8.5 HRS EA - CTI

Consultants:

Cathodic Test Station (CTS) #38 - OHL - Conduit Repair Prep

• OHL was on-site to address a previous installation issue at Cathodic Test Station (CTS) #38.

• When the test station was originally installed, only three wires were connected; the fourth wire was left short inside the conduit.

• The crew excavated the final 4 feet of the conduit trench to expose the short wire.

• This work was performed to prep the area for Corpro. they will splice the wire and complete the connection to the test station.

• OHL utilized the existing traffic control that was in place from RJ Noble's operations; no new traffic control was set up.

wrapped up work at 1:00 AM

Hours: 7:00 AM - 12:00 PM

Manpower:

LL-03- Laborers - QTY 4 - 5 HRS EA - OHL

LL-02- Foreman - QTY 1 - 5 HRS EA - OHL

LL-04- Operator - QTY 2 - 5 HRS EA - OHL

Equipment:

LE-23- Super 10 End Dump Truck - QTY 1 - 5 HRS EA - OHL

LE-04- Mini Excavator - QTY 1 - 5 HRS EA - OHL

LE-51- Pickup Truck - QTY 1 - 5 HRS EA - OHL

Light Plant - QTY 1 - 5 HRS EA - OHL

LE-125- Skid Steer - QTY 1 - 5 HRS EA - OHL

## Consolidated Resources

| Resource | Pay Type | Class | Qty | Company | Total Hours |
| --- | --- | --- | --- | --- | --- |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 2 | RJ NOBLE | 16 |
| LL-02- Foreman | CS - Cost | LO - Labor Overtime | 2 | RJ NOBLE | 1 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 10 | RJ NOBLE | 80 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 10 | RJ NOBLE | 5 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 7 | RJ NOBLE | 56 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 5 | RJ NOBLE | 2.5 |
| LL-11- Teamster | CS - Cost | LR - Labor Regular Time | 10 | DIII | 78 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 2 | RJ NOBLE | 2 |
| LL-11- Teamster | CS - Cost | LR - Labor Regular Time | 22 | DIII | 176 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 2 | PRSI | 16 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 2 | HUDSON | 16 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 2 | HUDSON | 1 |
| LE-13- Roller H222 | CS - Cost | LR - Labor Regular Time | 3 | RJ NOBLE | 25.5 |
| LE-30- Deere 210L Skip Loader | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE | 8.5 |
| LE-125- Skid Steer | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE | 8.5 |
| LE-63- Asphalt Paver | CS - Cost | LR - Labor Regular Time | 2 | RJ NOBLE | 17 |
| LE-160- Pup Roller | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE | 8.5 |
| LE-51- Pickup Truck | CS - Cost | LR - Labor Regular Time | 4 | RJ NOBLE | 34 |
| LE-01- Crew Truck | CS - Cost | LR - Labor Regular Time | 2 | RJ NOBLE | 17 |
| LE-23- Super 10 End Dump Truck | CS - Cost | LR - Labor Regular Time | 10 | DIII | 78 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 4 | RJ NOBLE | 34 |
| LE-157- Tack Truck | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE | 8.5 |
| LE-23- Super 10 End Dump Truck | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE | 8.5 |
| LE-42- Utility Truck | CS - Cost | LR - Labor Regular Time | 2 | RJ NOBLE | 17 |
| LE-19- Street sweeper | CS - Cost | LR - Labor Regular Time | 2 | RJ NOBLE | 17 |
| LE-23- Super 10 End Dump Truck | CS - Cost | LR - Labor Regular Time | 22 | DIII | 176 |
| LE-71- Pavement Grinder | CS - Cost | LR - Labor Regular Time | 2 | PRSI | 16 |
| LE-19- Street sweeper | CS - Cost | LR - Labor Regular Time | 1 | CTI | 8.5 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 4 | OHL | 20 |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 1 | OHL | 5 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 2 | OHL | 10 |
| LE-23- Super 10 End Dump Truck | CS - Cost | LR - Labor Regular Time | 1 | OHL | 5 |
| LE-04- Mini Excavator | CS - Cost | LR - Labor Regular Time | 1 | OHL | 5 |
| LE-51- Pickup Truck | CS - Cost | LR - Labor Regular Time | 1 | OHL | 5 |
| Light Plant | CS - Cost | LR - Labor Regular Time | 1 | OHL | 5 |
| LE-125- Skid Steer | CS - Cost | LR - Labor Regular Time | 1 | OHL | 5 |