DAILY FIELD REPORT - 06-28-2026

Project: Morena Conveyance Northern
Location: Genesee 433+23 to 369+00
Resident Engineer: Terry West
Weather: High: 65°F, Low: 58°F, Wind: 4 mph S, Overcast
Hours: 19:30 - 04:30

## Activities Detail

Genesee – RJ Noble – Grind and Pave

NB Genesee Inside Lanes - pipeline start to Governor - 1.18 Miles 369+00 to 432+32

• Grind & Overlay — Sunday, June 28, 2026:

Estimated on schedule

- SB INSIDE GENESEE — 66,879 SF (1253.981 tons)

Total: 255,032 SF / 4,781.85 Tons

• Material: 1/2" FIBER MIX ID#21242163F

• Plant: MM LAKESIDE

• Material: GRINDS TO MIRAMAR

• Actual Asphalt Laid: 1487.11 tons

• Traffic Control: Traffic control setup in Northbound and Southbound directions closing the #1 lanes from north of governor to appleton.

• RJ Noble started the grind from just inside the governor/genesee intersection heading south in the inside lanes.

the grind and overlay 1.2 miles to just before the end of the row at 369+00

81 loads of 1/2" HMA asphalt laid for a total of 1478.11 tons. Total to date @ 8827.95 tons of 1/2"

Hours: 7:30 PM - 4:30 AM

Manpower:

LL-02- Foreman - QTY 2 - 9 HRS EA - RJ NOBLE

LL-04- Operator - QTY 10 - 9 HRS EA - RJ NOBLE

LL-03- Laborers - QTY 6 - 9 HRS EA - RJ NOBLE

LL-04- Operator - QTY 2 - 9 HRS EA - PRSI

LL-03- Laborers - QTY 3 - 9 HRS EA - HUDSON

Equipment:

LE-63- Asphalt Paver - QTY 3 - 9.5 HRS EA - RJ NOBLE

LE-13- Roller H222 - QTY 4 - 9.5 HRS EA - RJ NOBLE

LE-09- Skip Loader - QTY 1 - 9.5 HRS EA - RJ NOBLE

LE-125- Skid Steer - QTY 1 - 9.5 HRS EA - RJ NOBLE

LE-30- Deere 210L Skip Loader - QTY 1 - 9.5 HRS EA - RJ NOBLE

LE-51- Pickup Truck - QTY 5 - 9.5 HRS EA - RJ NOBLE

LE-01- Crew Truck - QTY 1 - 9.5 HRS EA - RJ NOBLE

LL-03- Laborers - QTY 4 - 9.5 HRS EA - RJ NOBLE - RENTAL

LE-157- Tack Truck - QTY 1 - 9.5 HRS EA - RJ NOBLE

LE-23- Super 10 End Dump Truck - QTY 1 - 9.5 HRS EA - RJ NOBLE

LE-42- Utility Truck - QTY 2 - 9.5 HRS EA - RJ NOBLE

LE-19- Street sweeper - QTY 2 - 9.5 HRS EA - RJ NOBLE

LE-71- Pavement Grinder - QTY 2 - 9 HRS EA - PRSI

LE-19- Street sweeper - QTY 1 - 9.5 HRS EA - CTI

## Consolidated Resources

| Resource | Pay Type | Class | Qty | Company | Total Hours |
| --- | --- | --- | --- | --- | --- |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 2 | RJ NOBLE | 16 |
| LL-02- Foreman | CS - Cost | LO - Labor Overtime | 2 | RJ NOBLE | 2 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 10 | RJ NOBLE | 80 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 10 | RJ NOBLE | 10 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 6 | RJ NOBLE | 48 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 6 | RJ NOBLE | 6 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 2 | PRSI | 16 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 2 | PRSI | 2 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 3 | HUDSON | 24 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 3 | HUDSON | 3 |
| LE-63- Asphalt Paver | CS - Cost | LR - Labor Regular Time | 3 | RJ NOBLE | 28.5 |
| LE-13- Roller H222 | CS - Cost | LR - Labor Regular Time | 4 | RJ NOBLE | 38 |
| LE-09- Skip Loader | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE | 9.5 |
| LE-125- Skid Steer | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE | 9.5 |
| LE-30- Deere 210L Skip Loader | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE | 9.5 |
| LE-51- Pickup Truck | CS - Cost | LR - Labor Regular Time | 5 | RJ NOBLE | 47.5 |
| LE-01- Crew Truck | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE | 9.5 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 4 | RJ NOBLE | 38 |
| LE-157- Tack Truck | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE | 9.5 |
| LE-23- Super 10 End Dump Truck | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE | 9.5 |
| LE-42- Utility Truck | CS - Cost | LR - Labor Regular Time | 2 | RJ NOBLE | 19 |
| LE-19- Street sweeper | CS - Cost | LR - Labor Regular Time | 2 | RJ NOBLE | 19 |
| LE-71- Pavement Grinder | CS - Cost | LR - Labor Regular Time | 2 | PRSI | 18 |
| LE-19- Street sweeper | CS - Cost | LR - Labor Regular Time | 1 | CTI | 9.5 |