DAILY FIELD REPORT - 07-13-2026

Project: Morena Conveyance Northern
Location: Genesee Avenue Median 6, Town Center Area (Air Release Vault 14), Blow-off #7, Median 2, Median 3
Resident Engineer: Terry West
Weather: 
Hours: 06:30 - 15:00

General Notes:

Crews from OHL and Picket Fences performed soil stripping, valve work, and concrete prep at multiple median and utility locations.

## Activities Detail

Genesee Avenue Median 6 - OHL - Soil Stripping

• An OHL crew was located at the Genesee Avenue median, Median 6.

• The crew utilized a mini excavator and a skid steer to strip native soil from the landscaped area of the medianand load into the dump truck.

• This work is in preparation for the future placement of topsoil and plants.

• OHL is assisting Picket Fences on this task, this was all OHLA labor

Hours: 7:00 AM - 3:30 PM

Manpower:

LL-04- Operator - QTY 1 - 8 HRS EA - OHL

LL-03- Laborers - QTY 3 - 8 HRS EA - OHL

LL-02- Foreman - QTY 1 - 8 HRS EA - OHL

Equipment:

LE-04- Mini Excavator - QTY 1 - 8 HRS EA - OHL

LE-125- Skid Steer - QTY 1 - 8 HRS EA - OHL

LE-01- Crew Truck - QTY 1 - 8 HRS EA - OHL

Town Center Area (ARV 14) & Blow-off #7 - OHL - Valve Work

• An OHL crew began work at the Town Center area, starting at Air Release Vault 14, where they installed bolts and removed a 6-inch valve.

• The crew then relocated to Blow-off #7 to install the 6-inch valve.

•  They already had a 2nd 6" valve that was to be installed on the vertical piping coming up from the pipeline. to be installed before the air vac valve.

• the 4" valves currently installed were removed and preparation to install the 6" valves began.

• Time ran out in the day before they got the valves installed.

• cleaned up and off the job with traffic control picked up at 4:00 PM

Hours: 7:00 AM - 3:30 PM

Manpower:

LL-04- Operator - QTY 1 - 8 HRS EA - OHL

LL-03- Laborers - QTY 3 - 8 HRS EA - OHL

LL-02- Foreman - QTY 1 - 8 HRS EA - OHL

Median 2 and Median 3 - Picket Fences - Concrete & Subgrade Prep

• A third crew from Picket Fences was working in Median 2 and Median 3.

• @ median 3 the crew was installing forms and stripping out native soil and compacting sub grade, they were getting ready for concrete pour tomorrow.

• At the south end of the median, they were prepping subgrade, which involved stripping out native soil, grading, and compacting the area.

Hours: 6:30 AM - 3:00 PM

Manpower:

LL-03- Laborers - QTY 5 - 8 HRS EA - Picket Fences

LL-02- Foreman - QTY 1 - 8 HRS EA - Picket Fences

LL-01- Superintendent - QTY 1 - 8 HRS EA - Picket Fences

LL-15- Cement Mason - QTY 2 - 8 HRS EA - Picket Fences

Equipment:

LE-125- Skid Steer - QTY 1 - 8 HRS EA - Picket Fences

LE-04- Mini Excavator - QTY 1 - 8 HRS EA - Picket Fences

LE-01- Crew Truck - QTY 1 - 8 HRS EA - Picket Fences

## Consolidated Resources

| Resource | Pay Type | Class | Qty | Company | Total Hours |
| --- | --- | --- | --- | --- | --- |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | OHL | 8 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 3 | OHL | 24 |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 1 | OHL | 8 |
| LE-04- Mini Excavator | CS - Cost | LR - Labor Regular Time | 1 | OHL | 8 |
| LE-125- Skid Steer | CS - Cost | LR - Labor Regular Time | 1 | OHL | 8 |
| LE-01- Crew Truck | CS - Cost | LR - Labor Regular Time | 1 | OHL | 8 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | OHL | 8 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 3 | OHL | 24 |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 1 | OHL | 8 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 5 | Picket Fences | 40 |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 1 | Picket Fences | 8 |
| LL-01- Superintendent | CS - Cost | LR - Labor Regular Time | 1 | Picket Fences | 8 |
| LL-15- Cement Mason | CS - Cost | LR - Labor Regular Time | 2 | Picket Fences | 16 |
| LE-125- Skid Steer | CS - Cost | LR - Labor Regular Time | 1 | Picket Fences | 8 |
| LE-04- Mini Excavator | CS - Cost | LR - Labor Regular Time | 1 | Picket Fences | 8 |
| LE-01- Crew Truck | CS - Cost | LR - Labor Regular Time | 1 | Picket Fences | 8 |