DAILY FIELD REPORT - 07-14-2026

Project: Morena Conveyance Northern
Location: Median 3 - Genesee Drive, Town Center - Blow-off Vault #7, Median 2
Resident Engineer: Terry West
Weather: High: 74°F, Low: 66°F, Wind: 10 mph NW, Partly Cloudy
Hours: 0:30 - 15:00

General Notes:

Crews performed pervious concrete work in Median 3, valve and piping modifications at the Town Center Blow-off vault, and continued earthwork and grading in Median 2.

## Activities Detail

Median 3 - Genesee Drive - OHL - Pervious Concrete

• An OHL crew was on-site pouring pervious concrete in Median 3 on Genesee Drive.

• Work began at the north end of the median, located just south of Governor Drive.

• One section of pervious concrete completed today. .

• Due to properties of the pervious concrete, only one concrete chute could be utilized, even with one chute the concrete had to be moved by shovel down into the forms.

• To install the decorative cobble, the crew first had to dig out small sections within the wet pervious concrete.

• The cobble was then pounded into place with a sledgehammer while the pervious concrete was being finished.

Manpower:

LL-02- Foreman - QTY 1 - 8 HRS EA - OHL

LL-15- Cement Mason - QTY 3 - 8 HRS EA - OHL

Equipment:

LE-27- JLG Lift - QTY 1 - 8 HRS EA - OHL

LE-51- Pickup Truck - QTY 1 - 8 HRS EA - OHL

Town Center - Blow-2off Vault #7/Air Release Vault 12 - Valve Swaps — 497+94 & 512+39

• Crew continued work from the previous day at Blow-off Vault #7.

• Removed two existing overside 6-inch valves with 4" flange plug valves  and installed two standard 4-inch plug valves.

• Installed additional bolts to secure all flanges; however, not the permanent bolts

• Mobilized to Air Release Vault #12 at approximately 12:30 PM.

• Set up traffic control and removed the vault lids.

• Began installation the two oversized 6-inch valve bodies with 4" flanges plus two more of the same valves in air release vault # 12 to have all 4 plug valves in air release vault 12 be oversized.

• they got 2 of the valves partially bolted in the vault, still need to finish bolting up the other 2 valves and the rest of the pipe spools to complete the vault.

Hours: 6:30 AM - 4:30 PM

Manpower:

LL-02- Foreman - QTY 1 - 9.5 HRS EA - OHL NA

LL-03- Laborers - QTY 3 - 9.5 HRS EA - OHL NA

Equipment:

LE-32- Skytrak Forklift - QTY 1 - 9.5 HRS EA - OHL NA

LE-51- Pickup Truck - QTY 2 - 9.5 HRS EA - OHL NA

LE-70- Generator - QTY 1 - 9.5 HRS EA - OHL NA

LE-111- Trailer Mounted Blower - QTY 1 - 9.5 HRS EA - OHL NA

Median 3 & 2 - Picket Fences - Earthwork & Grading

• The Picket Fences crew was working in Median 3 & 2.

• Median 3 is being graded at the south end with native soil being loaded into a dump truck and hauled off.

• At median 2 the crew continued removing native soil from the median with and grading to get down to sub grade before forming for concrete.

Manpower:

LL-02- Foreman - QTY 1 - 8 HRS EA - Picket Fences

LL-03- Laborers - QTY 4 - 8 HRS EA - Picket Fences

LL-04- Operator - QTY 1 - 8 HRS EA - Picket Fences

LL-01- Superintendent - QTY 1 - 8 HRS EA - Picket Fences

Equipment:

LE-04- Mini Excavator - QTY 1 - 8 HRS EA - Picket Fences

LE-125- Skid Steer - QTY 1 - 8 HRS EA - Picket Fences

LE-51- Pickup Truck - QTY 1 - 8 HRS EA - Picket Fences

## Consolidated Resources

| Resource | Pay Type | Class | Qty | Company | Total Hours |
| --- | --- | --- | --- | --- | --- |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 1 | OHL | 8 |
| LL-15- Cement Mason | CS - Cost | LR - Labor Regular Time | 3 | OHL | 24 |
| LE-27- JLG Lift | CS - Cost | LR - Labor Regular Time | 1 | OHL | 8 |
| LE-51- Pickup Truck | CS - Cost | LR - Labor Regular Time | 1 | OHL | 8 |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-02- Foreman | CS - Cost | LO - Labor Overtime | 1 | OHL NA | 1.5 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 3 | OHL NA | 24 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 3 | OHL NA | 4.5 |
| LE-32- Skytrak Forklift | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 9.5 |
| LE-51- Pickup Truck | CS - Cost | LR - Labor Regular Time | 2 | OHL NA | 19 |
| LE-70- Generator | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 9.5 |
| LE-111- Trailer Mounted Blower | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 9.5 |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 1 | Picket Fences | 8 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 4 | Picket Fences | 32 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 1 | Picket Fences | 8 |
| LL-01- Superintendent | CS - Cost | LR - Labor Regular Time | 1 | Picket Fences | 8 |
| LE-04- Mini Excavator | CS - Cost | LR - Labor Regular Time | 1 | Picket Fences | 8 |
| LE-125- Skid Steer | CS - Cost | LR - Labor Regular Time | 1 | Picket Fences | 8 |
| LE-51- Pickup Truck | CS - Cost | LR - Labor Regular Time | 1 | Picket Fences | 8 |