DAILY FIELD REPORT - 07-02-2026

Project: Morena Conveyance Northern
Location: Nobel Dr & Town Centre Dr.
Resident Engineer: Terry West
Weather: High: 72°F, Low: 58°F, Wind: 8 mph WNW, Clear
Hours: 19:30 - 05:30

General Notes:

night work

## Activities Detail

Nobel and Town Centre - RJ Noble - Grind and Overlay — 488+67.14 to 500+57.08 and 506+78.74 to 527+21.38

• Grind & Overlay — Thursday, July 2, 2026:

488+67.14 to 500+57.08

506+78.74 to 527+21.38

- WB INSIDE NOBEL — 27,261 SF (estimated 459 tons)

- NB OUTSIDE TOWNE CENTER — 47,409 SF (Estimated 889 tons)

Total: 78,670 SF / 1,475 Tons

• Material: 1/2" FIBER MIX ID#21242163F

• Plant: MM LAKESIDE

• Material: GRINDS TO MIRAMAR

• Actual Asphalt Laid: 1348.16 tons

• Traffic Control: Traffic control was setup in the #1 lane on the westbound side of nobel, shifting traffic into the #2 lane from the east side of town centre dr to the west side of Genesee. Northbound and southbound turns and through traffic was blocked at genesee and town centre dr.  Detours were setup and flaggers were at both locations assisting traffic. On Town centre the #2 lane as closed shifting traffic into the # 1 lane from Nobel west until after town centre gateway. Two cars were parked in a red zone on town centre gateway that was impeding on the paving. PD was called, they showed up then had to leave right away. One of the vehicles owners just happened to show up, the 2nd vehicle owner was located and called, he came and moved the vehicle about an 30 min before RJ Noble showed up on town centre in the area. paving went as scheduled.

• The grind and overlay began @ 488+67, offset 142.42L, onthe West side of Genesee in the #1 lane on nobel, the inside lanes eastbound lanes through the intersection were included as well. after getting through the intersection they progressed east down the west bound # 1 lane up to Via Las Ramblas, where they left off at on day 1 at 500+57. At that point Nobel was completed, they stopped and moved over to Town Centre in the #2 lane from the cross walk @ 506+78 offset 46.94R and headed North. They ended the night at 527+21.38 offset 35.15R

Hours: 7:30 PM - 5:30 AM

Manpower:

LL-02- Foreman - QTY 2 - 10 HRS EA - RJ NOBLE - SOUTH

LL-04- Operator - QTY 10 - 10 HRS EA - RJ NOBLE - SOUTH

LL-03- Laborers - QTY 5 - 10 HRS EA - RJ NOBLE - SOUTH

LL-11- Teamster - QTY 10 - 9.3 HRS EA - DIII, SD GOLD

LL-03- Laborers - QTY 2 - 10.5 HRS EA - RJ NOBLE - SOUTH

LL-11- Teamster - QTY 20 - 9.5 HRS EA - DIII

LL-04- Operator - QTY 2 - 9.5 HRS EA - PRSI

LL-03- Laborers - QTY 2 - 10 HRS EA - HUDSON

Equipment:

LE-113- McElroy Tracstar 16-inch Fusion Machine - QTY 1 - 10 HRS EA - RJ NOBLE - SOUTH

LE-09- Skip Loader - QTY 1 - 10 HRS EA - RJ NOBLE - SOUTH

LE-125- Skid Steer - QTY 1 - 10 HRS EA - RJ NOBLE - SOUTH

LE-13- Roller H222 - QTY 3 - 10 HRS EA - RJ NOBLE - SOUTH

LE-63- Asphalt Paver - QTY 2 - 10 HRS EA - RJ NOBLE - SOUTH

LE-30- Deere 210L Skip Loader - QTY 1 - 10 HRS EA - RJ NOBLE - SOUTH

LE-51- Pickup Truck - QTY 5 - 10 HRS EA - RJ NOBLE - SOUTH

LE-01- Crew Truck - QTY 2 - 10 HRS EA - RJ NOBLE - SOUTH

LE-01- Crew Truck - QTY 10 - 10 HRS EA - DIII, SD GOLD

LL-03- Laborers - QTY 4 - 10 HRS EA - RJ NOBLE - SOUTH - RENTAL

LE-157- Tack Truck - QTY 1 - 10 HRS EA - RJ NOBLE - SOUTH

LE-42- Utility Truck - QTY 2 - 10 HRS EA - RJ NOBLE - SOUTH

LE-19- Street sweeper - QTY 2 - 10 HRS EA - RJ NOBLE - SOUTH

LE-01- Crew Truck - QTY 20 - 10 HRS EA - DIII

LE-71- Pavement Grinder - QTY 2 - 10 HRS EA - PRSI

LE-19- Street sweeper - QTY 1 - 10 HRS EA - CTI

Consultants:

LL-42- Asphalt QC Tech - QTY 1 - 10 HRS EA - The Quality Firm

## Consolidated Resources

| Resource | Pay Type | Class | Qty | Company | Total Hours |
| --- | --- | --- | --- | --- | --- |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 2 | RJ NOBLE - SOUTH | 16 |
| LL-02- Foreman | CS - Cost | LO - Labor Overtime | 2 | RJ NOBLE - SOUTH | 4 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 10 | RJ NOBLE - SOUTH | 80 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 10 | RJ NOBLE - SOUTH | 20 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 7 | RJ NOBLE - SOUTH | 56 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 5 | RJ NOBLE - SOUTH | 10 |
| LL-11- Teamster | CS - Cost | LR - Labor Regular Time | 10 | DIII, SD GOLD | 80 |
| LL-11- Teamster | CS - Cost | LO - Labor Overtime | 10 | DIII, SD GOLD | 13 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 2 | RJ NOBLE - SOUTH | 5 |
| LL-11- Teamster | CS - Cost | LR - Labor Regular Time | 20 | DIII | 160 |
| LL-11- Teamster | CS - Cost | LO - Labor Overtime | 20 | DIII | 30 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 2 | PRSI | 16 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 2 | PRSI | 3 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 2 | HUDSON | 16 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 2 | HUDSON | 4 |
| LE-113- McElroy Tracstar 16-inch Fusion Machine | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 10 |
| LE-09- Skip Loader | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 10 |
| LE-125- Skid Steer | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 10 |
| LE-13- Roller H222 | CS - Cost | LR - Labor Regular Time | 3 | RJ NOBLE - SOUTH | 30 |
| LE-63- Asphalt Paver | CS - Cost | LR - Labor Regular Time | 2 | RJ NOBLE - SOUTH | 20 |
| LE-30- Deere 210L Skip Loader | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 10 |
| LE-51- Pickup Truck | CS - Cost | LR - Labor Regular Time | 5 | RJ NOBLE - SOUTH | 50 |
| LE-01- Crew Truck | CS - Cost | LR - Labor Regular Time | 2 | RJ NOBLE - SOUTH | 20 |
| LE-01- Crew Truck | CS - Cost | LR - Labor Regular Time | 10 | DIII, SD GOLD | 100 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 4 | RJ NOBLE - SOUTH | 40 |
| LE-157- Tack Truck | CS - Cost | LR - Labor Regular Time | 1 | RJ NOBLE - SOUTH | 10 |
| LE-42- Utility Truck | CS - Cost | LR - Labor Regular Time | 2 | RJ NOBLE - SOUTH | 20 |
| LE-19- Street sweeper | CS - Cost | LR - Labor Regular Time | 2 | RJ NOBLE - SOUTH | 20 |
| LE-01- Crew Truck | CS - Cost | LR - Labor Regular Time | 20 | DIII | 200 |
| LE-71- Pavement Grinder | CS - Cost | LR - Labor Regular Time | 2 | PRSI | 20 |
| LE-19- Street sweeper | CS - Cost | LR - Labor Regular Time | 1 | CTI | 10 |
| LL-42- Asphalt QC Tech | CS - Cost | LR - Labor Regular Time | 1 | The Quality Firm | 8 |
| LL-42- Asphalt QC Tech | CS - Cost | LO - Labor Overtime | 1 | The Quality Firm | 2 |