DAILY FIELD REPORT - 07-05-2026

Project: Morena Conveyance Northern
Resident Engineer: Terry West
Weather: High: 74°F, Low: 64°F, Wind: 9 mph WNW, Overcast
Hours: 06:30 - 15:00

General Notes:

RJ Noble will be continueing North on Town Centre and then east down executive. Lights were not on flash tonight, it looks like no request was sent. I sent a request for tomorrow night and will update the request for the rest of the week tomorrow after Fabian sends their schedule as it sits now.

## Activities Detail

Town Centre and Executive - RJ Noble - Grind and Overlay —  527+21.38. to 556+47

• Grind & Overlay — Sunday, July 5, 2026:

527+21.38. to 556+47

- NB OUTSIDE TOWN CENTER — 43,518 SF (816 tons)

- EB OUTSIDE EXECUTIVE — 19,068 SF (358 tons)

Total: 62,586 SF / 1,174 Tons

• Material: 1/2" FIBER MIX ID#21242163F

• Plant: MM LAKESIDE

• Material: GRINDS TO MIRAMAR

• Asphalt Laid: 1220.29 tons

• Traffic Control: Traffic control was setup from South of Town Centre Gateway going north up the outside Northbound lane of town centre, shifting traffic into the #1 lane all the way up to executive. At executive, the traffic control turned East and headed east towards judicial, still in the outside lane and shifting traffic into the #1 lane. No directions were completely closed at any intersections tonight. The lights were not set to flash tonight; I sent an email to request flash on Town Centre and La Jolla Village, Town Centre and Executive, and Executive and Judicial for Monday night.

• The Grind and overlay began where they left off Thursday night, in the outside NB lane of Town Centre at  527+21.38. They worked there way North up to Executive. On executive they continued in the outside lane progressing east down towards judicial. The picked up about 10 feet of judicial in the intersection South of executive, contnued through judicial and then stopped at 556+47 for a totla length of 2646.59

The quality firm was on site testing compaction through the night.

concrete encountered  - 19848 SQ FT

Hours: 8:00 AM - 5:00 AM

Manpower:

LL-02- Foreman - QTY 1 - 9.5 HRS EA - OHLA

LL-04- Operator - QTY 9 - 9.5 HRS EA - OHLA

LL-04- Operator - QTY 1 - 10.5 HRS EA - OHLA

LL-03- Laborers - QTY 8 - 9.5 HRS EA - OHLA

LL-11- Teamster - QTY 8 - 8.8 HRS EA - DIII

LL-03- Laborers - QTY 2 - 10 HRS EA - OHLA

LL-11- Teamster - QTY 18 - 21 HRS EA - DIII

LL-04- Operator - QTY 2 - 9 HRS EA - PRSI

Equipment:

LE-13- Roller H222 - QTY 2 - 9.5 HRS EA - OHLA

LE-09- Skip Loader - QTY 1 - 9.5 HRS EA - OHLA

LE-125- Skid Steer - QTY 1 - 9.5 HRS EA - OHLA

LE-63- Asphalt Paver - QTY 2 - 9.5 HRS EA - OHLA

LE-160- Pup Roller - QTY 1 - 9.5 HRS EA - OHLA

LE-113- McElroy Tracstar 16-inch Fusion Machine - QTY 1 - 9.5 HRS EA - OHLA

LE-30- Deere 210L Skip Loader - QTY 1 - 9.5 HRS EA - OHLA

LE-51- Pickup Truck - QTY 3 - 9.5 HRS EA - OHLA

LE-01- Crew Truck - QTY 1 - 9.5 HRS EA - OHLA

LE-01- Crew Truck - QTY 8 - 8.8 HRS EA - DIII

LL-03- Laborers - QTY 3 - 9.5 HRS EA - OHLA - RENTAL

LE-42- Utility Truck - QTY 2 - 9.5 HRS EA - OHLA

LE-19- Street sweeper - QTY 1 - 9.5 HRS EA - OHLA

LE-01- Crew Truck - QTY 18 - 21 HRS EA - DIII

LE-71- Pavement Grinder - QTY 2 - 9 HRS EA - PRSI

Consultants:

LL-42- Asphalt QC Tech - QTY 1 - 8.5 HRS EA - The Quality Firm

## Consolidated Resources

| Resource | Pay Type | Class | Qty | Company | Total Hours |
| --- | --- | --- | --- | --- | --- |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 8 |
| LL-02- Foreman | CS - Cost | LO - Labor Overtime | 1 | OHL NA | 1.5 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 10 | OHL NA | 80 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 9 | OHL NA | 13.5 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 1 | OHL NA | 2.5 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 10 | OHL NA | 80 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 8 | OHL NA | 12 |
| LL-11- Teamster | CS - Cost | LR - Labor Regular Time | 26 | DIII | 208 |
| LL-11- Teamster | CS - Cost | LO - Labor Overtime | 8 | DIII | 6.4 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 2 | OHL NA | 4 |
| LL-11- Teamster | CS - Cost | LO - Labor Overtime | 18 | DIII | 234 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 2 | PRSI | 16 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 2 | PRSI | 2 |
| LE-13- Roller H222 | CS - Cost | LR - Labor Regular Time | 2 | OHL NA | 19 |
| LE-09- Skip Loader | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 9.5 |
| LE-125- Skid Steer | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 9.5 |
| LE-63- Asphalt Paver | CS - Cost | LR - Labor Regular Time | 2 | OHL NA | 19 |
| LE-160- Pup Roller | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 9.5 |
| LE-113- McElroy Tracstar 16-inch Fusion Machine | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 9.5 |
| LE-30- Deere 210L Skip Loader | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 9.5 |
| LE-51- Pickup Truck | CS - Cost | LR - Labor Regular Time | 3 | OHL NA | 28.5 |
| LE-01- Crew Truck | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 9.5 |
| LE-01- Crew Truck | CS - Cost | LR - Labor Regular Time | 8 | DIII | 70.4 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 3 | OHL NA | 28.5 |
| LE-42- Utility Truck | CS - Cost | LR - Labor Regular Time | 2 | OHL NA | 19 |
| LE-19- Street sweeper | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 9.5 |
| LE-01- Crew Truck | CS - Cost | LR - Labor Regular Time | 18 | DIII | 378 |
| LE-71- Pavement Grinder | CS - Cost | LR - Labor Regular Time | 2 | PRSI | 18 |
| LL-42- Asphalt QC Tech | CS - Cost | LR - Labor Regular Time | 1 | The Quality Firm | 8 |
| LL-42- Asphalt QC Tech | CS - Cost | LO - Labor Overtime | 1 | The Quality Firm | 0.5 |