DAILY FIELD REPORT - 07-06-2026

Project: Morena Conveyance Northern
Location: Executive Dr and Town Centre Dr.
Resident Engineer: Terry West
Weather: High: 72°F, Low: 50°F, Clear
Hours: 19:30 - 03:30

## Activities Detail

Executive Dr. and Town Centre Dr. —  528+17 to 548+48

• Grind & Overlay — Monday, July 6, 2026:

Estimate

- WB OUTSIDE EXECUTIVE — 17,467 SF (328 tons)

- SB OUTSIDE TOWN CENTER — 33,965 SF (637 tons)

Total: 51,432 SF / 965 Tons

Actual

- WB OUTSIDE EXECUTIVE — 19812.24 SF (372 tons)

- SB OUTSIDE TOWN CENTER — 34,713.49 SF (651 tons)

Total: 54525.73 SF / 1023.79 Tons

• Material: 1/2" FIBER MIX ID#21242163F

• Plant: MM LAKESIDE

• Material: GRINDS TO MIRAMAR

• Asphalt Laid:

• Traffic Control: traffic control setup closing the outside West bound lanes of executive from 10' East of judicial to the West side of town centre and executive intersection, shifting traffic into the#1 lane. traffic control setup on Town Centre Dr. in outside southbound lanes from the north side of executive south to 100' south of town centre gateway, shifting traffic into the #1 lane. 3 cars had to be towed due to parking in a no park zone where signs had been up since June 30th. PD was called, they wrote each car a ticket first then towed them.

• RJ noble started the grind and overlay at judicial and executive about 10' east of the intersection then worked their way West. they took care of the side streets for judicial, Town center, and executive as they passed each one.

Concrete encountered tonight - 16779

Hours: 7:00 PM - 5:00 AM

Manpower:

LL-02- Foreman - QTY 2 - 9.5 HRS EA - OHLA

LL-04- Operator - QTY 11 - 9.5 HRS EA - OHLA

LL-03- Laborers - QTY 10 - 9.5 HRS EA - OHLA

LL-04- Operator - QTY 2 - 9.5 HRS EA - PRSI

Equipment:

LE-113- McElroy Tracstar 16-inch Fusion Machine - QTY 1 - 9.5 HRS EA - OHLA

LE-13- Roller H222 - QTY 2 - 9.5 HRS EA - OHLA

LE-02- CAT 950 Wheel Loader - QTY 1 - 9.5 HRS EA - OHLA

LE-125- Skid Steer - QTY 1 - 9.5 HRS EA - OHLA

LE-160- Pup Roller - QTY 1 - 9.5 HRS EA - OHLA

LE-63- Asphalt Paver - QTY 2 - 9.5 HRS EA - OHLA

LE-51- Pickup Truck - QTY 4 - 9.5 HRS EA - OHLA

LE-19- Street sweeper - QTY 1 - 9.5 HRS EA - OHLA

LE-42- Utility Truck - QTY 1 - 9.5 HRS EA - OHLA

LE-71- Pavement Grinder - QTY 2 - 9 HRS EA - PRSI

LL-03- Laborers - QTY 1 - 9.5 HRS EA - OHLA - RENTAL

Consultants:

## Consolidated Resources

| Resource | Pay Type | Class | Qty | Company | Total Hours |
| --- | --- | --- | --- | --- | --- |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 2 | OHL NA | 16 |
| LL-02- Foreman | CS - Cost | LO - Labor Overtime | 2 | OHL NA | 3 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 11 | OHL NA | 88 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 11 | OHL NA | 16.5 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 10 | OHL NA | 80 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 10 | OHL NA | 15 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 2 | PRSI | 16 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 2 | PRSI | 3 |
| LE-113- McElroy Tracstar 16-inch Fusion Machine | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 9.5 |
| LE-13- Roller H222 | CS - Cost | LR - Labor Regular Time | 2 | OHL NA | 19 |
| LE-02- CAT 950 Wheel Loader | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 9.5 |
| LE-125- Skid Steer | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 9.5 |
| LE-160- Pup Roller | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 9.5 |
| LE-63- Asphalt Paver | CS - Cost | LR - Labor Regular Time | 2 | OHL NA | 19 |
| LE-51- Pickup Truck | CS - Cost | LR - Labor Regular Time | 4 | OHL NA | 38 |
| LE-19- Street sweeper | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 9.5 |
| LE-42- Utility Truck | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 9.5 |
| LE-71- Pavement Grinder | CS - Cost | LR - Labor Regular Time | 2 | PRSI | 18 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 9.5 |